{"text_format":"3","workbook":"xlsx","n_sheets":18,"sheets":["CALENDARIO PARADAS BUDGET","CALENDARIO PARADAS REAL","CALENDARIO PARADAS FORECAST","ANDON PROY.","ANDON","ANDON PROY","ANDON PROY V1","ANDON REAL","PLAN ACTIVIDADES PARADAS","PROYECCION ACTIVIDADES PARADAS","HORAS PARADAS","DISP_PLANTA","MTTR","MTBF","GRAF HORAS PLC","DISP_PLANTA_SEM","MTTR_SEM","MTBF_SEM"],"not_rendered":{"charts":18,"images":1,"external_links":8,"defined_names":386,"comments":1},"read":"whole","date_system":"1900"}

{"sheet":"CALENDARIO PARADAS BUDGET","index":0,"n_rows":117,"n_cols":9,"rows_kept":117,"hidden":true,"merged":[[0,0,0,8],[3,0,10,0],[3,1,4,1],[5,1,6,1],[7,1,8,1],[9,1,10,1],[12,0,19,0],[12,1,13,1],[14,1,15,1],[16,1,17,1],[18,1,19,1],[21,0,30,0],[21,1,22,1],[23,1,24,1],[25,1,26,1],[27,1,28,1],[29,1,30,1],[32,0,39,0],[32,1,33,1],[34,1,35,1],[36,1,37,1],[38,1,39,1],[41,0,50,0],[41,1,42,1],[43,1,44,1],[45,1,46,1],[47,1,48,1],[49,1,50,1],[52,0,59,0],[52,1,53,1],[54,1,55,1],[56,1,57,1],[58,1,59,1],[61,0,68,0],[61,1,62,1],[63,1,64,1],[65,1,66,1],[67,1,68,1],[70,0,79,0],[70,1,71,1],[72,1,73,1],[74,1,75,1],[76,1,77,1],[78,1,79,1],[81,0,88,0],[81,1,82,1],[83,1,84,1],[85,1,86,1],[87,1,88,1],[90,0,97,0],[90,1,91,1],[92,1,93,1],[94,1,95,1],[96,1,97,1],[99,0,108,0],[99,1,100,1],[101,1,102,1],[103,1,104,1],[105,1,106,1],[107,1,108,1],[110,0,117,0],[110,1,111,1],[112,1,113,1],[114,1,115,1],[116,1,117,1]]}
["CALENDARIO PARADAS PLANTA PESQUERA - 2018"]
[]
[null,null,"LUNES","MARTES","MIERCOLES","JUEVES","VIERNES","SABADO","DOMINGO"]
["ENERO",1,"2018-01-01","2018-01-02","2018-01-03","2018-01-04","2018-01-05","2018-01-06","2018-01-07"]
[]
[null,{"$f":"1+B4","v":2},{"$f":"+C4+7","v":"2018-01-08"},"2018-01-09","2018-01-10","2018-01-11","2018-01-12","2018-01-13","2018-01-14"]
[]
[null,{"$f":"1+B6","v":3},{"$f":"+C6+7","v":"2018-01-15"},"2018-01-16","2018-01-17","2018-01-18","2018-01-19","2018-01-20","2018-01-21"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B8","v":4},{"$f":"+C8+7","v":"2018-01-22"},"2018-01-23","2018-01-24","2018-01-25","2018-01-26","2018-01-27","2018-01-28"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["FEBRERO",{"$f":"+B10+1","v":5},{"$f":"+C10+7","v":"2018-01-29"},"2018-01-30","2018-01-31","2018-02-01","2018-02-02","2018-02-03","2018-02-04"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B13","v":6},{"$f":"+C13+7","v":"2018-02-05"},"2018-02-06","2018-02-07","2018-02-08","2018-02-09","2018-02-10","2018-02-11"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B15","v":7},{"$f":"+C15+7","v":"2018-02-12"},"2018-02-13","2018-02-14","2018-02-15","2018-02-16","2018-02-17","2018-02-18"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B17","v":8},{"$f":"+C17+7","v":"2018-02-19"},"2018-02-20","2018-02-21","2018-02-22","2018-02-23","2018-02-24","2018-02-25"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["MARZO",{"$f":"+B19+1","v":9},{"$f":"+C19+7","v":"2018-02-26"},"2018-02-27","2018-02-28","2018-03-01","2018-03-02","2018-03-03","2018-03-04"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B22","v":10},{"$f":"+C22+7","v":"2018-03-05"},"2018-03-06","2018-03-07","2018-03-08","2018-03-09","2018-03-10","2018-03-11"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B24","v":11},{"$f":"+C24+7","v":"2018-03-12"},"2018-03-13","2018-03-14","2018-03-15","2018-03-16","2018-03-17","2018-03-18"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B26","v":12},{"$f":"+C26+7","v":"2018-03-19"},"2018-03-20","2018-03-21","2018-03-22","2018-03-23","2018-03-24","2018-03-25"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B28","v":13},{"$f":"+C28+7","v":"2018-03-26"},"2018-03-27","2018-03-28","2018-03-29","2018-03-30","2018-03-31","2018-04-01"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["ABRIL",{"$f":"+B30+1","v":14},{"$f":"+C30+7","v":"2018-04-02"},"2018-04-03","2018-04-04","2018-04-05","2018-04-06","2018-04-07","2018-04-08"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B33","v":15},{"$f":"+C33+7","v":"2018-04-09"},"2018-04-10","2018-04-11","2018-04-12","2018-04-13","2018-04-14","2018-04-15"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B35","v":16},{"$f":"+C35+7","v":"2018-04-16"},"2018-04-17","2018-04-18","2018-04-19","2018-04-20","2018-04-21","2018-04-22"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B37","v":17},{"$f":"+C37+7","v":"2018-04-23"},"2018-04-24","2018-04-25","2018-04-26","2018-04-27","2018-04-28","2018-04-29"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["MAYO",{"$f":"+B39+1","v":18},{"$f":"C39+7","v":"2018-04-30"},"2018-05-01","2018-05-02","2018-05-03","2018-05-04","2018-05-05","2018-05-06"]
[null,null,"1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B42","v":19},{"$f":"+C42+7","v":"2018-05-07"},"2018-05-08","2018-05-09","2018-05-10","2018-05-11","2018-05-12","2018-05-13"]
[]
[null,20,{"$f":"+C44+7","v":"2018-05-14"},"2018-05-15","2018-05-16","2018-05-17","2018-05-18","2018-05-19","2018-05-20"]
[]
[null,21,{"$f":"+C46+7","v":"2018-05-21"},{"$f":"+D46+7","v":"2018-05-22"},"2018-05-23","2018-05-24","2018-05-25","2018-05-26","2018-05-27"]
[]
[null,22,{"$f":"+C48+7","v":"2018-05-28"},{"$f":"+D48+7","v":"2018-05-29"},"2018-05-30","2018-05-31","2018-06-01","2018-06-02","2018-06-03"]
[]
[]
["JUNIO",{"$f":"+B50+1","v":23},{"$f":"+C50+7","v":"2018-06-04"},"2018-06-05","2018-06-06","2018-06-07","2018-06-08","2018-06-09","2018-06-10"]
[]
[null,{"$f":"1+B53","v":24},{"$f":"+C53+7","v":"2018-06-11"},"2018-06-12","2018-06-13","2018-06-14","2018-06-15","2018-06-16","2018-06-17"]
[]
[null,{"$f":"1+B55","v":25},{"$f":"+C55+7","v":"2018-06-18"},"2018-06-19","2018-06-20","2018-06-21","2018-06-22","2018-06-23","2018-06-24"]
[]
[null,{"$f":"1+B57","v":26},{"$f":"+C57+7","v":"2018-06-25"},"2018-06-26","2018-06-27","2018-06-28","2018-06-29","2018-06-30","2018-07-01"]
[]
[]
["JULIO",{"$f":"+B59+1","v":27},{"$f":"+C59+7","v":"2018-07-02"},{"$f":"+D59+7","v":"2018-07-03"},"2018-07-04","2018-07-05","2018-07-06","2018-07-07","2018-07-08"]
[]
[null,{"$f":"1+B62","v":28},{"$f":"+C62+7","v":"2018-07-09"},"2018-07-10","2018-07-11","2018-07-12","2018-07-13","2018-07-14","2018-07-15"]
[]
[null,{"$f":"1+B64","v":29},{"$f":"+C64+7","v":"2018-07-16"},"2018-07-17","2018-07-18","2018-07-19","2018-07-20","2018-07-21","2018-07-22"]
[]
[null,{"$f":"1+B66","v":30},{"$f":"+C66+7","v":"2018-07-23"},"2018-07-24","2018-07-25","2018-07-26","2018-07-27","2018-07-28","2018-07-29"]
[]
[]
["AGOSTO",{"$f":"+B68+1","v":31},{"$f":"+C68+7","v":"2018-07-30"},"2018-07-31","2018-08-01","2018-08-02","2018-08-03","2018-08-04","2018-08-05"]
[{"$nulls":4},"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B71","v":32},{"$f":"+C71+7","v":"2018-08-06"},"2018-08-07","2018-08-08","2018-08-09","2018-08-10","2018-08-11","2018-08-12"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,33,{"$f":"+C73+7","v":"2018-08-13"},"2018-08-14","2018-08-15","2018-08-16","2018-08-17","2018-08-18","2018-08-19"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,34,{"$f":"+C75+7","v":"2018-08-20"},"2018-08-21","2018-08-22","2018-08-23","2018-08-24","2018-08-25","2018-08-26"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,35,{"$f":"+C77+7","v":"2018-08-27"},"2018-08-28","2018-08-29","2018-08-30","2018-08-31","2018-09-01","2018-09-02"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[]
["SEPTIEMBRE",{"$f":"+B79+1","v":36},{"$f":"+C79+7","v":"2018-09-03"},"2018-09-04","2018-09-05","2018-09-06","2018-09-07","2018-09-08","2018-09-09"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B82","v":37},{"$f":"+C82+7","v":"2018-09-10"},"2018-09-11","2018-09-12","2018-09-13","2018-09-14","2018-09-15","2018-09-16"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B84","v":38},{"$f":"+C84+7","v":"2018-09-17"},"2018-09-18","2018-09-19","2018-09-20","2018-09-21","2018-09-22","2018-09-23"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B86","v":39},{"$f":"+C86+7","v":"2018-09-24"},"2018-09-25","2018-09-26","2018-09-27","2018-09-28","2018-09-29","2018-09-30"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[]
["OCTUBRE",{"$f":"+B88+1","v":40},{"$f":"C88+7","v":"2018-10-01"},"2018-10-02","2018-10-03","2018-10-04","2018-10-05","2018-10-06","2018-10-07"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B91","v":41},{"$f":"+C91+7","v":"2018-10-08"},"2018-10-09","2018-10-10","2018-10-11","2018-10-12","2018-10-13","2018-10-14"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B93","v":42},{"$f":"+C93+7","v":"2018-10-15"},"2018-10-16","2018-10-17","2018-10-18","2018-10-19","2018-10-20","2018-10-21"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B95","v":43},{"$f":"+C95+7","v":"2018-10-22"},"2018-10-23","2018-10-24","2018-10-25","2018-10-26","2018-10-27","2018-10-28"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[]
["NOVIEMBRE",{"$f":"+B97+1","v":44},{"$f":"+C97+7","v":"2018-10-29"},"2018-10-30","2018-10-31","2018-11-01","2018-11-02","2018-11-03","2018-11-04"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B100","v":45},{"$f":"+C100+7","v":"2018-11-05"},"2018-11-06","2018-11-07","2018-11-08","2018-11-09","2018-11-10","2018-11-11"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,46,{"$f":"+C102+7","v":"2018-11-12"},"2018-11-13","2018-11-14","2018-11-15","2018-11-16","2018-11-17","2018-11-18"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,47,{"$f":"+C104+7","v":"2018-11-19"},"2018-11-20","2018-11-21","2018-11-22","2018-11-23","2018-11-24","2018-11-25"]
[]
[null,48,{"$f":"+C106+7","v":"2018-11-26"},"2018-11-27","2018-11-28","2018-11-29","2018-11-30","2018-12-01","2018-12-02"]
[]
[]
["DICIEMBRE",{"$f":"+B108+1","v":49},{"$f":"+C108+7","v":"2018-12-03"},"2018-12-04","2018-12-05","2018-12-06","2018-12-07","2018-12-08","2018-12-09"]
[]
[null,{"$f":"1+B111","v":50},{"$f":"+C111+7","v":"2018-12-10"},"2018-12-11","2018-12-12","2018-12-13","2018-12-14","2018-12-15","2018-12-16"]
[]
[null,{"$f":"1+B113","v":51},{"$f":"+C113+7","v":"2018-12-17"},"2018-12-18","2018-12-19","2018-12-20","2018-12-21","2018-12-22","2018-12-23"]
[]
[null,{"$f":"1+B115","v":52},{"$f":"+C115+7","v":"2018-12-24"},"2018-12-25","2018-12-26","2018-12-27","2018-12-28","2018-12-29","2018-12-30"]

{"sheet":"CALENDARIO PARADAS REAL","index":1,"n_rows":117,"n_cols":9,"rows_kept":117,"hidden":true,"merged":[[0,0,0,8],[3,0,10,0],[3,1,4,1],[5,1,6,1],[7,1,8,1],[9,1,10,1],[12,0,19,0],[12,1,13,1],[14,1,15,1],[16,1,17,1],[18,1,19,1],[21,0,30,0],[21,1,22,1],[23,1,24,1],[25,1,26,1],[27,1,28,1],[29,1,30,1],[32,0,39,0],[32,1,33,1],[34,1,35,1],[36,1,37,1],[38,1,39,1],[41,0,50,0],[41,1,42,1],[43,1,44,1],[45,1,46,1],[47,1,48,1],[49,1,50,1],[52,0,59,0],[52,1,53,1],[54,1,55,1],[56,1,57,1],[58,1,59,1],[61,0,68,0],[61,1,62,1],[63,1,64,1],[65,1,66,1],[67,1,68,1],[70,0,79,0],[70,1,71,1],[72,1,73,1],[74,1,75,1],[76,1,77,1],[78,1,79,1],[81,0,88,0],[81,1,82,1],[83,1,84,1],[85,1,86,1],[87,1,88,1],[90,0,97,0],[90,1,91,1],[92,1,93,1],[94,1,95,1],[96,1,97,1],[99,0,108,0],[99,1,100,1],[101,1,102,1],[103,1,104,1],[105,1,106,1],[107,1,108,1],[110,0,117,0],[110,1,111,1],[112,1,113,1],[114,1,115,1],[116,1,117,1]]}
["CALENDARIO PARADAS PLANTA PESQUERA - 2018"]
[]
[null,null,"LUNES","MARTES","MIERCOLES","JUEVES","VIERNES","SABADO","DOMINGO"]
["ENERO",1,"2018-01-01","2018-01-02","2018-01-03","2018-01-04","2018-01-05","2018-01-06","2018-01-07"]
[]
[null,{"$f":"1+B4","v":2},{"$f":"+C4+7","v":"2018-01-08"},"2018-01-09","2018-01-10","2018-01-11","2018-01-12","2018-01-13","2018-01-14"]
[]
[null,{"$f":"1+B6","v":3},{"$f":"+C6+7","v":"2018-01-15"},"2018-01-16","2018-01-17","2018-01-18","2018-01-19","2018-01-20","2018-01-21"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B8","v":4},{"$f":"+C8+7","v":"2018-01-22"},"2018-01-23","2018-01-24","2018-01-25","2018-01-26","2018-01-27","2018-01-28"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["FEBRERO",{"$f":"+B10+1","v":5},{"$f":"+C10+7","v":"2018-01-29"},"2018-01-30","2018-01-31","2018-02-01","2018-02-02","2018-02-03","2018-02-04"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B13","v":6},{"$f":"+C13+7","v":"2018-02-05"},"2018-02-06","2018-02-07","2018-02-08","2018-02-09","2018-02-10","2018-02-11"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B15","v":7},{"$f":"+C15+7","v":"2018-02-12"},"2018-02-13","2018-02-14","2018-02-15","2018-02-16","2018-02-17","2018-02-18"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B17","v":8},{"$f":"+C17+7","v":"2018-02-19"},"2018-02-20","2018-02-21","2018-02-22","2018-02-23","2018-02-24","2018-02-25"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["MARZO",{"$f":"+B19+1","v":9},{"$f":"+C19+7","v":"2018-02-26"},"2018-02-27","2018-02-28","2018-03-01","2018-03-02","2018-03-03","2018-03-04"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B22","v":10},{"$f":"+C22+7","v":"2018-03-05"},"2018-03-06","2018-03-07","2018-03-08","2018-03-09","2018-03-10","2018-03-11"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B24","v":11},{"$f":"+C24+7","v":"2018-03-12"},"2018-03-13","2018-03-14","2018-03-15","2018-03-16","2018-03-17","2018-03-18"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B26","v":12},{"$f":"+C26+7","v":"2018-03-19"},"2018-03-20","2018-03-21","2018-03-22","2018-03-23","2018-03-24","2018-03-25"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B28","v":13},{"$f":"+C28+7","v":"2018-03-26"},"2018-03-27","2018-03-28","2018-03-29","2018-03-30","2018-03-31","2018-04-01"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["ABRIL",{"$f":"+B30+1","v":14},{"$f":"+C30+7","v":"2018-04-02"},"2018-04-03","2018-04-04","2018-04-05","2018-04-06","2018-04-07","2018-04-08"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B33","v":15},{"$f":"+C33+7","v":"2018-04-09"},"2018-04-10","2018-04-11","2018-04-12","2018-04-13","2018-04-14","2018-04-15"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B35","v":16},{"$f":"+C35+7","v":"2018-04-16"},"2018-04-17","2018-04-18","2018-04-19","2018-04-20","2018-04-21","2018-04-22"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B37","v":17},{"$f":"+C37+7","v":"2018-04-23"},"2018-04-24","2018-04-25","2018-04-26","2018-04-27","2018-04-28","2018-04-29"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["MAYO",{"$f":"+B39+1","v":18},{"$f":"C39+7","v":"2018-04-30"},"2018-05-01","2018-05-02","2018-05-03","2018-05-04","2018-05-05","2018-05-06"]
[null,null,"1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B42","v":19},{"$f":"+C42+7","v":"2018-05-07"},"2018-05-08","2018-05-09","2018-05-10","2018-05-11","2018-05-12","2018-05-13"]
[]
[null,20,{"$f":"+C44+7","v":"2018-05-14"},"2018-05-15","2018-05-16","2018-05-17","2018-05-18","2018-05-19","2018-05-20"]
[]
[null,21,{"$f":"+C46+7","v":"2018-05-21"},{"$f":"+D46+7","v":"2018-05-22"},"2018-05-23","2018-05-24","2018-05-25","2018-05-26","2018-05-27"]
[]
[null,22,{"$f":"+C48+7","v":"2018-05-28"},{"$f":"+D48+7","v":"2018-05-29"},"2018-05-30","2018-05-31","2018-06-01","2018-06-02","2018-06-03"]
[]
[]
["JUNIO",{"$f":"+B50+1","v":23},{"$f":"+C50+7","v":"2018-06-04"},"2018-06-05","2018-06-06","2018-06-07","2018-06-08","2018-06-09","2018-06-10"]
[]
[null,{"$f":"1+B53","v":24},{"$f":"+C53+7","v":"2018-06-11"},"2018-06-12","2018-06-13","2018-06-14","2018-06-15","2018-06-16","2018-06-17"]
[]
[null,{"$f":"1+B55","v":25},{"$f":"+C55+7","v":"2018-06-18"},"2018-06-19","2018-06-20","2018-06-21","2018-06-22","2018-06-23","2018-06-24"]
[]
[null,{"$f":"1+B57","v":26},{"$f":"+C57+7","v":"2018-06-25"},"2018-06-26","2018-06-27","2018-06-28","2018-06-29","2018-06-30","2018-07-01"]
[]
[]
["JULIO",{"$f":"+B59+1","v":27},{"$f":"+C59+7","v":"2018-07-02"},{"$f":"+D59+7","v":"2018-07-03"},"2018-07-04","2018-07-05","2018-07-06","2018-07-07","2018-07-08"]
[]
[null,{"$f":"1+B62","v":28},{"$f":"+C62+7","v":"2018-07-09"},"2018-07-10","2018-07-11","2018-07-12","2018-07-13","2018-07-14","2018-07-15"]
[]
[null,{"$f":"1+B64","v":29},{"$f":"+C64+7","v":"2018-07-16"},"2018-07-17","2018-07-18","2018-07-19","2018-07-20","2018-07-21","2018-07-22"]
[]
[null,{"$f":"1+B66","v":30},{"$f":"+C66+7","v":"2018-07-23"},"2018-07-24","2018-07-25","2018-07-26","2018-07-27","2018-07-28","2018-07-29"]
[]
[]
["AGOSTO",{"$f":"+B68+1","v":31},{"$f":"+C68+7","v":"2018-07-30"},"2018-07-31","2018-08-01","2018-08-02","2018-08-03","2018-08-04","2018-08-05"]
[{"$nulls":4},"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B71","v":32},{"$f":"+C71+7","v":"2018-08-06"},"2018-08-07","2018-08-08","2018-08-09","2018-08-10","2018-08-11","2018-08-12"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,33,{"$f":"+C73+7","v":"2018-08-13"},"2018-08-14","2018-08-15","2018-08-16","2018-08-17","2018-08-18","2018-08-19"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,34,{"$f":"+C75+7","v":"2018-08-20"},"2018-08-21","2018-08-22","2018-08-23","2018-08-24","2018-08-25","2018-08-26"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,35,{"$f":"+C77+7","v":"2018-08-27"},"2018-08-28","2018-08-29","2018-08-30","2018-08-31","2018-09-01","2018-09-02"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[]
["SEPTIEMBRE",{"$f":"+B79+1","v":36},{"$f":"+C79+7","v":"2018-09-03"},"2018-09-04","2018-09-05","2018-09-06","2018-09-07","2018-09-08","2018-09-09"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B82","v":37},{"$f":"+C82+7","v":"2018-09-10"},"2018-09-11","2018-09-12","2018-09-13","2018-09-14","2018-09-15","2018-09-16"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B84","v":38},{"$f":"+C84+7","v":"2018-09-17"},"2018-09-18","2018-09-19","2018-09-20","2018-09-21","2018-09-22","2018-09-23"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B86","v":39},{"$f":"+C86+7","v":"2018-09-24"},"2018-09-25","2018-09-26","2018-09-27","2018-09-28","2018-09-29","2018-09-30"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[]
["OCTUBRE",{"$f":"+B88+1","v":40},{"$f":"C88+7","v":"2018-10-01"},"2018-10-02","2018-10-03","2018-10-04","2018-10-05","2018-10-06","2018-10-07"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B91","v":41},{"$f":"+C91+7","v":"2018-10-08"},"2018-10-09","2018-10-10","2018-10-11","2018-10-12","2018-10-13","2018-10-14"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B93","v":42},{"$f":"+C93+7","v":"2018-10-15"},"2018-10-16","2018-10-17","2018-10-18","2018-10-19","2018-10-20","2018-10-21"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B95","v":43},{"$f":"+C95+7","v":"2018-10-22"},"2018-10-23","2018-10-24","2018-10-25","2018-10-26","2018-10-27","2018-10-28"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[]
["NOVIEMBRE",{"$f":"+B97+1","v":44},{"$f":"+C97+7","v":"2018-10-29"},"2018-10-30","2018-10-31","2018-11-01","2018-11-02","2018-11-03","2018-11-04"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B100","v":45},{"$f":"+C100+7","v":"2018-11-05"},"2018-11-06","2018-11-07","2018-11-08","2018-11-09","2018-11-10","2018-11-11"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,46,{"$f":"+C102+7","v":"2018-11-12"},"2018-11-13","2018-11-14","2018-11-15","2018-11-16","2018-11-17","2018-11-18"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,47,{"$f":"+C104+7","v":"2018-11-19"},"2018-11-20","2018-11-21","2018-11-22","2018-11-23","2018-11-24","2018-11-25"]
[]
[null,48,{"$f":"+C106+7","v":"2018-11-26"},"2018-11-27","2018-11-28","2018-11-29","2018-11-30","2018-12-01","2018-12-02"]
[]
[]
["DICIEMBRE",{"$f":"+B108+1","v":49},{"$f":"+C108+7","v":"2018-12-03"},"2018-12-04","2018-12-05","2018-12-06","2018-12-07","2018-12-08","2018-12-09"]
[]
[null,{"$f":"1+B111","v":50},{"$f":"+C111+7","v":"2018-12-10"},"2018-12-11","2018-12-12","2018-12-13","2018-12-14","2018-12-15","2018-12-16"]
[]
[null,{"$f":"1+B113","v":51},{"$f":"+C113+7","v":"2018-12-17"},"2018-12-18","2018-12-19","2018-12-20","2018-12-21","2018-12-22","2018-12-23"]
[]
[null,{"$f":"1+B115","v":52},{"$f":"+C115+7","v":"2018-12-24"},"2018-12-25","2018-12-26","2018-12-27","2018-12-28","2018-12-29","2018-12-30"]

{"sheet":"CALENDARIO PARADAS FORECAST","index":2,"n_rows":117,"n_cols":9,"rows_kept":117,"hidden":true,"merged":[[0,0,0,8],[3,0,10,0],[3,1,4,1],[5,1,6,1],[7,1,8,1],[9,1,10,1],[12,0,19,0],[12,1,13,1],[14,1,15,1],[16,1,17,1],[18,1,19,1],[21,0,30,0],[21,1,22,1],[23,1,24,1],[25,1,26,1],[27,1,28,1],[29,1,30,1],[32,0,39,0],[32,1,33,1],[34,1,35,1],[36,1,37,1],[38,1,39,1],[41,0,50,0],[41,1,42,1],[43,1,44,1],[45,1,46,1],[47,1,48,1],[49,1,50,1],[52,0,59,0],[52,1,53,1],[54,1,55,1],[56,1,57,1],[58,1,59,1],[61,0,68,0],[61,1,62,1],[63,1,64,1],[65,1,66,1],[67,1,68,1],[70,0,79,0],[70,1,71,1],[72,1,73,1],[74,1,75,1],[76,1,77,1],[78,1,79,1],[81,0,88,0],[81,1,82,1],[83,1,84,1],[85,1,86,1],[87,1,88,1],[90,0,97,0],[90,1,91,1],[92,1,93,1],[94,1,95,1],[96,1,97,1],[99,0,108,0],[99,1,100,1],[101,1,102,1],[103,1,104,1],[105,1,106,1],[107,1,108,1],[110,0,117,0],[110,1,111,1],[112,1,113,1],[114,1,115,1],[116,1,117,1]]}
[{"$f":"+'CALENDARIO PARADAS BUDGET'!A1:I1","v":"CALENDARIO PARADAS PLANTA PESQUERA - 2018"}]
[]
[null,null,"LUNES","MARTES","MIERCOLES","JUEVES","VIERNES","SABADO","DOMINGO"]
["ENERO",1,"2018-01-01","2018-01-02","2018-01-03","2018-01-04","2018-01-05","2018-01-06","2018-01-07"]
[]
[null,{"$f":"1+B4","v":2},{"$f":"+C4+7","v":"2018-01-08"},"2018-01-09","2018-01-10","2018-01-11","2018-01-12","2018-01-13","2018-01-14"]
[]
[null,{"$f":"1+B6","v":3},{"$f":"+C6+7","v":"2018-01-15"},"2018-01-16","2018-01-17","2018-01-18","2018-01-19","2018-01-20","2018-01-21"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B8","v":4},{"$f":"+C8+7","v":"2018-01-22"},"2018-01-23","2018-01-24","2018-01-25","2018-01-26","2018-01-27","2018-01-28"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["FEBRERO",{"$f":"+B10+1","v":5},{"$f":"+C10+7","v":"2018-01-29"},"2018-01-30","2018-01-31","2018-02-01","2018-02-02","2018-02-03","2018-02-04"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B13","v":6},{"$f":"+C13+7","v":"2018-02-05"},"2018-02-06","2018-02-07","2018-02-08","2018-02-09","2018-02-10","2018-02-11"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B15","v":7},{"$f":"+C15+7","v":"2018-02-12"},"2018-02-13","2018-02-14","2018-02-15","2018-02-16","2018-02-17","2018-02-18"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B17","v":8},{"$f":"+C17+7","v":"2018-02-19"},"2018-02-20","2018-02-21","2018-02-22","2018-02-23","2018-02-24","2018-02-25"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["MARZO",{"$f":"+B19+1","v":9},{"$f":"+C19+7","v":"2018-02-26"},"2018-02-27","2018-02-28","2018-03-01","2018-03-02","2018-03-03","2018-03-04"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B22","v":10},{"$f":"+C22+7","v":"2018-03-05"},"2018-03-06","2018-03-07","2018-03-08","2018-03-09","2018-03-10","2018-03-11"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B24","v":11},{"$f":"+C24+7","v":"2018-03-12"},"2018-03-13","2018-03-14","2018-03-15","2018-03-16","2018-03-17","2018-03-18"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B26","v":12},{"$f":"+C26+7","v":"2018-03-19"},"2018-03-20","2018-03-21","2018-03-22","2018-03-23","2018-03-24","2018-03-25"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B28","v":13},{"$f":"+C28+7","v":"2018-03-26"},"2018-03-27","2018-03-28","2018-03-29","2018-03-30","2018-03-31","2018-04-01"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["ABRIL",{"$f":"+B30+1","v":14},{"$f":"+C30+7","v":"2018-04-02"},"2018-04-03","2018-04-04","2018-04-05","2018-04-06","2018-04-07","2018-04-08"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B33","v":15},{"$f":"+C33+7","v":"2018-04-09"},"2018-04-10","2018-04-11","2018-04-12","2018-04-13","2018-04-14","2018-04-15"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B35","v":16},{"$f":"+C35+7","v":"2018-04-16"},"2018-04-17","2018-04-18","2018-04-19","2018-04-20","2018-04-21","2018-04-22"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B37","v":17},{"$f":"+C37+7","v":"2018-04-23"},"2018-04-24","2018-04-25","2018-04-26","2018-04-27","2018-04-28","2018-04-29"]
[null,null,"1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H","1RA VEDA\n\nPT: 24 H"]
[]
["MAYO",{"$f":"+B39+1","v":18},{"$f":"C39+7","v":"2018-04-30"},"2018-05-01","2018-05-02","2018-05-03","2018-05-04","2018-05-05","2018-05-06"]
[null,null,"1RA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B42","v":19},{"$f":"+C42+7","v":"2018-05-07"},"2018-05-08","2018-05-09","2018-05-10","2018-05-11","2018-05-12","2018-05-13"]
[]
[null,20,{"$f":"+C44+7","v":"2018-05-14"},"2018-05-15","2018-05-16","2018-05-17","2018-05-18","2018-05-19","2018-05-20"]
[]
[null,21,{"$f":"+C46+7","v":"2018-05-21"},{"$f":"+D46+7","v":"2018-05-22"},"2018-05-23","2018-05-24","2018-05-25","2018-05-26","2018-05-27"]
[]
[null,22,{"$f":"+C48+7","v":"2018-05-28"},{"$f":"+D48+7","v":"2018-05-29"},"2018-05-30","2018-05-31","2018-06-01","2018-06-02","2018-06-03"]
[]
[]
["JUNIO",{"$f":"+B50+1","v":23},{"$f":"+C50+7","v":"2018-06-04"},"2018-06-05","2018-06-06","2018-06-07","2018-06-08","2018-06-09","2018-06-10"]
[]
[null,{"$f":"1+B53","v":24},{"$f":"+C53+7","v":"2018-06-11"},"2018-06-12","2018-06-13","2018-06-14","2018-06-15","2018-06-16","2018-06-17"]
[]
[null,{"$f":"1+B55","v":25},{"$f":"+C55+7","v":"2018-06-18"},"2018-06-19","2018-06-20","2018-06-21","2018-06-22","2018-06-23","2018-06-24"]
[]
[null,{"$f":"1+B57","v":26},{"$f":"+C57+7","v":"2018-06-25"},"2018-06-26","2018-06-27","2018-06-28","2018-06-29","2018-06-30","2018-07-01"]
[]
[]
["JULIO",{"$f":"+B59+1","v":27},{"$f":"+C59+7","v":"2018-07-02"},{"$f":"+D59+7","v":"2018-07-03"},"2018-07-04","2018-07-05","2018-07-06","2018-07-07","2018-07-08"]
[]
[null,{"$f":"1+B62","v":28},{"$f":"+C62+7","v":"2018-07-09"},"2018-07-10","2018-07-11","2018-07-12","2018-07-13","2018-07-14","2018-07-15"]
[]
[null,{"$f":"1+B64","v":29},{"$f":"+C64+7","v":"2018-07-16"},"2018-07-17","2018-07-18","2018-07-19","2018-07-20","2018-07-21","2018-07-22"]
[]
[null,{"$f":"1+B66","v":30},{"$f":"+C66+7","v":"2018-07-23"},"2018-07-24","2018-07-25","2018-07-26","2018-07-27","2018-07-28","2018-07-29"]
[]
[]
["AGOSTO",{"$f":"+B68+1","v":31},{"$f":"+C68+7","v":"2018-07-30"},"2018-07-31","2018-08-01","2018-08-02","2018-08-03","2018-08-04","2018-08-05"]
[{"$nulls":4},"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B71","v":32},{"$f":"+C71+7","v":"2018-08-06"},"2018-08-07","2018-08-08","2018-08-09","2018-08-10","2018-08-11","2018-08-12"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,33,{"$f":"+C73+7","v":"2018-08-13"},"2018-08-14","2018-08-15","2018-08-16","2018-08-17","2018-08-18","2018-08-19"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,34,{"$f":"+C75+7","v":"2018-08-20"},"2018-08-21","2018-08-22","2018-08-23","2018-08-24","2018-08-25","2018-08-26"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,35,{"$f":"+C77+7","v":"2018-08-27"},"2018-08-28","2018-08-29","2018-08-30","2018-08-31","2018-09-01","2018-09-02"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[]
["SEPTIEMBRE",{"$f":"+B79+1","v":36},{"$f":"+C79+7","v":"2018-09-03"},"2018-09-04","2018-09-05","2018-09-06","2018-09-07","2018-09-08","2018-09-09"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B82","v":37},{"$f":"+C82+7","v":"2018-09-10"},"2018-09-11","2018-09-12","2018-09-13","2018-09-14","2018-09-15","2018-09-16"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B84","v":38},{"$f":"+C84+7","v":"2018-09-17"},"2018-09-18","2018-09-19","2018-09-20","2018-09-21","2018-09-22","2018-09-23"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B86","v":39},{"$f":"+C86+7","v":"2018-09-24"},"2018-09-25","2018-09-26","2018-09-27","2018-09-28","2018-09-29","2018-09-30"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[]
["OCTUBRE",{"$f":"+B88+1","v":40},{"$f":"C88+7","v":"2018-10-01"},"2018-10-02","2018-10-03","2018-10-04","2018-10-05","2018-10-06","2018-10-07"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B91","v":41},{"$f":"+C91+7","v":"2018-10-08"},"2018-10-09","2018-10-10","2018-10-11","2018-10-12","2018-10-13","2018-10-14"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B93","v":42},{"$f":"+C93+7","v":"2018-10-15"},"2018-10-16","2018-10-17","2018-10-18","2018-10-19","2018-10-20","2018-10-21"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B95","v":43},{"$f":"+C95+7","v":"2018-10-22"},"2018-10-23","2018-10-24","2018-10-25","2018-10-26","2018-10-27","2018-10-28"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[]
["NOVIEMBRE",{"$f":"+B97+1","v":44},{"$f":"+C97+7","v":"2018-10-29"},"2018-10-30","2018-10-31","2018-11-01","2018-11-02","2018-11-03","2018-11-04"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,{"$f":"1+B100","v":45},{"$f":"+C100+7","v":"2018-11-05"},"2018-11-06","2018-11-07","2018-11-08","2018-11-09","2018-11-10","2018-11-11"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,46,{"$f":"+C102+7","v":"2018-11-12"},"2018-11-13","2018-11-14","2018-11-15","2018-11-16","2018-11-17","2018-11-18"]
[null,null,"2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H","2DA VEDA\n\nPT: 24 H"]
[null,47,{"$f":"+C104+7","v":"2018-11-19"},"2018-11-20","2018-11-21","2018-11-22","2018-11-23","2018-11-24","2018-11-25"]
[]
[null,48,{"$f":"+C106+7","v":"2018-11-26"},"2018-11-27","2018-11-28","2018-11-29","2018-11-30","2018-12-01","2018-12-02"]
[]
[]
["DICIEMBRE",{"$f":"+B108+1","v":49},{"$f":"+C108+7","v":"2018-12-03"},"2018-12-04","2018-12-05","2018-12-06","2018-12-07","2018-12-08","2018-12-09"]
[]
[null,{"$f":"1+B111","v":50},{"$f":"+C111+7","v":"2018-12-10"},"2018-12-11","2018-12-12","2018-12-13","2018-12-14","2018-12-15","2018-12-16"]
[]
[null,{"$f":"1+B113","v":51},{"$f":"+C113+7","v":"2018-12-17"},"2018-12-18","2018-12-19","2018-12-20","2018-12-21","2018-12-22","2018-12-23"]
[]
[null,{"$f":"1+B115","v":52},{"$f":"+C115+7","v":"2018-12-24"},"2018-12-25","2018-12-26","2018-12-27","2018-12-28","2018-12-29","2018-12-30"]

{"sheet":"ANDON PROY.","index":3,"n_rows":59,"n_cols":15,"rows_kept":59,"hidden":true,"merged":[[0,2,0,8],[1,2,1,8],[4,0,8,0],[9,0,12,0],[13,0,17,0],[18,0,21,0],[22,0,26,0],[27,0,30,0],[31,0,34,0],[35,0,39,0],[40,0,43,0],[44,0,47,0],[48,0,52,0],[53,0,56,0]]}
[null,null,"CALENDARIO 2021"]
[null,null,"ANDON Planeamiento Planta Concentradora"]
[]
["MES","SEMANA","L","M","M","J","V","S","D"]
["ENERO",{"$nulls":5},1,2,3]
[null,"S1","Previos parada","Previos parada","Previos parada","Previos parada","Previos parada","Previos parada","Previos parada"]
[null,"S2","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
[null,"S3","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
[null,"S4","Parada de Planta","Parada de Planta",27,28,29,30,31]
["FEBRERO","S5",1,2,3,4,5,6,7]
[null,"S6",8,9,10,11,12,13,14]
[null,"S7",15,16,17,"Previos parada","Previos parada","Previos parada","Previos parada"]
[null,"S8","Previos parada","Previos parada","Previos parada","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta"]
["MARZO","S9","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",{"$nulls":5},{"$f":"3*24","v":72}]
[null,"S10","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",13,14]
[null,"S11",15,16,17,18,19,20,21]
[null,"S12",22,23,24,25,26,27,28]
[null,"S13",29,30,31,1,2,3,4]
["ABRIL","S14",5,6,7,8,9,10,11]
[null,"S15",12,13,14,15,16,17,18]
[null,"S16",19,20,"Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
[null,"S17","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",30,1,2]
["MAYO","S18",3,4,5,6,7,8,9]
[null,"S19",10,11,12,13,14,15,16]
[null,"S20",17,18,19,20,21,22,23]
[null,"S21",24,25,"Previos parada","Previos parada","Previos parada","Parada de Planta","Parada de Planta"]
[null,"S22","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
["JUNIO","S23","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",13]
[null,"S24",14,15,16,17,18,19,20]
[null,"S25",21,22,23,24,25,26,27]
[null,"S26",28,29,30,1,2,3,4]
["JULIO","S27","Previos parada","Previos parada","Previos parada","Previos parada","Previos parada","Previos parada","Previos parada"]
[null,"S28","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
[null,"S29","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
[null,"S30","Parada de Planta","Parada de Planta",28,29,30,31,1]
["AGOSTO","S31",2,3,4,5,6,7,8]
[null,"S32",9,10,11,12,13,14,15]
[null,"S33",16,17,18,"Previos parada","Previos parada","Previos parada","Previos parada"]
[null,"S34","Previos parada","Previos parada","Previos parada","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta"]
[null,"S35","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
["SETIEMBRE","S36","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",11,12]
[null,"S37",13,14,15,16,17,18,19]
[null,"S38",20,21,22,23,24,25,26]
[null,"S39",27,28,29,30,1,2,"Previos parada"]
["OCTUBRE","S40","Previos parada","Previos parada","Previos parada","Previos parada","Previos parada","Previos parada","Previos parada"]
[null,"S41","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
[null,"S42","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
[null,"S43","Parada de Planta",26,27,28,29,30,31]
["NOVIEMBRE","S44",1,2,3,4,5,6,7]
[null,"S45",8,9,10,11,12,13,14]
[null,"S46",15,16,"Previos parada","Previos parada","Previos parada","Previos parada","Previos parada"]
[null,"S47","Previos parada","Previos parada","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
[null,"S48","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
["DICIEMBRE","S49","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",10,11,12,{"$f":"4*24","v":96}]
[null,"S50",13,14,15,16,17,18,19]
[null,"S51",20,21,22,23,24,25,26]
[null,"S52",27,28,29,30,31]
[]
[{"$nulls":13},{"$f":"144/48","v":3}]

{"sheet":"ANDON","index":4,"n_rows":58,"n_cols":15,"rows_kept":58,"merged":[[0,2,0,8],[1,2,1,8],[4,0,7,0],[8,0,11,0],[12,0,16,0],[17,0,20,0],[21,0,24,0],[25,0,29,0],[30,0,33,0],[34,0,38,0],[39,0,42,0],[43,0,46,0],[47,0,51,0],[52,0,55,0]]}
[null,null,"CALENDARIO 2024"]
[null,null,"ANDON Planeamiento Planta Concentradora"]
[]
["MES","SEMANA","L","M","M","J","V","S","D"]
["ENERO","S1","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta",5,6,7]
[null,"S2",8,9,10,11,12,13,14]
[null,"S3",15,16,17,18,19,20,21]
[null,"S4",22,23,24,25,26,27,28]
["FEBRERO","S5",29,30,31,1,2,3,4]
[null,"S6",5,6,7,8,9,10,11]
[null,"S7",12,13,14,15,16,17,18]
[null,"S8",19,20,21,22,23,24,25]
["MARZO","S9",26,27,28,29,1,2,3]
[null,"S10",4,5,6,7,8,9,10,{"$nulls":5},{"$f":"3*24","v":72}]
[null,"S11",11,12,13,14,15,16,17]
[null,"S12",18,19,20,21,22,23,24]
[null,"S13",25,26,27,28,29,30,31]
["ABRIL","S14",1,2,3,4,5,6,7]
[null,"S15",8,9,10,11,12,13,14]
[null,"S16",15,16,17,18,19,20,21]
[null,"S17",22,23,24,25,26,27,28]
["MAYO","S18",29,30,1,2,3,4,5]
[null,"S19",6,7,8,9,10,11,12]
[null,"S20",13,14,15,16,17,18,19]
[null,"S21",20,21,22,23,24,25,26]
["JUNIO","S22",27,28,29,30,31,1,2]
[null,"S23",3,4,5,6,7,8,9]
[null,"S24",10,11,12,13,14,15,16]
[null,"S25",17,18,19,20,21,22,23]
[null,"S26",24,25,26,27,28,29,30]
["JULIO","S27",1,2,3,4,5,6,7]
[null,"S28",8,9,10,11,12,13,14]
[null,"S29",15,16,17,18,19,20,21]
[null,"S30",22,23,24,25,26,27,28]
["AGOSTO","S31",29,30,31,1,2,3,4]
[null,"S32",5,6,7,8,9,10,11]
[null,"S33",12,13,14,15,16,17,18]
[null,"S34",19,20,21,22,23,24,25]
[null,"S35",26,27,28,29,30,31,1]
["SETIEMBRE","S36",2,3,4,5,6,7,8]
[null,"S37",9,10,11,12,13,14,15]
[null,"S38",16,17,18,19,20,21,22]
[null,"S39",23,24,25,26,27,28,29]
["OCTUBRE","S40",30,1,2,3,4,5,6]
[null,"S41",7,8,9,10,11,12,13]
[null,"S42",14,15,16,17,18,19,20]
[null,"S43",21,22,23,24,25,26,27]
["NOVIEMBRE","S44",28,29,30,31,1,2,3]
[null,"S45",4,5,6,7,8,9,10]
[null,"S46",11,12,13,14,15,16,17]
[null,"S47",18,19,20,21,22,23,24]
[null,"S48",25,26,27,28,29,30,1]
["DICIEMBRE","S49",2,3,4,5,6,7,8]
[null,"S50",9,10,11,12,13,14,15]
[null,"S51",16,17,18,19,20,21,22]
[null,"S52",23,24,25,26,27,28,29]
[]
[{"$nulls":13},{"$f":"144/48","v":3}]

{"sheet":"ANDON PROY","index":5,"n_rows":58,"n_cols":15,"rows_kept":58,"merged":[[0,2,0,8],[1,2,1,8],[4,0,7,0],[8,0,11,0],[12,0,16,0],[17,0,20,0],[21,0,24,0],[25,0,29,0],[30,0,33,0],[34,0,38,0],[39,0,42,0],[43,0,46,0],[47,0,51,0],[52,0,55,0]]}
[null,null,"CALENDARIO 2024"]
[null,null,"ANDON Planeamiento Planta Concentradora"]
[]
["MES","SEMANA","L","M","M","J","V","S","D"]
["ENERO","S1","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta",5,6,7]
[null,"S2",8,9,10,11,12,13,14]
[null,"S3",15,16,17,18,19,20,21]
[null,"S4",22,23,24,25,26,27,28]
["FEBRERO","S5",29,30,31,1,2,3,4]
[null,"S6",5,6,7,8,9,10,11]
[null,"S7",12,13,14,15,16,17,18]
[null,"S8",19,20,21,22,23,24,25]
["MARZO","S9",26,27,28,29,1,2,3]
[null,"S10",4,5,6,7,8,9,10,{"$nulls":5},{"$f":"3*24","v":72}]
[null,"S11",11,12,13,14,15,16,17]
[null,"S12",18,19,20,21,22,23,24]
[null,"S13",25,26,27,28,29,30,31]
["ABRIL","S14",1,2,3,4,5,6,7]
[null,"S15",8,9,10,11,12,13,14]
[null,"S16",15,16,17,18,19,20,21]
[null,"S17",22,23,24,25,26,27,28]
["MAYO","S18",29,30,1,2,3,4,5]
[null,"S19",6,7,8,9,10,11,12]
[null,"S20",13,14,15,16,17,18,19]
[null,"S21",20,21,22,23,24,25,26]
["JUNIO","S22",27,28,29,30,31,1,2]
[null,"S23",3,4,5,6,7,8,9]
[null,"S24",10,11,12,13,14,15,16]
[null,"S25",17,18,19,20,21,22,23]
[null,"S26",24,25,26,27,28,29,30]
["JULIO","S27",1,2,3,4,5,6,7]
[null,"S28",8,9,10,11,12,13,14]
[null,"S29",15,16,17,18,19,20,21]
[null,"S30",22,23,24,25,26,27,28]
["AGOSTO","S31",29,30,31,1,2,3,4]
[null,"S32",5,6,7,8,9,10,11]
[null,"S33",12,13,14,15,16,17,18]
[null,"S34",19,20,21,22,23,24,25]
[null,"S35",26,27,28,29,30,31,1]
["SETIEMBRE","S36",2,3,4,5,6,7,8]
[null,"S37",9,10,11,12,13,14,15]
[null,"S38",16,17,18,19,20,21,22]
[null,"S39",23,24,25,26,27,28,29]
["OCTUBRE","S40",30,1,2,3,4,5,6]
[null,"S41",7,8,9,10,11,12,13]
[null,"S42",14,15,16,17,18,19,20]
[null,"S43",21,22,23,24,25,26,27]
["NOVIEMBRE","S44",28,29,30,31,1,2,3]
[null,"S45",4,5,6,7,8,9,10]
[null,"S46",11,12,13,14,15,16,17]
[null,"S47",18,19,20,21,22,23,24]
[null,"S48",25,26,27,28,29,30,1]
["DICIEMBRE","S49",2,3,4,5,6,7,8]
[null,"S50",9,10,11,12,13,14,15]
[null,"S51",16,17,18,19,20,21,22]
[null,"S52",23,24,25,26,27,28,29]
[]
[{"$nulls":13},{"$f":"144/48","v":3}]

{"sheet":"ANDON PROY V1","index":6,"n_rows":59,"n_cols":15,"rows_kept":59,"hidden":true,"merged":[[0,2,0,8],[1,2,1,8],[4,0,8,0],[9,0,12,0],[13,0,17,0],[18,0,21,0],[22,0,26,0],[27,0,30,0],[31,0,34,0],[35,0,39,0],[40,0,43,0],[44,0,47,0],[48,0,52,0],[53,0,56,0]]}
[null,null,"CALENDARIO 2023"]
[null,null,"ANDON Planeamiento Planta Concentradora"]
[]
["MES","SEMANA","L","M","M","J","V","S","D"]
["ENERO",{"$nulls":6},1,"Previos parada"]
[null,"S1","Previos parada","Previos parada","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
[null,"S2","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",14,15,16]
[null,"S3",17,18,19,20,21,22,23]
[null,"S4",24,25,26,27,"Previos parada","Previos parada","Previos parada"]
["FEBRERO","S5","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",5,6]
[null,"S6",7,8,9,10,11,12,13]
[null,"S7",14,15,16,17,18,19,20]
[null,"S8",21,22,23,24,"Previos parada","Previos parada","Previos parada"]
["MARZO","S9","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",6,{"$nulls":5},{"$f":"3*24","v":72}]
[null,"S10",7,8,9,10,11,12,13]
[null,"S11",14,15,16,17,18,19,20]
[null,"S12",21,22,23,24,25,26,27]
[null,"S13","Previos parada","Previos parada","Previos parada","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta"]
["ABRIL","S14","Parada de Planta","Parada de Planta",6,7,8,9,10]
[null,"S15",11,12,13,14,15,16,17]
[null,"S16",18,19,20,21,22,23,24]
[null,"S17",25,26,"Previos parada","Previos parada","Previos parada","Previos parada","Parada de Planta"]
["MAYO","S18","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",6,7,8]
[null,"S19",9,10,11,12,13,14,15]
[null,"S20",16,17,18,19,20,21,22]
[null,"S21",23,24,25,26,27,"Previos parada","Previos parada"]
[null,"S22","Previos parada","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
["JUNIO","S23",6,7,8,9,10,11,12]
[null,"S24",13,14,15,16,17,18,19]
[null,"S25",20,21,22,23,24,25,26]
[null,"S26","Previos parada","Previos parada","Previos parada","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta"]
["JULIO","S27","Parada de Planta","Parada de Planta",6,7,8,9,10]
[null,"S28",11,12,13,14,15,16,17]
[null,"S29",18,19,20,21,22,23,24]
[null,"S30",25,26,27,"Previos parada","Previos parada","Previos parada","Previos parada"]
["AGOSTO","S31","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",6,7]
[null,"S32",8,9,10,11,12,13,14]
[null,"S33",15,16,17,18,19,20,21]
[null,"S34",22,23,24,25,26,27,"Previos parada"]
[null,"S35","Previos parada","Previos parada","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
["SETIEMBRE","S36","Parada de Planta",6,7,8,9,10,11]
[null,"S37",12,13,14,15,16,17,18]
[null,"S38",19,20,21,22,23,24,25]
[null,"S39",26,"Previos parada","Previos parada","Previos parada","Previos parada","Parada de Planta","Parada de Planta"]
["OCTUBRE","S40","Parada de Planta","Parada de Planta","Parada de Planta",6,7,8,9]
[null,"S41",10,11,12,13,14,15,16]
[null,"S42",17,18,19,20,21,22,23]
[null,"S43",24,25,26,27,"Previos parada","Previos parada","Previos parada"]
["NOVIEMBRE","S44","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta",6]
[null,"S45",7,8,9,10,11,12,13]
[null,"S46",14,15,16,17,18,19,20]
[null,"S47",21,22,23,24,25,26,"Previos parada"]
[null,"S48","Previos parada","Previos parada","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta","Parada de Planta"]
["DICIEMBRE","S49","Parada de Planta",6,7,8,9,10,11]
[null,"S50",12,13,14,15,16,17,18]
[null,"S51",19,20,21,22,23,24,25]
[null,"S52",26,27,28,29,30,31,1]
[]
[{"$nulls":13},{"$f":"144/48","v":3}]

{"sheet":"ANDON REAL","index":7,"n_rows":58,"n_cols":15,"rows_kept":58,"merged":[[0,2,0,8],[1,2,1,8],[4,0,7,0],[8,0,11,0],[12,0,16,0],[17,0,20,0],[21,0,24,0],[25,0,29,0],[30,0,33,0],[34,0,38,0],[39,0,42,0],[43,0,46,0],[47,0,51,0],[52,0,55,0]]}
[null,null,"CALENDARIO 2024"]
[null,null,"ANDON Planeamiento Planta Concentradora"]
[]
["MES","SEMANA","L","M","M","J","V","S","D"]
["ENERO","S1","Previos parada","Parada de Planta","Parada de Planta","Parada de Planta",5,6,7]
[null,"S2",8,9,10,11,12,13,14]
[null,"S3",15,16,17,18,19,20,21]
[null,"S4",22,23,24,25,26,27,28]
["FEBRERO","S5",29,30,31,1,2,3,4]
[null,"S6",5,6,7,8,9,10,11]
[null,"S7",12,13,14,15,16,17,18]
[null,"S8",19,20,21,22,23,24,25]
["MARZO","S9",26,27,28,29,1,2,3]
[null,"S10",4,5,6,7,8,9,10,{"$nulls":5},{"$f":"3*24","v":72}]
[null,"S11",11,12,13,14,15,16,17]
[null,"S12",18,19,20,21,22,23,24]
[null,"S13",25,26,27,28,29,30,31]
["ABRIL","S14",1,2,3,4,5,6,7]
[null,"S15",8,9,10,11,12,13,14]
[null,"S16",15,16,17,18,19,20,21]
[null,"S17",22,23,24,25,26,27,28]
["MAYO","S18",29,30,1,2,3,4,5]
[null,"S19",6,7,8,9,10,11,12]
[null,"S20",13,14,15,16,17,18,19]
[null,"S21",20,21,22,23,24,25,26]
["JUNIO","S22",27,28,29,30,31,1,2]
[null,"S23",3,4,5,6,7,8,9]
[null,"S24",10,11,12,13,14,15,16]
[null,"S25",17,18,19,20,21,22,23]
[null,"S26",24,25,26,27,28,29,30]
["JULIO","S27",1,2,3,4,5,6,7]
[null,"S28",8,9,10,11,12,13,14]
[null,"S29",15,16,17,18,19,20,21]
[null,"S30",22,23,24,25,26,27,28]
["AGOSTO","S31",29,30,31,1,2,3,4]
[null,"S32",5,6,7,8,9,10,11]
[null,"S33",12,13,14,15,16,17,18]
[null,"S34",19,20,21,22,23,24,25]
[null,"S35",26,27,28,29,30,31,1]
["SETIEMBRE","S36",2,3,4,5,6,7,8]
[null,"S37",9,10,11,12,13,14,15]
[null,"S38",16,17,18,19,20,21,22]
[null,"S39",23,24,25,26,27,28,29]
["OCTUBRE","S40",30,1,2,3,4,5,6]
[null,"S41",7,8,9,10,11,12,13]
[null,"S42",14,15,16,17,18,19,20]
[null,"S43",21,22,23,24,25,26,27]
["NOVIEMBRE","S44",28,29,30,31,1,2,3]
[null,"S45",4,5,6,7,8,9,10]
[null,"S46",11,12,13,14,15,16,17]
[null,"S47",18,19,20,21,22,23,24]
[null,"S48",25,26,27,28,29,30,1]
["DICIEMBRE","S49",2,3,4,5,6,7,8]
[null,"S50",9,10,11,12,13,14,15]
[null,"S51",16,17,18,19,20,21,22]
[null,"S52",23,24,25,26,27,28,29]
[]
[{"$nulls":13},{"$f":"144/48","v":3}]

{"sheet":"PLAN ACTIVIDADES PARADAS","index":8,"n_rows":2902,"n_cols":313,"rows_kept":2250,"cut":true,"merged":[[2,64,2,68],[2,69,2,73],[2,74,2,78],[2,79,2,83],[2,84,2,88],[2,89,2,93],[2,94,2,98],[2,99,2,103],[2,104,2,109],[2,110,2,114],[2,115,2,119],[2,120,2,124],[2,125,2,129],[2,130,2,134],[2,135,2,139],[2,140,2,144],[2,145,2,149],[2,150,2,154],[2,155,2,159],[2,160,2,164],[2,165,2,170],[2,171,2,175],[2,176,2,180],[2,181,2,185],[2,186,2,190],[2,191,2,195],[2,196,2,200],[2,201,2,205],[2,206,2,210],[2,211,2,215],[2,216,2,220],[2,221,2,225],[2,226,2,231],[2,232,2,236],[2,237,2,241],[2,242,2,246],[2,247,2,251],[2,252,2,256],[2,257,2,261],[2,262,2,266],[2,267,2,271],[2,272,2,276],[2,277,2,281],[2,282,2,286],[2,287,2,292],[2,293,2,297],[2,298,2,302],[2,303,2,307],[3,12,3,15],[3,16,3,19],[3,20,3,24],[3,25,3,28],[3,33,3,37],[3,38,3,41],[3,42,3,46],[3,47,3,50],[3,51,3,54],[3,55,3,59],[3,60,3,63],[5,12,5,15],[5,16,5,19],[5,20,5,24],[5,25,5,28],[5,29,5,33],[5,34,5,37],[5,38,5,41],[5,42,5,46],[5,47,5,50],[5,51,5,54],[5,55,5,59],[5,60,5,63]],"bounds":{"rows_first":1000,"rows_last":250,"rows_between":1000,"halvings":1}}
[{"$nulls":4},"ACTIVIDADES DE PARADAS TOTALES PLANTA CONCENTRADORAS x 52 SEMANAS - 2024"]
[{"$nulls":64},2015,{"$nulls":60},2016,{"$nulls":60},2017,{"$nulls":60},2018]
[{"$nulls":4},"BUDGET PLANNING AND MAINTENANCE CONCENTRATING PLANT",{"$nulls":7},2024,{"$nulls":51},"ENERO",{"$nulls":4},"FEBRERO",{"$nulls":4},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":4},"MAYO",{"$nulls":4},"JUNIO",{"$nulls":4},"JULIO",{"$nulls":4},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":5},"OCTUBRE",{"$nulls":4},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE",{"$nulls":4},"ENERO",{"$nulls":4},"FEBRERO",{"$nulls":4},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":4},"MAYO",{"$nulls":4},"JUNIO",{"$nulls":4},"JULIO",{"$nulls":4},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":5},"OCTUBRE",{"$nulls":4},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE",{"$nulls":4},"ENERO",{"$nulls":4},"FEBRERO",{"$nulls":4},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":4},"MAYO",{"$nulls":4},"JUNIO",{"$nulls":4},"JULIO",{"$nulls":4},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":5},"OCTUBRE",{"$nulls":4},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE",{"$nulls":4},"ENERO",{"$nulls":4},"FEBRERO",{"$nulls":4},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":4},"MAYO",{"$nulls":4},"JUNIO",{"$nulls":4},"JULIO",{"$nulls":4},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":5},"OCTUBRE",{"$nulls":4},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE"]
[{"$nulls":4},"HUANZALA",{"$nulls":7},"ENERO",{"$nulls":3},"FEBRERO",{"$nulls":3},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":3},"MAYO",{"$nulls":3},"JUNIO",{"$nulls":4},"JULIO",{"$nulls":3},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":3},"OCTUBRE",{"$nulls":3},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE",{"$nulls":3},1,2,3,4,5,5,6,7,8,9,9,10,11,12,13,14,15,16,17,18,18,19,20,21,22,22,23,24,25,26,27,28,29,30,31,31,32,33,34,35,35,36,37,38,39,40,40,41,42,43,44,44,45,46,47,48,48,49,50,51,52,1,2,3,4,5,5,6,7,8,9,9,10,11,12,13,14,15,16,17,18,18,19,20,21,22,22,23,24,25,26,27,28,29,30,31,31,32,33,34,35,35,36,37,38,39,40,40,41,42,43,44,44,45,46,47,48,48,49,50,51,52,1,2,3,4,5,5,6,7,8,9,9,10,11,12,13,14,15,16,17,18,18,19,20,21,22,22,23,24,25,26,27,28,29,30,31,31,32,33,34,35,35,36,37,38,39,40,40,41,42,43,44,44,45,46,47,48,48,49,50,51,52,1,2,3,4,5,5,6,7,8,9,9,10,11,12,13,14,15,16,17,18,18,19,20,21,22,22,23,24,25,26,27,28,29,30,31,31,32,33,34,35,35,36,37,38,39,40,40,41,42,43,44,44,45,46,47,48,48,49,50,51,52]
[{"$nulls":12},1,{"$f":"M5+1","v":2},{"$f":"N5+1","v":3},{"$f":"O5+1","v":4},5,6,7,8,9,10,11,{"$f":"W5+1","v":12},{"$f":"X5+1","v":13},14,15,16,{"$f":"AB5+1","v":17},{"$f":"AC5+1","v":18},19,20,21,{"$f":"AG5+1","v":22},23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52]
["PLANTA BENEFICIO HUANZALA",{"$nulls":11},"01ENE24 - 28ENE24",{"$nulls":3},"29ENE24 - 25FEB24",{"$nulls":3},"26FEB24 - 31MAR24",{"$nulls":4},"01ABR24 - 28ABR24",{"$nulls":3},"29ABR24 - 26MAY24",{"$nulls":4},"27MAY24 - 30JUN24",{"$nulls":3},"01JUL24 - 28JUL23",{"$nulls":3},"29JUL24 - 25AGO24",{"$nulls":4},"26AGO24 - 29SET24",{"$nulls":3},"30SET24 - 27OCT24",{"$nulls":3},"28OCT24 - 24NOV24",{"$nulls":4},"24NOV24 - 29DIC24"]
["PARADA TOTAL",{"$nulls":6},"H PRD",null,"SEM",null,null,{"$f":"MAX(M9:M5000)","v":0},{"$f":"MAX(N9:N5000)","v":144},{"$f":"MAX(O9:O5000)","v":168},48,0,0,0,72,168,120,0,0,0,0,168,168,24,0,0,0,96,96,0,0,null,0,24,168,168,0,0,0,0,120,168,72,0,0,0,48,168,144,0,0,0,0,144,168,48,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"MAX(BZ9:BZ5000)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"MAX(EL9:EL5000)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"MAX(GX9:GX5000)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"MAX(JJ9:JJ5000)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
["ITEM","CLASE1","CLASE","AREA1","AREA","EQUIPO","DESCRIPCION DE LA ACTIVIDAD","TIEMPO","UNID.","FREC.","UNID.","TIPO",{"$f":"+M5","v":1},{"$f":"+N5","v":2},3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,null,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"E",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",{"$nulls":3},"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"E",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",{"$nulls":3},"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"E",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",{"$nulls":3},"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"E",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",{"$nulls":3},"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A"]
[1,{"$f":"CONCATENATE(C9,D9)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion Chancadora secundaria sanvick","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","H",null,{"$f":"+H9","v":5},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$nulls":3},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$nulls":4},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$nulls":3},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$nulls":4},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$nulls":4},{"$f":"H9","v":5},5,{"$f":"H9","v":5},{"$nulls":3},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$f":"H9*3","v":15},{"$nulls":4},{"$f":"H9*3","v":15},{"$f":"H9","v":5},{"$f":"H9","v":5}]
[{"$f":"+A9+1","v":2},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion Chancadora secundaria sanvick","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","C",null,{"$f":"+H10","v":5},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$nulls":3},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$nulls":4},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$nulls":3},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$nulls":4},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$nulls":4},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$nulls":3},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$f":"H10*3","v":15},{"$nulls":4},{"$f":"H10*3","v":15},{"$f":"H10","v":5},{"$f":"H10","v":5}]
[3,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion Chancadora secundaria sanvick","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[4,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion chancadora Terciario sanvick","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[5,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion chancadora Terciario sanvick","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[6,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion chancadora Terciario sanvick","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[7,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[8,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[9,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE COVER BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[10,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE DISCHARGE PIPE",4,"Hra",1344,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[11,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1344,"DIA","F",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[12,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE IMPULSOR BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[13,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",672,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[14,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",672,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[15,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[16,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[17,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",336,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[18,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",336,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[19,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[20,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[21,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CADENA ALIMENTADORA ( APRON FEEDER) QA1548","MANTTO DE CADENA APRON FEEDER",5,"Hra",1620,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[22,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CADENA ALIMENTADORA ( APRON FEEDER) QA1548","MANTTO DE CADENA APRON FEEDER",5,"Hra",2046.3125,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[23,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CADENA ALIMENTADORA ( APRON FEEDER) QA1548","MANTTO DE CADENA APRON FEEDER",5,"Hra",5400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[24,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Cedazo # 01 - Vibratorio de alta frecuencia YOKAYAMI","CAMBIO DE MALLA",6,"Hra",130.9090909090909,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[25,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Cedazo # 02 - Vibratorio Simplicity 7x14","CAMBIO DE MALLA",6,"Hra",65.45454545454545,"DIA","E",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[26,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Cedazo # 02 - Vibratorio Simplicity 7x14","CAMBIO DE MALLA",6,"Hra",130.9090909090909,"DIA","E",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[27,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Cedazo # 02 - Vibratorio Simplicity 7x14","CAMBIO DE MALLA",6,"Hra",261.8181818181818,"DIA","E",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[28,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Cedazo # 02 - Vibratorio Simplicity 7x14","CAMBIO DE MALLA",6,"Hra",523.6363636363636,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[29,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 1151 FORRO LATERAL SUPER. DERE./IZQUI. (JGO X 02 PZAS)",4.5,"Hra",1282.5,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[30,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 1161 FORRO LATERAL INFER. DERE./IZQUI. (JGO X 02 PZAS)",4.5,"Hra",1282.5,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[31,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 1191 FIXED JAW PLATE (M-1796-01)",2.5,"Hra",641.25,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,72,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[32,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2059-1 SQUARE HEAD BOLT M48X650X130MM",2.5,"Hra",1282.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[33,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2059-2 SQUARE BOLTS M-48X700X130",2.5,"Hra",641.25,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[34,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2059-3 SQUARE LOWER BOLT M48 X 940 X 130  CON DOBLE TUERCA",2.5,"Hra",641.25,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[35,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2059-3 SQUARE LOWER BOLT M48X940X130MM",2.5,"Hra",641.25,"DIA","D",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[36,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2061 JAW PLATE STOPPER",6.5,"Hra",2565,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,19.5,{"$nulls":4},19.5,6.5,6.5]
[37,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2081 MOVABLE JAW PLATE (M-1796-02)",2.5,"Hra",641.25,"DIA","F",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,72,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[38,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 3029 ROLLERBEARING SKF22356C3(FRAME)",12,"Hra",20520,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[39,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 3061 LABYRINTH COLLAR",18,"Hra",20520,"DIA","D",null,18,18,18,{"$nulls":3},18,18,18,{"$nulls":4},18,18,18,{"$nulls":3},18,18,{"$nulls":4},18,18,18,{"$nulls":4},18,18,18,{"$nulls":3},18,18,54,{"$nulls":4},54,18,18]
[40,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 3161 LABYRINTH COLLAR INNER SIDE",18,"Hra",20520,"DIA","D",null,18,18,18,{"$nulls":3},18,18,18,{"$nulls":4},18,18,18,{"$nulls":3},18,18,{"$nulls":4},18,18,18,{"$nulls":4},18,18,18,{"$nulls":3},18,18,54,{"$nulls":4},54,18,18]
[41,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 4021 TOGGLE HEAD",12,"Hra",1282.5,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[42,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 4021-2 TOGGLE SEAT",12,"Hra",1282.5,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[43,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 4241 TENSION ROD. M-48X1040",2.5,"Hra",641.25,"DIA","D",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[44,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 4251 SPRING F/TENSION ORD",2.5,"Hra",641.25,"DIA","D",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[45,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 4331 TOGGLE BLOCK SPRING",6.5,"Hra",2565,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,19.5,{"$nulls":4},19.5,6.5,6.5]
[46,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 442793201 RING",2.5,"Hra",1282.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[47,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 900064800 ADAPTER G1BXG3/4B",3,"Hra",1282.5,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[48,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 900065500 ADAPTER G3/4BXG3/4B",3,"Hra",1282.5,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[49,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE BOLT F/CHECK PLATE M42X170X100MM P1059",2.5,"Hra",641.25,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[50,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE COIL SPRING F/BOLT JAW FIXED MOVABLE",2.5,"Hra",1282.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[51,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE E-405 V-BELTS",3.5,"Hra",2565,"DIA","E",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[52,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE PIN DE TENSION ROD",4.5,"Hra",1282.5,"DIA","E",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[53,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442.8017-01 DUST SEAL RING",3.5,"Hra",285,"DIA","E",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[54,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442647001 SEAL RING (CHANCAD. SANDV)",2.5,"Hra",142.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[55,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442647301 SPIDER BUSHING",12,"Hra",285,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[56,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442789201   HYDR.CYL. BUSCHING",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[57,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442789301 PISTON WEARING PL",6,"Hra",285,"DIA","D",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[58,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442789401 STEP WASHER",3.5,"Hra",285,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[59,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442789501 MAIN SHAFT STEP",6,"Hra",285,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[60,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442791101 BURNING RING",2,"Hra",142.5,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[61,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442791200 HEAD NUT WITH BUR",3.5,"Hra",570,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[62,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442791301 MAIN SHAFT SLEEVE",6,"Hra",285,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[63,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442791401 PROTECTION OF WEARING DOWN FOR ARM",4.5,"Hra",570,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[64,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442791501 PROTECTION OF WEARING DWN IN BOX OF NECKLACE",4.5,"Hra",570,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[65,{"$f":"CONCATENATE(C73,D73)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442793101 SEAL RING INNER",3,"Hra",1140,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[{"$f":"+A73+1","v":66},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442793401 GASKET",3,"Hra",570,"DIA","C",null,{"$f":"+H74","v":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$nulls":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$nulls":4},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$nulls":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$nulls":4},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$nulls":4},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$nulls":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$f":"H74*3","v":9},{"$nulls":4},{"$f":"H74*3","v":9},{"$f":"H74","v":3},{"$f":"H74","v":3}]
[67,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442797601 SPIDER CAP",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[68,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442798600 FEED HOPPER CONE LH",4,"Hra",570,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[69,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442798690 FEED HOPPER CONE RH",4,"Hra",570,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[70,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442798901 MANTLE B (CHANCAD. SANDV)",6,"Hra",142.5,"DIA","G",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[71,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442802101 RETAINER",6,"Hra",1140,"DIA","D",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[72,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442802201 SCRAPER",5.5,"Hra",1140,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[73,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442824901 CONCAVE EC-EC2",8,"Hra",142.5,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[74,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886401 WEARING DOWN PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[75,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886501 WEARING DOWN PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[76,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886601   WEARING PLATE",3,"Hra",570,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,168,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[77,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886701    WEARING PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[78,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886801  WEARING PLATE",3,"Hra",570,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[79,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886901    WEARING PLATE",3,"Hra",570,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[80,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4428870  BOTTOM SHELL LINERS KIT PARENT NO",2,"Hra",285,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[81,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442993601  PINION SHAFT",6,"Hra",1140,"DIA","D",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[82,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4524188001  ECCENTRIC WEARING PLATE",3,"Hra",1140,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[83,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4524190001 BOTTOM SHELL BUSHING",4,"Hra",1140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[84,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4524191001 ECCENTRIC BUSCHING THROW 16+19+22",7,"Hra",1140,"DIA","C",null,7,7,7,{"$nulls":3},7,7,7,{"$nulls":4},7,7,7,{"$nulls":3},7,7,{"$nulls":4},7,7,7,{"$nulls":4},7,7,7,{"$nulls":3},7,7,21,{"$nulls":4},21,7,7]
[85,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4524193001 ECCENTRIC BUSHING THROW 29+32+34+36",7,"Hra",1140,"DIA","D",null,7,7,7,{"$nulls":3},7,7,7,{"$nulls":4},7,7,7,{"$nulls":3},7,7,{"$nulls":4},7,7,7,{"$nulls":4},7,7,7,{"$nulls":3},7,7,21,{"$nulls":4},21,7,7]
[86,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4525542901 FILTER KIT CH/CS420/CS430",1.5,"Hra",71.25,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[87,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4525574901 EA REPAIR KIT PINION SHAFT  HOUSING",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[88,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4525777901  BOTTOMSHELL ARM LINER KIT CH / CS 430",5.5,"Hra",285,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[89,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4525791901  FASTENER KIT CONCAVE CH430",3,"Hra",570,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[90,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4525797901 LOCATING BAR KIT CH/ CS430",3.5,"Hra",1140,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[91,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 873.0833-00 O-RING 379, 3 X 5, 7 SMS 1586",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[92,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 873111200 SEALING COMPOUND ( CHANCAD. SANDV) 2440450",2.5,"Hra",142.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[93,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 906-0140-00 LUBRICATING OIL PUMP",6.5,"Hra",570,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,19.5,{"$nulls":4},19.5,6.5,6.5]
[94,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 912.0139-00 FILTER CARTRIDGE",1.5,"Hra",142.5,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[95,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 912015500 FILTER CARTRIDGE",1.5,"Hra",142.5,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[96,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE ARM SHIELD ",5.5,"Hra",285,"DIA","D",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[97,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE DOWEL PIN",4,"Hra",570,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[98,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE DUST SEAL RETAINING RING",3,"Hra",1140,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[99,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE HYDROSET PUMP ASS.",6,"Hra",570,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[100,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE INNER HEAD NUT",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[101,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE LUBRICATION PUMP ASS.",6.5,"Hra",570,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,19.5,{"$nulls":4},19.5,6.5,6.5]
[102,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE MAINSHAFT ASS.EXCL. MANTLE",8,"Hra",4560,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[103,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE PINIONSHAFT HOUSING ASS. EXCL.PULLEY",8,"Hra",4560,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[104,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[105,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[106,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE SPIDER BUSHING",3.5,"Hra",570,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[107,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE STEP BEARING SET",5.5,"Hra",1140,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[108,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE TOP SHELL ASS. EXCL. CONCAVE",4,"Hra",4560,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[109,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","ENGRASE DE EQUIPOS",2,"Hra",71.25,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[110,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[111,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 3090-1 ESPACIADOR  DE CONTRA EJE",1.5,"Hra",2280,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[112,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442 7984 01 ARM SHIELD",5.5,"Hra",285,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[113,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442.8017-01 DUST SEAL RING",3.5,"Hra",285,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[114,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442647001 SEAL RING (CHANCAD. SANDV)",2.5,"Hra",142.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[115,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442647301 SPIDER BUSHING",12,"Hra",285,"DIA","D",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[116,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442719301 OIL SEAL REING (CHANCAD. SANDV)",3.5,"Hra",285,"DIA","D",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[117,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442789301 PISTON WEARING PL",6,"Hra",285,"DIA","D",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[118,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442789401 STEP WASHER",3.5,"Hra",285,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[119,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442789501 MAIN SHAFT STEP",6,"Hra",285,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[120,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442791101 BURNING RING",2,"Hra",142.5,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[121,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442791200 HEAD NUT WITH BUR",3.5,"Hra",570,"DIA","F",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[122,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442791301 MAIN SHAFT SLEEVE",6,"Hra",285,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[123,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442791401 PROTECTION OF WEARING DOWN FOR ARM",4.5,"Hra",570,"DIA","D",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[124,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442791501 PROTECTION OF WEARING DWN IN BOX OF NECKLACE",4.5,"Hra",570,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[125,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 4427925-01 EXCENTRIC BUSHING 29+32+34+36",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[126,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442792901 DUST COLLAR",4,"Hra",1140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[127,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442793401 GASKET",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[128,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 4427935-01 BOTTOM SHELL BUSHING",4,"Hra",1140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[129,{"$f":"CONCATENATE(C137,D137)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442797601 SPIDER CAP",12,"Hra",285,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[{"$f":"+A137+1","v":130},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442798600 FEED HOPPER CONE LH",4,"Hra",570,"DIA","D",null,{"$f":"+H138","v":4},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$nulls":3},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$nulls":4},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$nulls":3},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$nulls":4},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$nulls":4},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$nulls":3},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$f":"H138*3","v":12},{"$nulls":4},{"$f":"H138*3","v":12},{"$f":"H138","v":4},{"$f":"H138","v":4}]
[131,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442798690 FEED HOPPER CONE RH",4,"Hra",570,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[132,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442798901 MANTLE B (CHANCAD. SANDV)",6,"Hra",142.5,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[133,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442802201 SCRAPER",5.5,"Hra",1140,"DIA","D",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[134,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886401 WEARING DOWN PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[135,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886501 WEARING DOWN PLATE",3,"Hra",570,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[136,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886601   WEARING PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},120,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[137,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886701    WEARING PLATE",3,"Hra",570,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[138,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886801  WEARING PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[139,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886901    WEARING PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[140,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 4521216001 CONCAVE MF M1",8,"Hra",142.5,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[141,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 840103400 SCREW",2.5,"Hra",142.5,"DIA","D",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[142,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 847001600 WASHER",1.5,"Hra",142.5,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[143,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 863003200 DISC SPRING 71X36X4",2,"Hra",285,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[144,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 868079000 RODAMIENTO 22219E/C3",2.5,"Hra",285,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[145,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 873.0833-00 O-RING 379, 3 X 5, 7 SMS 1586",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[146,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 873111200 SEALING COMPOUND ( CHANCAD. SANDV) 2440450",2.5,"Hra",142.5,"DIA","D",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[147,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 906-0140-00 LUBRICATING OIL PUMP",6.5,"Hra",570,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,19.5,{"$nulls":4},19.5,6.5,6.5]
[148,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 912.0139-00 FILTER CARTRIDGE",1.5,"Hra",142.5,"DIA","F",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[149,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 912015500 FILTER CARTRIDGE",1.5,"Hra",142.5,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[150,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE CFW-F2 BAF SF SLO.5 DRWX7 18-30-6/4.5 RETEN",3.5,"Hra",570,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[151,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE FILTRO",4,"Hra",142.5,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[152,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE FILTRO DEL HIDROSET",4,"Hra",142.5,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[153,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE FILTRO DEL LUBRICADOR",4,"Hra",142.5,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[154,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[155,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[156,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","ENGRASE DE EQUIPOS",2,"Hra",71.25,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[157,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",31.25,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[158,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRENSORA SULLAIR LS12-60H/A/SUL y tanque de aire comprimido","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[159,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRENSORA SULLAIR LS12-60H/A/SUL y tanque de aire comprimido","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[160,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRENSORA SULLAIR LS12-60H/A/SUL y tanque de aire comprimido","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[161,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA GARDEN DENVER EXTRACTOR DE POLVO PRIMARIO","CAMBIO DE FILTRO DE ACEITE",4,"Hra",228,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[162,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA GARDEN DENVER EXTRACTOR DE POLVO PRIMARIO","CAMBIO DE FILTRO DE AIRE",4,"Hra",228,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[163,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA GARDEN DENVER EXTRACTOR DE POLVO PRIMARIO","CAMBIO DE SEPARADOR DE KIT",2,"Hra",228,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[164,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR 10B-40HP/AC/STD CELDAS WENCO","CAMBIO DE FILTRO DE ACEITE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[165,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR 10B-40HP/AC/STD CELDAS WENCO","CAMBIO DE FILTRO DE AGUA",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[166,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR 10B-40HP/AC/STD CELDAS WENCO","CAMBIO DE FILTRO DE AIRE ",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[167,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR 10B-40HP/AC/STD CELDAS WENCO","CAMBIO DE FILTRO DE ELEMENTO",4,"Hra",288,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[168,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR 10B-40HP/AC/STD CELDAS WENCO","CAMBIO DE FILTRO ELEMENTO SEPARADOR",4,"Hra",288,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[169,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR LS12 -60H/A/SUL","CAMBIO DE ELEMENTO DE FILTRO",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[170,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR LS12 -60H/A/SUL","CAMBIO DE FILTRO DE AIRE",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[171,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR LS12 -60H/A/SUL","CAMBIO DE FILTRO SEPARADOR DE AGUA",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[172,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR LS12 -60H/A/SUL","CAMBIO DE FILTRO SEPARADOR PRIMARIO",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[173,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR LS12 -60H/A/SUL","CAMBIO DE FILTRO SEPARADOR SECUNDARIO",4,"Hra",201.6,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[174,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","estractor de polvo zona chancado  secundario","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[175,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","estractor de polvo zona chancado  secundario","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[176,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","estractor de polvo zona chancado  secundario","ENGRASE DE EQUIPOS",5,"Hra",15.625,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[177,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","estractor de polvo zona chancado  secundario","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[178,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[179,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[180,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[181,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","MANTENIMIENTO EXTRACTOR",12,"Hra",90,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[182,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","MANTENIMIENTO EXTRACTOR",12,"Hra",180,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[183,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","MANTENIMIENTO EXTRACTOR",12,"Hra",360,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[184,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","G",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[185,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[186,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[187,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[188,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[189,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[190,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[191,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[192,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[193,{"$f":"CONCATENATE(C201,D201)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[{"$f":"+A201+1","v":194},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","G",null,{"$f":"+H202","v":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$nulls":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$nulls":4},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$nulls":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$nulls":4},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$nulls":4},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$nulls":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$f":"H202*3","v":9},{"$nulls":4},{"$f":"H202*3","v":9},{"$f":"H202","v":3},{"$f":"H202","v":3}]
[195,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[196,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[197,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[198,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[199,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE CONVEYOR BELTS 750MM X 3P X 3.2 X 1.6 X 30\"",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[200,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[201,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[202,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[203,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[204,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[205,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[206,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[207,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE BANDA DE 30\"",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[208,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[209,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[210,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[211,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","D",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[212,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[213,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[214,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[215,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[216,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[217,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","D",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[218,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[219,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[220,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[221,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","D",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[222,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[223,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[224,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[225,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[226,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[227,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[228,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[229,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[230,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[231,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[232,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[233,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[234,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",13333.333333333334,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[235,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[236,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[237,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[238,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",13333.333333333334,"DIA","G",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[239,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",666.6666666666666,"DIA","G",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[240,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\"","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",666.6666666666666,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[241,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",666.6666666666666,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[242,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[243,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE BALL BEARING NK-318-K",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[244,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[245,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE CHAIN WHEEL RS-140-C-NT-25X80MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[246,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE CHAIN WHELL RS-140-C-NT-17X80MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[247,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE H318 MANGUITO",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[248,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE PILLOW BLOCK FYH- P318",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[249,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE POLEA MATRIZ ENJEBADO 720X850X80X1370MM",8,"Hra",1344,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[250,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",168,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[251,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[252,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE ROLLER CHAIN RS-140 WROL (CON PASADOR)",3,"Hra",336,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[253,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",266,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[254,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE BALL BEARING NK-318-K",2,"Hra",1064,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[255,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",532,"DIA","D",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[256,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE CHAIN WHEEL RS-140-C-NT-25X80MM. DIAM.",3,"Hra",1064,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[257,{"$f":"CONCATENATE(C265,D265)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE CHAIN WHELL RS-140-C-NT-17X80MM. DIAM.",3,"Hra",1064,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[{"$f":"+A265+1","v":258},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE H318 MANGUITO",2,"Hra",1064,"DIA","C",null,{"$f":"+H266","v":2},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$nulls":3},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$nulls":4},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$nulls":3},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$nulls":4},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$nulls":4},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$nulls":3},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$f":"H266*3","v":6},{"$nulls":4},{"$f":"H266*3","v":6},{"$f":"H266","v":2},{"$f":"H266","v":2}]
[259,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE PILLOW BLOCK FYH- P318",4.5,"Hra",1064,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[260,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE POLEA MATRIZ ENJEBADO 720X850X80X1370MM",8,"Hra",2128,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[261,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",266,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[262,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",266,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[263,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE ROLLER CHAIN RS-140 WROL (CON PASADOR)",3,"Hra",532,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[264,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[265,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[266,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE BANDA TRANSPORTADORA 30",12,"Hra",336,"DIA","D",null,12,12,12,{"$nulls":3},12,12,120,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[267,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[268,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[269,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[270,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[271,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[272,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[273,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE RODILLOS DE CARGA CNT 90MM.X210MM 24-1 520-24MCC",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[274,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[275,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","G",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[276,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","G",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[277,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[278,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[279,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE CONVEYOR BELTS 750MM X 3P X 3.2 X 1.6 X 30\"",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[280,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[281,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","D",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[282,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[283,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[284,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE RODILLOS DE CARGA CNT 90MM.X210MM 24-1 520-24MCC",2,"Hra",168,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[285,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[286,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[287,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[288,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","D",null,12,12,12,{"$nulls":3},12,12,120,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[289,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[290,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","E",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[291,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","E",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[292,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[293,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[294,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE POLIN DE CARGA LISO DIAMETRO 5 1/2\" X 350 MM",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[295,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[296,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[297,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE 1212K   BALL BEARING",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[298,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE 1215KTVC3  BALL BEARING",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[299,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[300,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE CARRIER ROLLER 5\" CGA.D/IMPACTO 24\"",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[301,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[302,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE CHAIN WHEEL RS 100 CNT 24 X 55 MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[303,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE H212 (55MM)",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[304,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE HA2313 (H2313.203)  (2 3/16)   MANGUITO D/MONTAJE",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[305,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","D",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[306,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE POLEA TRACTORA 420X850X50X1190MM",8,"Hra",1344,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[307,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE POLIN DE CARGA LISO DIAMETRO 5 1/2\" X 350 MM",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[308,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[309,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE RODILLOS DE RETORNO RSD 600-24 MCC",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[310,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[311,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE 1217KTVC3  BALL BEARING",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[312,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE BANDA TRANSPORTADORA DE 42",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[313,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE MANGUITO D/MONTAJE H-2317",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[314,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE POLEA MATRIZ ENJEBADO 720X850X80X1370MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[315,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE POLIN DE CARGA PARA FAJA DE 42\"",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[316,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE POLIN DE RETORNO PARA FAJA DE 42\"",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[317,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[318,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[319,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE SN517  PILLOW BLOCK BALL BEARING",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[320,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",199.5,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[321,{"$f":"CONCATENATE(C329,D329)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE BALL BEARING NK-318-K",2,"Hra",798,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[{"$f":"+A329+1","v":322},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",399,"DIA","C",null,{"$f":"+H330","v":12},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$nulls":3},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$nulls":4},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$nulls":3},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$nulls":4},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$nulls":4},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$nulls":3},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$f":"H330*3","v":36},{"$nulls":4},{"$f":"H330*3","v":36},{"$f":"H330","v":12},{"$f":"H330","v":12}]
[323,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE CHAIN WHEEL RS-140-C-NT-25X80MM. DIAM.",3,"Hra",798,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[324,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE CHAIN WHELL RS-140-C-NT-17X80MM. DIAM.",3,"Hra",798,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[325,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE H318 MANGUITO",2,"Hra",798,"DIA","E",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[326,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE PILLOW BLOCK FYH- P318",4.5,"Hra",798,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[327,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE POLEA MATRIZ ENJEBADO 720X850X80X1370MM",8,"Hra",1596,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[328,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",4000,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[329,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",4000,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[330,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",199.5,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[331,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",199.5,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[332,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE ROLLER CHAIN RS-140 WROL (CON PASADOR)",3,"Hra",399,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[333,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",4000,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[334,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 4 A  de 30\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",1066.6666666666667,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[335,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 4 A  de 30\"","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",1066.6666666666667,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[336,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 4 A  de 30\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",1066.6666666666667,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[337,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 5B  de 30\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[338,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 5B  de 30\"","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[339,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 5B  de 30\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[340,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancado terciario","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[341,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancado terciario","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[342,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancado terciario","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[343,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancadora secundaria ","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[344,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancadora secundaria ","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[345,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancadora secundaria ","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[346,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","MOTOREDUCTOR FAJA TRANSPORTADORA 4 B 24\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[347,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","MOTOREDUCTOR FAJA TRANSPORTADORA 4 B 24\"","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[348,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","MOTOREDUCTOR FAJA TRANSPORTADORA 4 B 24\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[349,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","TALLER ELECTRICO PLANTA","CONEXIONADO DE MOTORES",5,"Hra",30,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[350,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","TALLER ELECTRICO PLANTA","HERMETIZADO DE MOTOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[351,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","TALLER ELECTRICO PLANTA","TRABAJOS DE TABLEROS",1,"Hra",30,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[352,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","TALLER ELECTRICO PLANTA","TRABAJOS DE TABLEROS",1,"Hra",120,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[353,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","TALLER MECANICO PLANTA","ENGRASE DE EQUIPOS",1,"Hra",30,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[354,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","VALVULA ROTATIVA ","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",666.6666666666666,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[355,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","VALVULA ROTATIVA ","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",666.6666666666666,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[356,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","VALVULA ROTATIVA ","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",666.6666666666666,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[357,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chanacdo Secundario","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",41.666666666666664,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[358,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chanacdo Secundario","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",41.666666666666664,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[359,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chanacdo Secundario","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",41.666666666666664,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[360,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chancado Terciario","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[361,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chancado Terciario","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[362,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chancado Terciario","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[363,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",5,"Hra",40,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[364,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[365,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",1280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[366,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[367,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[368,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[369,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[370,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[371,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",160,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[372,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",80,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[373,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[374,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[375,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[376,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE ORING",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[377,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",160,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[378,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[379,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[380,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[381,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[382,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",1280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[383,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",4,"Hra",20,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[384,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",4,"Hra",20,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[385,{"$f":"CONCATENATE(C393,D393)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",640,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A393+1","v":386},"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",80,"DIA","D",null,{"$f":"+H394","v":4},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$nulls":3},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$nulls":4},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$nulls":3},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$nulls":4},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$nulls":4},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$nulls":3},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$f":"H394*3","v":12},{"$nulls":4},{"$f":"H394*3","v":12},{"$f":"H394","v":4},{"$f":"H394","v":4}]
[387,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",320,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[388,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",320,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[389,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",80,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[390,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[391,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",20,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[392,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",160,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[393,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE ORING",4,"Hra",20,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[394,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[395,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[396,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",320,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[397,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE ANILLO DE PISTON",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[398,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE CAJA DE EMPAQUETADURA (CAJA DE EXPELLER)",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[399,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE COVER PLATE",4,"Hra",84,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[400,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE EJE",4,"Hra",2688,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[401,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE EXPELLER",4,"Hra",168,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[402,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE EXPELLER RING",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[403,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",84,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[404,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE IMPELLER O'RING",4,"Hra",84,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[405,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE IMPULSOR",4,"Hra",84,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[406,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE LABERINTO",4,"Hra",672,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[407,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE LANTERN RING (DISTRIBUIDOR DE AGUA)",4,"Hra",84,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[408,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE NECK RING",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[409,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE OILSEAL DE TAPA LATERAL",4,"Hra",672,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[410,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE RETENEDOR DE GRASA",4,"Hra",2688,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[411,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[412,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[413,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE ROLLER BEARING 938+932 (RODAMIENTO)",4,"Hra",336,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[414,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE SHAFT SLEEVE (BOCINA)",4,"Hra",84,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[415,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE SHAFT SLEEVE O-RING",4,"Hra",84,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[416,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE TAPA LATERAL",4,"Hra",672,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[417,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE TROAT BUSH",4,"Hra",84,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[418,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[419,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE 129-4 BUJE CIERRE HIDRAULICO (DISTRIBUIDOR DE AGUA)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[420,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE ANILLO DE NEOPRENO DE BAJA",4,"Hra",96,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[421,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE ANILLO NEOPRENE",4,"Hra",96,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[422,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE BEARING  5318WBR = 3318(RODAMIENTO)",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[423,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE BOTADOR D/AGUA LADO IMPULSOR",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[424,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE BOTADOR D/AGUA LADO TRANSMISION (A)",4,"Hra",192,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[425,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE CAJA DE PRENSA ESTOPAS",4,"Hra",3072,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[426,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE COVER PLATE",4,"Hra",48,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[427,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE EJE",4,"Hra",3072,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[428,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE FORRO LADO DE PRENSA ESTOPA BOMBA 8 X 6 DENVER (FRAME PLATE)",4,"Hra",48,"DIA","F",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[429,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE IMPULSOR CERRADO PARA BOMBA DENVER 8 X 6",4,"Hra",48,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[430,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE MANGA PARA EJE (BOCINA)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[431,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE OIL SEAL ( C )",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[432,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE OIL SEAL (D)",4,"Hra",192,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[433,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE PERNOS D/LA PLACA D/SELLO",4,"Hra",192,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[434,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE PLACA D/SELLO",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[435,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE PLATO DE SUCCION BOMBA DENVER 8 X 6 (TROAT BUSH)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[436,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[437,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[438,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (A)",4,"Hra",384,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[439,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (B)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[440,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE TUBERIA DE SUCCION BRIDADA BOMBA 8X6 SRL",4,"Hra",96,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[441,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","F",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[442,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",40,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[443,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[444,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",1280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[445,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[446,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[447,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",640,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[448,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[449,{"$f":"CONCATENATE(C457,D457)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A457+1","v":450},"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",320,"DIA","C",null,{"$f":"+H458","v":4},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$nulls":3},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$nulls":4},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$nulls":3},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$nulls":4},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$nulls":4},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$nulls":3},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$f":"H458*3","v":12},{"$nulls":4},{"$f":"H458*3","v":12},{"$f":"H458","v":4},{"$f":"H458","v":4}]
[451,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",80,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[452,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",20,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[453,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[454,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",160,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[455,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE ORING",4,"Hra",20,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[456,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[457,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[458,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",320,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[459,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",60,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[460,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",120,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[461,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",1920,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[462,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[463,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[464,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",1221.8181818181818,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[465,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[466,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[467,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[468,{"$f":"CONCATENATE(C476,D476)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[469,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[470,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[471,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[472,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE ORING",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[473,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[474,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[475,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[476,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[477,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[478,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[479,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE ANILLO DE PISTON",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[480,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE CAJA DE EMPAQUETADURA (CAJA DE EXPELLER)",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[481,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE COVER PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[482,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE EJE",4,"Hra",3072,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[483,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE EXPELLER",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[484,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE EXPELLER RING",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[485,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[486,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE IMPELLER O'RING",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[487,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE IMPULSOR",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[488,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE LABERINTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[489,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE LANTERN RING (DISTRIBUIDOR DE AGUA)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[490,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE NECK RING",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[491,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE OILSEAL DE TAPA LATERAL",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[492,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE RETENEDOR DE GRASA",4,"Hra",1536,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[493,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[494,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[495,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE ROLLER BEARING 938+932 (RODAMIENTO)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[496,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE SHAFT SLEEVE (BOCINA)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[497,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE SHAFT SLEEVE O-RING",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[498,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE TAPA LATERAL",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[499,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE TROAT BUSH",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[500,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[501,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE 129-4 BUJE CIERRE HIDRAULICO (DISTRIBUIDOR DE AGUA)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[502,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE ANILLO DE NEOPRENO DE BAJA",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[503,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE ANILLO NEOPRENE",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[504,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE BEARING  5318WBR = 3318(RODAMIENTO)",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[505,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE BOTADOR D/AGUA LADO IMPULSOR",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[506,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE BOTADOR D/AGUA LADO TRANSMISION (A)",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[507,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE CAJA DE PRENSA ESTOPAS",4,"Hra",3072,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[508,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE COVER PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[509,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE EJE",4,"Hra",3072,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[510,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE FORRO LADO DE PRENSA ESTOPA BOMBA 8 X 6 DENVER (FRAME PLATE)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[511,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE IMPULSOR CERRADO PARA BOMBA DENVER 8 X 6",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[512,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE MANGA PARA EJE (BOCINA)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[513,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE OIL SEAL ( C )",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A521+1","v":514},"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE OIL SEAL (D)",4,"Hra",192,"DIA","C",null,{"$f":"+H522","v":4},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$nulls":3},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$nulls":4},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$nulls":3},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$nulls":4},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$nulls":4},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$nulls":3},{"$f":"H522","v":4},{"$f":"H522","v":4},{"$f":"H522*3","v":12},{"$nulls":4},{"$f":"H522*3","v":12},{"$f":"H522","v":4},{"$f":"H522","v":4}]
[515,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE PERNOS D/LA PLACA D/SELLO",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[516,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE PLACA D/SELLO",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[517,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE PLATO DE SUCCION BOMBA DENVER 8 X 6 (TROAT BUSH)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[518,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[519,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[520,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (A)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[521,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (B)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[522,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE TUBERIA DE SUCCION BRIDADA BOMBA 8X6 SRL",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[523,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[524,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[525,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[526,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",1920,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[527,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[528,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[529,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",1221.8181818181818,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[530,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[531,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[532,{"$f":"CONCATENATE(C540,D540)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[533,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[534,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[535,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[536,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[537,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE ORING",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[538,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[539,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[540,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[541,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA DE LUBRICACIÓN ALTA PARA MOLINO FULLER (2 UNIDADES)","CAMBIO DE ELEMENTO DE FILTRO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[542,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA DE LUBRICACIÓN ALTA PARA MOLINO FULLER (2 UNIDADES)","CAMBIO DE FILTRO LAVABLE EN MALLA ACERO INOXI 40MI",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[543,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA DE LUBRICACIÓN BAJA PARA MOLINO FULLER (2 UNIDADES)","CAMBIO DE ELEMENTO DE FILTRO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[544,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA DE LUBRICACIÓN BAJA PARA MOLINO FULLER (2 UNIDADES)","CAMBIO DE FILTRO LAVABLE EN MALLA ACERO INOXI 40MI",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[545,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[546,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE CANASTILLA INFERIOR 3.1/2 EN CAUCHO",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[547,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[548,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE CANASTILLA SUPERIOR 3.1/2\" EN CAUCHO",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[549,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE COVER PLATE (TAPA 3.1/2\" GALIGHER EN CAUCHO)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[550,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE IMPULSOR VERTICAL GALIGHER 3.1/2\" (11-120)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[551,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE MANGUITO H-322",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[552,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE PUMP CASING (CAJA VERTICAL 3.1/2\" EN CAUCHO)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[553,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE RETEN INFERIOR CR-39934",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[554,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE RETEN SUPERIOR CR-31189",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[555,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE RODAMIENTO 22222EK",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[556,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE RODAMIENTO CIERRE 22313 E",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[557,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[558,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[559,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE TUBO DE DESCARGA (90-240)",4,"Hra",3360,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[560,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[561,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL DE MOLINO FULLER","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[562,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL DE MOLINO FULLER","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[563,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL DE MOLINO FULLER","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[564,"OPEXMMO","OPEXM","MO","MOLIENDA","CEDAZO DE ALTA FRECUENCIA MOLINO 8X11","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[565,"OPEXMMO","OPEXM","MO","MOLIENDA","CEDAZO DE ALTA FRECUENCIA MOLINO 8X11","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[566,"OPEXMMO","OPEXM","MO","MOLIENDA","CEDAZO DE ALTA FRECUENCIA MOLINO 8X11","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[567,"OPEXMMO","OPEXM","MO","MOLIENDA","Celda de Flotación SK-240","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[568,"OPEXMMO","OPEXM","MO","MOLIENDA","Celda de Flotación SK-240","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[569,"OPEXMMO","OPEXM","MO","MOLIENDA","Celda de Flotación SK-240","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[570,"OPEXMMO","OPEXM","MO","MOLIENDA","CICLON DE CAL  D-10","CAMBIO DE APEX",4,"Hra",112,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[571,"OPEXMMO","OPEXM","MO","MOLIENDA","CICLON DE CAL  D-10","CAMBIO DE APEX CILINDRICO",4,"Hra",112,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[572,"OPEXMMO","OPEXM","MO","MOLIENDA","CICLON DE CAL  D-10","CAMBIO DE CABEZAL DE CAUCHO",4,"Hra",224,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[573,"OPEXMMO","OPEXM","MO","MOLIENDA","CICLON DE CAL  D-10","CAMBIO DE FORRO JEBE CILINDRICO",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[574,"OPEXMMO","OPEXM","MO","MOLIENDA","CICLON DE CAL  D-10","CAMBIO DE FORRO JEBE CUERPO CONICO",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[575,"OPEXMMO","OPEXM","MO","MOLIENDA","CICLON DE CAL  D-10","CAMBIO DE MANGA DE JEBE DE DESCARGA",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[576,"OPEXMMO","OPEXM","MO","MOLIENDA","CICLON DE CAL  D-10","CAMBIO DE VORTEX",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[577,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE 1213KTVC3   BALL BEARING NTN",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[{"$f":"+A585+1","v":578},"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","C",null,{"$f":"+H586","v":12},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$nulls":3},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$nulls":4},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$nulls":3},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$nulls":4},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$nulls":4},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$nulls":3},{"$f":"H586","v":12},{"$f":"H586","v":12},{"$f":"H586*3","v":36},{"$nulls":4},{"$f":"H586*3","v":36},{"$f":"H586","v":12},{"$f":"H586","v":12}]
[579,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE CHAIN WHEEL RS-80-C-NT17X40MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[580,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE CHAIN WHEEL RS-80-C-NT-40X40MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[581,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[582,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE PILLOW BLOCK BEARING FYH-4KP-213+HS-313-",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[583,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",672,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[584,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[585,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE POLINES RECTAS D/IMPACTO 102X686X25X890",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[586,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE RODAMIENTO22313 E1K C3",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[587,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE ROLLER CHAIN RS-80",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[588,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",5,"Hra",168,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[589,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE BANDA TRANSPORTADORA DE 24",5,"Hra",336,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[590,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE CADENA",5,"Hra",336,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[591,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",5,"Hra",672,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[592,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",5,"Hra",672,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[593,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",5,"Hra",672,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[594,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE PILLOW BLOCK UKP 313",5,"Hra",672,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[595,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",5,"Hra",1344,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[596,{"$f":"CONCATENATE(C604,D604)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",5,"Hra",168,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[597,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE RODAMIENTOS",5,"Hra",672,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[598,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[599,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[600,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE ROLLER CHAIN RS-100",5,"Hra",336,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[601,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[602,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[603,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE BANDA TRANSPORTADORA DE 24",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[604,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE CADENA",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[605,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[606,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[607,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[608,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[609,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[610,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[611,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE RODAMIENTOS",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[612,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[613,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de Molino de Cal de 24\" x longitud de 11.5m","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",100,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[614,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de Molino de Cal de 24\" x longitud de 11.5m","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",100,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[615,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de Molino de Cal de 24\" x longitud de 11.5m","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",100,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[616,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora N 4 MOLINO FULLER DE 24\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[617,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora N 4 MOLINO FULLER DE 24\"","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[618,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora N 4 MOLINO FULLER DE 24\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[619,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE 012062 CARBON SEAL",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[620,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE BRONZE INSERT",6,"Hra",2932.3636363636365,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[621,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE CONTRA EJE PIÑON DEL MOLINO FULLER DIAM. 9.6' X 14'",24,"Hra",5864.727272727273,"DIA","C",null,24,24,24,{"$nulls":3},24,24,24,{"$nulls":4},24,24,24,{"$nulls":3},24,24,{"$nulls":4},24,24,24,{"$nulls":4},24,24,24,{"$nulls":3},24,24,72,{"$nulls":4},72,24,24]
[622,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE CORAZA TAPA DE ALIMENTACION",12,"Hra",183.27272727272728,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[623,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE CORAZA TAPA DE DESCARGA",12,"Hra",183.27272727272728,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[624,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE FILLING SEGMENT",4,"Hra",366.54545454545456,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[625,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE FORRO DE CILINDRO - GETS",4,"Hra",366.54545454545456,"DIA","C",null,60,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[626,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE FRICTION SHOES ASSEMBLY",3.5,"Hra",183.27272727272728,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[627,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE LEVANTADOR TAPA DE ALIMENTACION",2,"Hra",183.27272727272728,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[628,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE LEVANTADOR TAPA DE DESCARGA",2,"Hra",183.27272727272728,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[629,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE PERNOS Y BOCINA DEL ACOPLE DEL REDUCTOR MOLINO FULLER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[630,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE RELEASE SPRING",2.5,"Hra",91.63636363636364,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[631,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE REPLACEMENT FRICTION LINING & FASTENERS",3.5,"Hra",183.27272727272728,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,168,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[632,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE SELLO SPOUT FEEDER",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[633,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE SHELL LINER - GETS",4,"Hra",366.54545454545456,"DIA","C",null,60,4,4,{"$nulls":3},72,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[634,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE SPOUT FEEDER  MOLINO FULLER - GETS",4.5,"Hra",183.27272727272728,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[635,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE TORQUE BAR",4,"Hra",183.27272727272728,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[636,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE TROMMEL",4,"Hra",366.54545454545456,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[637,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE TRUNION LINER - DESCARGA",6,"Hra",2932.3636363636365,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[638,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE TRUNNION LINER - ALIMENTACION",6,"Hra",2932.3636363636365,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[639,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE  HEAD PLATE (ACCS. COMPLETO)",12,"Hra",183.27272727272728,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[640,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE  LINER TYPE \"A\"",12,"Hra",424.42105263157896,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[641,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE 110 TRUNNION METAL F/CHARGE SIDE - GETS",12,"Hra",2932.3636363636365,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[{"$f":"+A649+1","v":642},"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE 124 TRUNNION LINER F/DISCHARGE",12,"Hra",2932.3636363636365,"DIA","C",null,{"$f":"+H650","v":12},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$nulls":3},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$nulls":4},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$nulls":3},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$nulls":4},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$nulls":4},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$nulls":3},{"$f":"H650","v":12},{"$f":"H650","v":12},{"$f":"H650*3","v":36},{"$nulls":4},{"$f":"H650*3","v":36},{"$f":"H650","v":12},{"$f":"H650","v":12}]
[643,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE 208 TRUNNION D/ENTRADA",12,"Hra",2932.3636363636365,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[644,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE BOCINAS DE JEBE PARA ACOPLAMIENTO CONTRA EJE",3,"Hra",2932.3636363636365,"DIA","C",null,48,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[645,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE BOLT F/LINER",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[646,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE CASQUILLO DE BRONCE DE MOLINO 8X11 LADO CARGA",6,"Hra",1466.1818181818182,"DIA","C",null,144,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[647,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE CASQUILLO EN BRONCE DE MOLINO 8X11 LADO DESCARGA",6,"Hra",1466.1818181818182,"DIA","C",null,144,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[648,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE FORRO METALICO DOBLE ONDA P/MOLINO 8 X 11",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},168,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[649,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE LIFTER BAR C/ACCESORIOS",12,"Hra",183.27272727272728,"DIA","C",null,12,12,12,{"$nulls":3},24,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[650,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE LINER TYPE \"B\"",12,"Hra",366.54545454545456,"DIA","C",null,12,12,12,{"$nulls":3},24,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[651,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE LINER TYPE \"C\"",12,"Hra",366.54545454545456,"DIA","C",null,12,12,12,{"$nulls":3},24,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[652,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE PERNO PARA FORRO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},24,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[653,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE PERNOS P/ACOPLA. TIPO BRIDA",6,"Hra",2932.3636363636365,"DIA","C",null,60,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[654,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE PINION GEAR",10,"Hra",2932.3636363636365,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[655,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE SPOUT FEEDER - GETS",12,"Hra",183.27272727272728,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[656,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE TROMMEL",6,"Hra",366.54545454545456,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[657,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE TRUNION METAL F/ DISCHARGE SIDE - GETS",12,"Hra",2932.3636363636365,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[658,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE BOCINAS DE JEBE PARA ACOPLAMIENTO",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[659,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE CASQUILLO EMBABITADO DE MOLINO 8 X 3",8,"Hra",560,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[660,{"$f":"CONCATENATE(C668,D668)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE EMPAQUETADURA D/LANA 1/2\"X0.80MTSX1.20MT\"",2.5,"Hra",70,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[661,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO CABEZAL DESCARGA TIPO G - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[662,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO \"H1\" - GETS",12,"Hra",1120,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[663,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO \"H2\" - GETS",12,"Hra",2240,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[664,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO \"I\" - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[665,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO C - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,168,36,{"$nulls":4},36,12,12]
[666,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO D - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[667,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO E - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[668,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO F - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[669,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE HEAD PLATE",6,"Hra",280,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[670,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE HEAD PLATES ANILLO \"B\"",12,"Hra",280,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[671,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE LIFTER BAR \"B\" COMPLETO",12,"Hra",280,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[672,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE LIFTER BAR C/ACCESORIOS (ENTRADA MOLINO)",12,"Hra",280,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[673,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE PERNO PARA FORRO - GETS",6,"Hra",560,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[674,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE PERNOS PARA ACOPLA.MIENTO CONTRA EJE",6,"Hra",480,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[675,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE PINION GEAR",24,"Hra",2240,"DIA","C",null,24,24,24,{"$nulls":3},24,24,24,{"$nulls":4},24,24,24,{"$nulls":3},24,24,{"$nulls":4},24,24,24,{"$nulls":4},24,24,24,{"$nulls":3},24,24,72,{"$nulls":4},72,24,24]
[676,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE ROLLER BEARING",6,"Hra",1920,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[677,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE SPOUT FEEDER MOLINO 8X3 - GETS",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[678,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE BOCINAS DE JEBE PARA ACOPLAMIENTO",3,"Hra",560,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[679,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE CASQUILLO EMBABITADO DE MOLINO 8 X 3",2,"Hra",560,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[680,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE EMPAQUETADURA DE LANA",2.5,"Hra",70,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[681,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO CABEZAL DESCARGA TIPO G - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},96,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[682,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO \"H1\" - GETS",12,"Hra",1120,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},96,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[683,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO \"H2\" - GETS",12,"Hra",2240,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},96,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[684,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO \"I\" - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},96,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[685,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO C - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},96,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[686,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO D - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},96,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[687,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO E - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},96,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[688,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO F - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},96,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[689,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE HEAD PLATE",6,"Hra",280,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[690,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE HEAD PLATES ANILLO \"B\"",6,"Hra",280,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[691,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE LIFTER BAR \"B\" COMPLETO",12,"Hra",280,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[692,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE LIFTER BAR C/ACCESORIOS (ENTRADA MOLINO)",12,"Hra",280,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[693,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE PERNO PARA FORRO - GETS",6,"Hra",560,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[694,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE PERNOS PARA ACOPLA.MIENTO CONTRA EJE",6,"Hra",480,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[695,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE PINION GEAR",24,"Hra",2240,"DIA","C",null,24,24,24,{"$nulls":3},24,24,24,{"$nulls":4},24,24,24,{"$nulls":3},24,24,{"$nulls":4},24,24,24,{"$nulls":4},24,24,24,{"$nulls":3},24,24,72,{"$nulls":4},72,24,24]
[696,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE ROLLER BEARING",4,"Hra",3840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[697,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE SPOUT FEEDER MOLINO 8X3 - GETS",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[698,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO DE CAL 4\" X 8\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[699,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO DE CAL 4\" X 8\"","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[700,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO DE CAL 4\" X 8\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",100,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[701,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE 34 BRIDGE COUPLING F/SHAFT PULLEY",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[702,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE EMPAQUETADURA DE LANA",2.5,"Hra",72,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[703,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE FORRO T. D. OUTER. + CENTER RING - GETS",12,"Hra",576,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[704,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE FORRO T.A. ANILLO EXT. + INT",12,"Hra",576,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[705,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE FORRO TIPO \"I\" - GETS",12,"Hra",576,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[{"$f":"+A713+1","v":706},"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE HEAD PLATE",6,"Hra",576,"DIA","C",null,{"$f":"+H714","v":6},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$nulls":3},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$nulls":4},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$nulls":3},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$nulls":4},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$nulls":4},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$nulls":3},{"$f":"H714","v":6},{"$f":"H714","v":6},{"$f":"H714*3","v":18},{"$nulls":4},{"$f":"H714*3","v":18},{"$f":"H714","v":6},{"$f":"H714","v":6}]
[707,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE LIFTER BARS CILINDRO + ELEM. SUJ.",12,"Hra",576,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[708,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE PERNOS PARA ACOPLA.MIENTO CONTRA EJE",6,"Hra",576,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[709,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE PINION GEAR",24,"Hra",18432,"DIA","C",null,24,24,24,{"$nulls":3},24,24,24,{"$nulls":4},24,24,24,{"$nulls":3},24,24,{"$nulls":4},24,24,24,{"$nulls":4},24,24,24,{"$nulls":3},24,24,72,{"$nulls":4},72,24,24]
[710,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE SPOUT FEEDER MOLINO 8X3 - GETS",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[711,"OPEXMMO","OPEXM","MO","MOLIENDA","Motor de lubricacion 01 molino 8x11","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[712,"OPEXMMO","OPEXM","MO","MOLIENDA","Motor de lubricacion 01 molino 8x11","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[713,"OPEXMMO","OPEXM","MO","MOLIENDA","Motor de lubricacion 01 molino 8x11","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[714,"OPEXMMO","OPEXM","MO","MOLIENDA","Motor de lubricacion 02 molino 8x11","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[715,"OPEXMMO","OPEXM","MO","MOLIENDA","Motor de lubricacion 02 molino 8x11","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[716,"OPEXMMO","OPEXM","MO","MOLIENDA","Motor de lubricacion 02 molino 8x11","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[717,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE BRIDA CONEXION DESCARGA",5,"Hra",112,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[718,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE BRIDA Y CONEXION DE ALIMENTAD",5,"Hra",112,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[719,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE CUERPO CILINDRICO METALICO",5,"Hra",1792,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[720,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE EMPAQUETADURA P/ABRAZADERA VITAULICA 6\"",2,"Hra",224,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[721,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE FORRO DE JEBE CABEZAL",3.5,"Hra",224,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[722,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE FORRO JEBE CILINDRICO",5.5,"Hra",224,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[723,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE FORRO JEBE CPO. CONICO.L",5.5,"Hra",224,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[724,{"$f":"CONCATENATE(C732,D732)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE FORRO JEBE CPO. CONICO.S",5.5,"Hra",224,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[725,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE TAPA DE FE. DEL CABEZAL",3.5,"Hra",448,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[726,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE TAPA DE JEBE CABEZAL",3.5,"Hra",448,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[727,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE TUBERIA REVESTIDA CON CAUCHO INTERNAMENT",2.5,"Hra",896,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[728,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE BRIDA CONEXION DESCARGA",1,"Hra",112,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[729,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE BRIDA Y CONEXION DE ALIMENTAD",1,"Hra",112,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[730,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE CUERPO CILINDRICO METALICO",5,"Hra",1792,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[731,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE EMPAQUETADURA P/ABRAZADERA VITAULICA 6\"",2,"Hra",224,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[732,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE FORRO DE JEBE CABEZAL",3.5,"Hra",224,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[733,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE FORRO JEBE CILINDRICO",5.5,"Hra",224,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[734,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE FORRO JEBE CPO. CONICO.L",5.5,"Hra",224,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[735,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE FORRO JEBE CPO. CONICO.S",5.5,"Hra",224,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[736,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE TAPA DE FE. DEL CABEZAL",3.5,"Hra",448,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[737,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE TAPA DE JEBE CABEZAL",3.5,"Hra",448,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[738,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE TUBERIA REVESTIDA CON CAUCHO INTERNAMENT",2.5,"Hra",896,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[739,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE  BRIDA DE DESCARGA",1,"Hra",168,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[740,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE BRIDA DE ALIMENTACION  CICLON D6",1,"Hra",168,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[741,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE CABEZAL METALICO CICLON D6",3.5,"Hra",672,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[742,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE CUERPO CILINDRICO METALICO CICLON D6",5,"Hra",1344,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[743,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE CUERPO CONICO METALICO",5,"Hra",336,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[744,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE FORRO DE JEBE CABEZAL",3.5,"Hra",336,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[745,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE FORRO DE JEBE CONICO 12 GRADOS",5.5,"Hra",672,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[746,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE FORRO DE JEBE CUERPO CILINDRO",5.5,"Hra",672,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[747,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE MANGA DE JEBE DE DESCARGA",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[748,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE PLACA DE MANGA",3,"Hra",168,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[749,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE PLACA SEPARADORA",3,"Hra",168,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[750,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE SOPORTE DE APEX",1,"Hra",168,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[751,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE TAPA DE JEBE DEL CABEZAL",3.5,"Hra",672,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[752,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE TAPA METALICA CABEZAL",3.5,"Hra",672,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[753,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° DE MOLINOS 01 Y 02 - (D-10)","CAMBIO DE BRIDA Y CONEXION ALIMENTACION",1,"Hra",168,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[754,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° DE MOLINOS 01 Y 02 - (D-10)","CAMBIO DE BRIDA Y CONEXION DESCARGA",1,"Hra",168,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[755,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° DE MOLINOS 01 Y 02 - (D-10)","CAMBIO DE CABEZAL DE CAUCHO",3.5,"Hra",336,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[756,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° DE MOLINOS 01 Y 02 - (D-10)","CAMBIO DE FORRO JEBE CILINDRICO",5.5,"Hra",672,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[757,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° DE MOLINOS 01 Y 02 - (D-10)","CAMBIO DE FORRO JEBE CUERPO CONICO",5.5,"Hra",672,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[758,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° DE MOLINOS 01 Y 02 - (D-10)","CAMBIO DE MANGA DE JEBE DE DESCARGA",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[759,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° DE MOLINOS 01 Y 02 - (D-10)","CAMBIO DE TAPA DE JEBE DE CABEZAL",3.5,"Hra",672,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":4},3.5,3.5,3.5,{"$nulls":3},3.5,3.5,10.5,{"$nulls":4},10.5,3.5,3.5]
[760,"OPEXMMO","OPEXM","MO","MOLIENDA","TALLER ELECTRICO PLANTA","CONEXIONADO DE MOTORES",5,"Hra",30,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[761,"OPEXMMO","OPEXM","MO","MOLIENDA","TALLER ELECTRICO PLANTA","HERMETIZADO DE MOTOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[762,"OPEXMMO","OPEXM","MO","MOLIENDA","TALLER ELECTRICO PLANTA","LIMPIEZA DE MOTOR",5,"Hra",30,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[763,"OPEXMMO","OPEXM","MO","MOLIENDA","TALLER ELECTRICO PLANTA","TRABAJOS DE TABLEROS",1,"Hra",30,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[764,"OPEXMMO","OPEXM","MO","MOLIENDA","TALLER ELECTRICO PLANTA","TRABAJOS DE TABLEROS",1,"Hra",120,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[765,"OPEXMMO","OPEXM","MO","MOLIENDA","TALLER MECANICO PLANTA","ENGRASE DE EQUIPOS",1,"Hra",30,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[766,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","B. V. N°9 concentrado de plomo","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[767,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","B. V. N°9 concentrado de plomo","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[768,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","B. V. N°9 concentrado de plomo","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[769,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Bomb agua filtro prensa","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[{"$f":"+A777+1","v":770},"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Bomb agua filtro prensa","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,{"$f":"+H778","v":5},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$nulls":3},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$nulls":4},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$nulls":3},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$nulls":4},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$nulls":4},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$nulls":3},{"$f":"H778","v":5},{"$f":"H778","v":5},{"$f":"H778*3","v":15},{"$nulls":4},{"$f":"H778*3","v":15},{"$f":"H778","v":5},{"$f":"H778","v":5}]
[771,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Bomb agua filtro prensa","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[772,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE BEARING  6535/6580(RODAMIENTO)",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[773,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE BOCINA (SHAFT SLEEVE)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[774,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE CAMISA DE EJE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[775,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE DISTRIBUIDOR DE AGUA (E118-1 P50 RETENEDORES DE LA LINTERNA)",4,"Hra",144,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[776,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE E-025 END COVER SHIM SET (LAINA)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[777,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE EJE PARA BOMBA 77",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[778,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE FRAME PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[779,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE IMPULSOR (BOMBA WARMAN 6 X 4 EAH)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[780,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE LABERIHT (LABERINTO)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[781,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE SHAFT ORING",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[782,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE SHAFT SLEEVE SPACER",4,"Hra",144,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[783,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE TROAT BUSH",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[784,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE BEARING  6535/6580(RODAMIENTO)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[785,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE BOCINA (SHAFT SLEEVE)",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[786,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE CAMISA DE EJE",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[787,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE DISTRIBUIDOR DE AGUA (E118-1 P50 RETENEDORES DE LA LINTERNA)",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[788,{"$f":"CONCATENATE(C796,D796)","v":"OPEXMFP"},"OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE E-025 END COVER SHIM SET (LAINA)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[789,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE EJE PARA BOMBA 77",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[790,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE FRAME PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[791,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE IMPULSOR (BOMBA WARMAN 6 X 4 EAH)",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[792,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE LABERIHT (LABERINTO)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[793,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE SHAFT ORING",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[794,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE SHAFT SLEEVE SPACER",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[795,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE TROAT BUSH",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[796,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE 129-4 BUJE CIERRE HIDRAULICO (DISTRIBUIDOR DE AGUA)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[797,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE ANILLO DE NEOPRENO DE BAJA",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[798,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE ANILLO NEOPRENE",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[799,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE BEARING  5318WBR = 3318(RODAMIENTO)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[800,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE BOTADOR D/AGUA LADO IMPULSOR",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[801,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE BOTADOR D/AGUA LADO TRANSMISION (A)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[802,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE CAJA DE PRENSA ESTOPAS",4,"Hra",1920,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[803,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE COVER PLATE",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[804,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE EJE",4,"Hra",960,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[805,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE FORRO LADO DE PRENSA ESTOPA BOMBA 8 X 6 DENVER (FRAME PLATE)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[806,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE IMPULSOR CERRADO PARA BOMBA DENVER 8 X 6",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[807,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE MANGA PARA EJE (BOCINA)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[808,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE OIL SEAL ( C )",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[809,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE OIL SEAL (D)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[810,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE PERNOS D/LA PLACA D/SELLO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[811,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE PLACA D/SELLO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[812,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE PLATO DE SUCCION BOMBA DENVER 8 X 6 (TROAT BUSH)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[813,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (A)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[814,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (B)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[815,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE TUBERIA DE SUCCION BRIDADA BOMBA 8X6 SRL",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[816,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE 129-4 BUJE CIERRE HIDRAULICO (DISTRIBUIDOR DE AGUA)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[817,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE ANILLO DE NEOPRENO DE BAJA",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[818,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE ANILLO NEOPRENE",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[819,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE BEARING  5318WBR = 3318(RODAMIENTO)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[820,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE BOTADOR D/AGUA LADO IMPULSOR",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[821,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE BOTADOR D/AGUA LADO TRANSMISION (A)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[822,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE CAJA DE PRENSA ESTOPAS",4,"Hra",1920,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[823,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE COVER PLATE",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[824,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE EJE",4,"Hra",960,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[825,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE FORRO LADO DE PRENSA ESTOPA BOMBA 8 X 6 DENVER (FRAME PLATE)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[826,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE IMPULSOR CERRADO PARA BOMBA DENVER 8 X 6",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[827,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE MANGA PARA EJE (BOCINA)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[828,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE OIL SEAL ( C )",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[829,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE OIL SEAL (D)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[830,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE PERNOS D/LA PLACA D/SELLO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[831,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE PLACA D/SELLO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[832,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE PLATO DE SUCCION BOMBA DENVER 8 X 6 (TROAT BUSH)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[833,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (A)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A841+1","v":834},"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (B)",4,"Hra",240,"DIA","C",null,{"$f":"+H842","v":4},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$nulls":3},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$nulls":4},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$nulls":3},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$nulls":4},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$nulls":4},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$nulls":3},{"$f":"H842","v":4},{"$f":"H842","v":4},{"$f":"H842*3","v":12},{"$nulls":4},{"$f":"H842*3","v":12},{"$f":"H842","v":4},{"$f":"H842","v":4}]
[835,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE TUBERIA DE SUCCION BRIDADA BOMBA 8X6 SRL",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[836,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[837,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[838,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[839,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE BOCINA",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[840,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE COVER PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[841,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE EJE",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[842,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE EJECTOR",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[843,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[844,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[845,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE EXPELLER",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[846,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE FRAME PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[847,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE IMPULSOR",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[848,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE LABERINTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[849,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE ORING",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[850,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[851,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE RETEN",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[852,{"$f":"CONCATENATE(C860,D860)","v":"OPEXMFP"},"OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[853,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[854,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[855,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[856,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE BOCINA",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[857,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE COVER PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[858,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE EJE",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[859,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE EJECTOR",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[860,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[861,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[862,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE EXPELLER",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[863,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE FRAME PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[864,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE IMPULSOR",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[865,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE LABERINTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[866,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE ORING",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[867,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[868,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE RETEN",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[869,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[870,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[871,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[872,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[873,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE BOCINA",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[874,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE COVER PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[875,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE EJE",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[876,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE EJECTOR",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[877,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[878,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[879,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE EXPELLER",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[880,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE FRAME PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[881,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE IMPULSOR",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[882,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE LABERINTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[883,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE ORING",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[884,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[885,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE RETEN",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[886,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[887,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Bomba espumas plomo","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[888,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Bomba espumas plomo","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[889,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Bomba espumas plomo","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[890,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[891,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[892,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE COVER BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[893,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE DISCHARGE PIPE",4,"Hra",1344,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[894,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1344,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[895,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE IMPULSOR BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[896,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[897,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A905+1","v":898},"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,{"$f":"+H906","v":4},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$nulls":3},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$nulls":4},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$nulls":3},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$nulls":4},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$nulls":4},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$nulls":3},{"$f":"H906","v":4},{"$f":"H906","v":4},{"$f":"H906*3","v":12},{"$nulls":4},{"$f":"H906*3","v":12},{"$f":"H906","v":4},{"$f":"H906","v":4}]
[899,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[900,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[901,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",537.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[902,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",537.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[903,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[904,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[905,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[906,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[907,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[908,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[909,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[910,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[911,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[912,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[913,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[914,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[915,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[916,{"$f":"CONCATENATE(C924,D924)","v":"OPEXMFP"},"OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[917,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[918,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[919,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[920,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[921,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[922,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[923,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[924,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL GALIN GHER DE 2.5 LADO 61 (BOMBA VERTICAL 85)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[925,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL GALIN GHER DE 2.5 LADO 61 (BOMBA VERTICAL 85)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[926,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL GALIN GHER DE 2.5 LADO 61 (BOMBA VERTICAL 85)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[927,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[928,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[929,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[930,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[931,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[932,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[933,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[934,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[935,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[936,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[937,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[938,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[939,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[940,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[941,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[942,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[943,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[944,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[945,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[946,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[947,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[948,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[949,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[950,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[951,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[952,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[953,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[954,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[955,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[956,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[957,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[958,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[959,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[960,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[961,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A969+1","v":962},"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,{"$f":"+H970","v":4},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$nulls":3},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$nulls":4},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$nulls":3},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$nulls":4},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$nulls":4},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$nulls":3},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$f":"H970*3","v":12},{"$nulls":4},{"$f":"H970*3","v":12},{"$f":"H970","v":4},{"$f":"H970","v":4}]
[963,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[964,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[965,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[966,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[967,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[968,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[969,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[970,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[971,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[972,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[973,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[974,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[975,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[976,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[977,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[978,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[979,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[980,{"$f":"CONCATENATE(C988,D988)","v":"OPEXMFP"},"OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[981,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[982,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[983,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[984,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[985,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[986,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[987,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[988,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[989,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[990,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[991,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[992,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[993,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[994,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[996,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[997,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1000,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1001,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1003,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1004,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1006,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1007,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1010,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1011,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1013,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1014,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1016,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1017,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1020,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1021,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1023,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1024,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A1033+1","v":1026},"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,{"$f":"+H1034","v":4},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$nulls":3},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$nulls":4},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$nulls":3},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$nulls":4},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$nulls":4},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$nulls":3},{"$f":"H1034","v":4},{"$f":"H1034","v":4},{"$f":"H1034*3","v":12},{"$nulls":4},{"$f":"H1034*3","v":12},{"$f":"H1034","v":4},{"$f":"H1034","v":4}]
[1027,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1029,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE IMPULSOR RUBBER (BOMBA VERTICAL 2.5)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1030,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1033,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1034,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1036,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1037,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1039,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1040,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1043,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1044,{"$f":"CONCATENATE(C1052,D1052)","v":"OPEXMFP"},"OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1046,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1047,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1049,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1050,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1053,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1054,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1056,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº1","CAMBIO DE 140MM X 170MM X 15MM RETEN INFERIOR D/CAJA D/ RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1057,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº1","CAMBIO DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1059,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº1","CAMBIO DE MANGUITO DE  MONTAJE SUPERIOR  CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1060,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº1","CAMBIO DE MANGUITO DE MONTAJE INFERIOR H3122 CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1063,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº1","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1064,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº1","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1066,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº1","CAMBIO DE TAPA INFERIOR  DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1067,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº1","CAMBIO DE TAPA SUPERIOR DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1069,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº2","CAMBIO DE 100MM X 125MM X 12MM RETEN SUPERIOR D/CAJA D/RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1070,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº2","CAMBIO DE 140MM X 170MM X 15MM RETEN INFERIOR D/CAJA D/ RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1072,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº2","CAMBIO DE DIFUSOR CELDA OK10",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1073,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº2","CAMBIO DE MANGUITO DE  MONTAJE SUPERIOR  CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1076,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº2","CAMBIO DE RODAMIENTO SUPERIOR CELDA  OK 10 (2312CE1 AKM )",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1077,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº2","CAMBIO DE ROTOR CELDA OK 10",5,"Hra",183.27272727272728,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1079,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº2","CAMBIO DE TAPA SUPERIOR DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1080,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº3","CAMBIO DE CAJA DE RODAMIENTOS ",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1082,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº3","CAMBIO DE MANGUITO DE  MONTAJE SUPERIOR ",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1083,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº3","CAMBIO DE MANGUITO DE MONTAJE INFERIOR",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1086,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº3","CAMBIO DE RODAMIENTO INFERIOR  CELDA",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1087,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº3","CAMBIO DE RODAMIENTO SUPERIOR CELDA  O",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1089,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº3","CAMBIO DE TAPA INFERIOR  DE CAJA DE RODAMIENTOS",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[{"$f":"+A1097+1","v":1090},"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº3","CAMBIO DE TAPA SUPERIOR DE CAJA DE RODAMIENTOS",5,"Hra",977.4545454545455,"DIA","C",null,{"$f":"+H1098","v":5},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$nulls":3},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$nulls":4},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$nulls":3},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$nulls":4},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$nulls":4},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$nulls":3},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$f":"H1098*3","v":15},{"$nulls":4},{"$f":"H1098*3","v":15},{"$f":"H1098","v":5},{"$f":"H1098","v":5}]
[1092,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA DE FLOTACION WEMCO ROUGHER PLOMO ( Nº 1)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1093,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA DE FLOTACION WEMCO ROUGHER PLOMO ( Nº 1)","ENGRASE DE EQUIPOS",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1096,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA DE FLOTACION WEMCO ROUGHER PLOMO ( Nº 2)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1097,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA DE FLOTACION WEMCO ROUGHER PLOMO ( Nº 2)","ENGRASE DE EQUIPOS",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1099,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA DE FLOTACION WEMCO ROUGHER PLOMO ( Nº 3)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1100,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA DE FLOTACION WEMCO ROUGHER PLOMO ( Nº 3)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1102,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA DE FLOTACION WEMCO ROUGHER PLOMO ( Nº 3)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1103,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA FLOTA DR- 500 Pb PLOMO ( Nº 1)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,168,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1105,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA FLOTA DR- 500 Pb PLOMO ( Nº 1)","ENGRASE DE EQUIPOS",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1106,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA FLOTA DR- 500 Pb PLOMO ( Nº 1)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1109,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA FLOTA DR- 500 Pb PLOMO ( Nº 2)","ENGRASE DE EQUIPOS",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1110,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA FLOTA DR- 500 Pb PLOMO ( Nº 2)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1112,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb # 03","CAMBIO DE 100-A ANILLO SEGURO D/IMPULSOR",4,"Hra",896,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1113,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb # 03","CAMBIO DE 25 IMPELLER POLIURETANO DR-500",4,"Hra",224,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1115,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb # 03","CAMBIO DE PISO P/CELDA DR-500",10,"Hra",224,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1116,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb # 03","CAMBIO DE RODAMIENTO MUA 3.7/16",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1119,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #01","CAMBIO DE 05 EJE",10,"Hra",896,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1120,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #01","CAMBIO DE ANILLO SEGURO D/IMPULSOR",4,"Hra",896,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1122,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #01","CAMBIO DE PISO P/CELDA DR-500",10,"Hra",224,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1123,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #01","CAMBIO DE RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1125,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #01","CAMBIO DE TUBO DE AEREACION",2,"Hra",896,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1126,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #01","CAMBIO DE V-BELTS B-98 OPTIBELT DR-500",2,"Hra",112,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1129,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #02","CAMBIO DE 25 IMPELLER POLIURETANO DR-500",4,"Hra",224,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1130,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #02","CAMBIO DE 34 TUBO DE AEREACION",2,"Hra",896,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1132,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #02","CAMBIO DE RODAMIENTO MUA 3.7/16",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1133,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #02","CAMBIO DE SECTOR DIFUSOR POLIURETANO CELDA DENVER DR-500",6,"Hra",224,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1135,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDAS OK-10 DE ZINC Y PB","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1136,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 01 de 30\" x longitud de 16m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1139,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 01 de 30\" x longitud de 16m","CAMBIO DE CHAIN WHEEL RS-140-C-NT-25X80MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1140,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 01 de 30\" x longitud de 16m","CAMBIO DE CHAIN WHELL RS-140-C-NT-17X80MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1142,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 01 de 30\" x longitud de 16m","CAMBIO DE PILLOW BLOCK FYH- P318",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[1143,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 01 de 30\" x longitud de 16m","CAMBIO DE POLEA MATRIZ ENJEBADO 720X850X80X1370MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[1145,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 01 de 30\" x longitud de 16m","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1146,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 01 de 30\" x longitud de 16m","CAMBIO DE ROLLER CHAIN RS-140 WROL (CON PASADOR)",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1148,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 02 de 22\" x longitud 34m","CAMBIO DE CHUMACERA P214 (SYJ514)",2.5,"Hra",672,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[1149,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 02 de 22\" x longitud 34m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[1152,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 02 de 22\" x longitud 34m","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1153,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 03 de 30\" x longitud 29.80m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1155,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 03 de 30\" x longitud 29.80m","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1156,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 03 de 30\" x longitud 29.80m","CAMBIO DE RODILLOS DE RETORNO RSD 600-24 MCC",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1158,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Motor de Acondicionador de Pb 01","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1159,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Motor de Acondicionador de Pb 01","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1162,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Acondicionador 10x10","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1163,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Acondicionador 10x10","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1165,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Agitador holding Tank de Zinc de filtro prensa","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1166,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Agitador holding Tank de Zinc de filtro prensa","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1168,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1169,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2688,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1172,{"$f":"CONCATENATE(C1180,D1180)","v":"OPEXMFZ"},"OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1173,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1175,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1176,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1178,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",84,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1179,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1181,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1182,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",84,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1185,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1186,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1188,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE COVER PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1189,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE EJE",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1191,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1192,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1195,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE IMPULSOR",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1196,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE LABERINTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1198,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1199,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE RETEN",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1201,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1202,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1205,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE COVER PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1206,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE EJE",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1208,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1209,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1211,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE FRAME PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1212,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE IMPULSOR",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1215,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1216,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE RETEN",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A1225+1","v":1218},"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",114.28571428571429,"DIA","C",null,{"$f":"+H1226","v":5},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$nulls":3},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$nulls":4},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$nulls":3},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$nulls":4},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$nulls":4},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$nulls":3},{"$f":"H1226","v":5},{"$f":"H1226","v":5},{"$f":"H1226*3","v":15},{"$nulls":4},{"$f":"H1226*3","v":15},{"$f":"H1226","v":5},{"$f":"H1226","v":5}]
[1219,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",114.28571428571429,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1221,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1222,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1224,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE BOCINA",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1225,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE COVER PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1228,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1229,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1231,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE FRAME PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1232,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE IMPULSOR",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1234,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE ORING",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1235,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1238,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1239,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1241,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE BOCINA",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1242,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE COVER PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1244,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE EJECTOR",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1245,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1248,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE FRAME PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1249,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE IMPULSOR",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1251,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE ORING",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1252,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1254,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1255,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIFUGA 77 A  10X8 E-M","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1257,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIFUGA 77 A  10X8 E-M","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1258,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",114.28571428571429,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1261,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1262,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1264,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE DISCHARGE PIPE",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1265,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1267,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1268,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1271,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1272,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1274,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1275,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1277,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1278,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1281,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE DISCHARGE PIPE",4,"Hra",2240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A1289+1","v":1282},"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1120,"DIA","C",null,{"$f":"+H1290","v":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$nulls":3},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$nulls":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$nulls":3},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$nulls":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$nulls":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$nulls":3},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$f":"H1290*3","v":12},{"$nulls":4},{"$f":"H1290*3","v":12},{"$f":"H1290","v":4},{"$f":"H1290","v":4}]
[1284,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1285,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1287,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1288,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1291,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1292,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1294,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1295,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE DISCHARGE PIPE",4,"Hra",3360,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1297,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1298,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1300,{"$f":"CONCATENATE(C1308,D1308)","v":"OPEXMFZ"},"OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1301,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1304,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1305,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1307,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE CANASTILLA INFERIOR 3.1/2 EN CAUCHO",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1308,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1310,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE COVER PLATE (TAPA 3.1/2\" GALIGHER EN CAUCHO)",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1311,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE IMPULSOR VERTICAL GALIGHER 3.1/2\" (11-120)",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1314,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE RETEN INFERIOR CR-39934",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1315,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE RETEN SUPERIOR CR-31189",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1317,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE RODAMIENTO CIERRE 22313 E",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1318,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE TUBO DE DESCARGA (90-240)",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1320,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1321,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1324,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1325,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1327,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1328,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1330,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1331,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1333,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1334,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1337,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1338,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE IMPULSOR BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1340,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1341,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1343,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1344,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1347,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1348,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1350,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE 100MM X 125MM X 12MM RETEN SUPERIOR D/CAJA D/RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1351,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE 140MM X 170MM X 15MM RETEN INFERIOR D/CAJA D/ RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1353,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE DIFUSOR CELDA OK10",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1354,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE MANGUITO DE  MONTAJE SUPERIOR  CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1357,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE RODAMIENTO SUPERIOR CELDA  OK 10 (2312CE1 AKM )",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1358,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1360,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE ROTOR CELDA OK10",5,"Hra",183.27272727272728,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1361,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE TAPA INFERIOR  DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1363,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1364,{"$f":"CONCATENATE(C1372,D1372)","v":"OPEXMFZ"},"OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE 100MM X 125MM X 12MM RETEN SUPERIOR D/CAJA D/RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1367,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE DIFUSOR CELDA OK10",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1368,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE MANGUITO DE  MONTAJE SUPERIOR  CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1370,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE RODAMIENTO INFERIOR  CELDA OK 10",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1371,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE RODAMIENTO SUPERIOR CELDA  OK 10 (2312CE1 AKM )",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1373,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1374,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE ROTOR CELDA OK10",5,"Hra",183.27272727272728,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1376,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE TAPA SUPERIOR DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1377,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1380,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº3","CAMBIO DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1381,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº3","CAMBIO DE DIFUSOR CELDA OK10",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1383,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº3","CAMBIO DE MANGUITO DE MONTAJE INFERIOR H3122 CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1384,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº3","CAMBIO DE RODAMIENTO INFERIOR  CELDA OK 10",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1386,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº3","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1387,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº3","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1390,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº3","CAMBIO DE TAPA SUPERIOR DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1391,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº3","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1393,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE 140MM X 170MM X 15MM RETEN INFERIOR D/CAJA D/ RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1394,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1396,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE MANGUITO DE  MONTAJE SUPERIOR  CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1397,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE MANGUITO DE MONTAJE INFERIOR H3122 CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1400,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1401,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1403,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE TAPA INFERIOR  DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1404,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE TAPA SUPERIOR DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1406,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","CAMBIO DE 100MM X 125MM X 12MM RETEN SUPERIOR D/CAJA D/RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1407,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","CAMBIO DE 140MM X 170MM X 15MM RETEN INFERIOR D/CAJA D/ RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1409,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","CAMBIO DE DIFUSOR CELDA OK10",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[{"$f":"+A1417+1","v":1410},"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","CAMBIO DE MANGUITO DE  MONTAJE SUPERIOR  CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,{"$f":"+H1418","v":1.5},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$nulls":3},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$nulls":4},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$nulls":3},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$nulls":4},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$nulls":4},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$nulls":3},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$f":"H1418*3","v":4.5},{"$nulls":4},{"$f":"H1418*3","v":4.5},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5}]
[1413,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","CAMBIO DE RODAMIENTO SUPERIOR CELDA  OK 10 (2312CE1 AKM )",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1414,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1416,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","CAMBIO DE ROTOR CELDA OK 10",5,"Hra",183.27272727272728,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1417,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","CAMBIO DE TAPA INFERIOR  DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1419,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1420,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #02","CAMBIO DE 05 EJE D/IMPULSOR",10,"Hra",977.4545454545455,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1423,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #02","CAMBIO DE DIFUSOR CELDA DENVER SUBA-24",6,"Hra",244.36363636363637,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1424,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #02","CAMBIO DE HOOD PLUG P.N. 43-B",2.5,"Hra",488.72727272727275,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[1426,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #02","CAMBIO DE PISO ENJEBADO 39\" X 39\"",10,"Hra",244.36363636363637,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1427,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #03","CAMBIO DE 05 EJE D/IMPULSOR",10,"Hra",977.4545454545455,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1429,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #03","CAMBIO DE 23 HOOD TYPE \"A\"",2.5,"Hra",977.4545454545455,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[1430,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #03","CAMBIO DE DIFUSOR CELDA DENVER SUBA-24",6,"Hra",244.36363636363637,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1433,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #03","CAMBIO DE PISO ENJEBADO 39\" X 39\"",10,"Hra",244.36363636363637,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1434,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 03 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[1436,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 03 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1437,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 03 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1439,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 03 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1440,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 03 - WEMCO 500","CAMBIO DE PISO ENJEBADO DE CELDA WENCO 500P3",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1442,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 03 - WEMCO 500","CAMBIO DE RODAMIENTO 941/932",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1443,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 03 - WEMCO 500","CAMBIO DE W62154-01 END CAP AND SEAL ASSY",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1446,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 05 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1447,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 05 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1449,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 05 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1450,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 05 - WEMCO 500","CAMBIO DE PISO ENJEBADO DE CELDA WENCO 500P3",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1452,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 05 - WEMCO 500","CAMBIO DE RODAMIENTO 941/932",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1453,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 05 - WEMCO 500","CAMBIO DE W62154-01 END CAP AND SEAL ASSY",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1456,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 06 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1457,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 06 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1459,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 06 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1460,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 06 - WEMCO 500","CAMBIO DE PISO ENJEBADO DE CELDA WENCO 500P3",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1462,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 06 - WEMCO 500","CAMBIO DE RODAMIENTO 941/932",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1463,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 06 - WEMCO 500","CAMBIO DE W62154-01 END CAP AND SEAL ASSY",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1466,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #01 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1467,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #01 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1469,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #01 - WEMCO 500","CAMBIO DE FAJAS DE TRANSMISION HERMANADAS",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1470,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #01 - WEMCO 500","CAMBIO DE FAJAS DE TRANSMISION HERMANADAS",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1472,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #01 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1473,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #01 - WEMCO 500","CAMBIO DE PISO ENJEBADO DE CELDA WENCO 500P3",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1476,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #01 - WEMCO 500","CAMBIO DE W62154-01 END CAP AND SEAL ASSY",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1477,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #02 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[1479,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #02 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1480,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #02 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1482,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #02 - WEMCO 500","CAMBIO DE FAJAS DE TRANSMISION HERMANADAS",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1483,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #02 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1485,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #02 - WEMCO 500","CAMBIO DE RING, SUPPORT",1.5,"Hra",366.54545454545456,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1486,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #02 - WEMCO 500","CAMBIO DE RODAMIENTO 941/932",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1489,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #04 - WEMCO 500","CAMBIO DE 6535/6580 RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1490,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #04 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1492,{"$f":"CONCATENATE(C1500,D1500)","v":"OPEXMFZ"},"OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #04 - WEMCO 500","CAMBIO DE COLLAR ASSEMBLY  STL/RUBBER  P.N.63276-05",6,"Hra",1466.1818181818182,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1493,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #04 - WEMCO 500","CAMBIO DE FAJAS DE TRANSMISION HERMANADAS",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1495,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #04 - WEMCO 500","CAMBIO DE PISO ENJEBADO DE CELDA WENCO 500P3",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1496,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #04 - WEMCO 500","CAMBIO DE RING, SUPPORT",1.5,"Hra",366.54545454545456,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1499,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC # 03","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1500,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC # 05","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1502,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC #01","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1503,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC #02","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1505,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (10 MOTOR CELDAS WEMCO)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1506,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (10 MOTOR CELDAS WEMCO)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1509,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (11 MOTOR CELDAS WEMCO)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1510,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (11 MOTOR CELDAS WEMCO)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1512,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (11 MOTOR CELDAS WEMCO)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1513,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (12 MOTOR CELDAS WEMCO)\n","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1515,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (12 MOTOR CELDAS WEMCO)\n","ENGRASE DE EQUIPOS",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1516,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (12 MOTOR CELDAS WEMCO)\n","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1518,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (3 MOTOR CELDAS WEMCO)\n","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1519,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (3 MOTOR CELDAS WEMCO)\n","ENGRASE DE EQUIPOS",5,"Hra",31.25,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1522,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (4 MOTOR CELDAS WEMCO)\n","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1523,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (4 MOTOR CELDAS WEMCO)\n","ENGRASE DE EQUIPOS",5,"Hra",31.25,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1525,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (7MOTOR CELDAS WEMCO)\n","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1526,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (7MOTOR CELDAS WEMCO)\n","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1528,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (7MOTOR CELDAS WEMCO)\n","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1529,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (8 MOTOR CELDAS WEMCO)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1532,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (8 MOTOR CELDAS WEMCO)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1533,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc # 12 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[1535,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc # 12 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1536,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc # 12 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[{"$f":"+A1545+1","v":1538},"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc # 12 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,{"$f":"+H1546","v":2},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$nulls":3},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$nulls":4},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$nulls":3},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$nulls":4},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$nulls":4},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$nulls":3},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$f":"H1546*3","v":6},{"$nulls":4},{"$f":"H1546*3","v":6},{"$f":"H1546","v":2},{"$f":"H1546","v":2}]
[1539,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc # 12 - WEMCO 500","CAMBIO DE PISO ENJEBADO DE CELDA WENCO 500P3",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1542,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc # 12 - WEMCO 500","CAMBIO DE W62154-01 END CAP AND SEAL ASSY",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1543,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #07 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[1545,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #07 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1546,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #07 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1548,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #07 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1549,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #07 - WEMCO 500","CAMBIO DE PISO ENJEBADO DE CELDA WENCO 500P3",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1552,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #07 - WEMCO 500","CAMBIO DE W62154-01 END CAP AND SEAL ASSY",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1553,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN SCAVENGER ZINC #08","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1555,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #08 - WEMCO 500","CAMBIO DE 6535/6580 RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1556,{"$f":"CONCATENATE(C1564,D1564)","v":"OPEXMFZ"},"OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #08 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1558,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #08 - WEMCO 500","CAMBIO DE COLLAR ASSEMBLY  STL/RUBBER  P.N.63276-05",6,"Hra",1466.1818181818182,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1559,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #08 - WEMCO 500","CAMBIO DE FAJAS DE TRANSMISION HERMANADAS",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1561,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #08 - WEMCO 500","CAMBIO DE PISO ENJEBADO DE CELDA WENCO 500P3",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1562,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #08 - WEMCO 500","CAMBIO DE RING, SUPPORT",1.5,"Hra",366.54545454545456,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1565,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN SCAVENGER ZINC #09","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1566,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #09 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[1568,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #09 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1569,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #09 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1571,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #09 - WEMCO 500","CAMBIO DE FAJAS DE TRANSMISION HERMANADAS",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1572,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #09 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1575,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #09 - WEMCO 500","CAMBIO DE RODAMIENTO 941/932",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1576,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #09 - WEMCO 500","CAMBIO DE W62154-01 END CAP AND SEAL ASSY",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1578,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #10 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[1579,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #10 - WEMCO 500","CAMBIO DE 6535/6580 RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[1581,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #10 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1582,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #10 - WEMCO 500","CAMBIO DE COLLAR ASSEMBLY  STL/RUBBER  P.N.63276-05",6,"Hra",1466.1818181818182,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1585,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #10 - WEMCO 500","CAMBIO DE PISO ENJEBADO DE CELDA WENCO 500P3",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1586,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #10 - WEMCO 500","CAMBIO DE RING, SUPPORT",1.5,"Hra",366.54545454545456,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1588,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #10 - WEMCO 500","CAMBIO DE W62154-01 END CAP AND SEAL ASSY",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1589,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #11 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[1591,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #11 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1592,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #11 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1594,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #11 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1595,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #11 - WEMCO 500","CAMBIO DE PISO ENJEBADO DE CELDA WENCO 500P3",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1598,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #11 - WEMCO 500","CAMBIO DE W62154-01 END CAP AND SEAL ASSY",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1599,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE 10 BEARING CUP (LOWER BEARING) F60208-11630.10",2,"Hra",1954.909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,36,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1601,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE 11 DISPERSER",4,"Hra",1954.909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,36,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A1609+1","v":1602},"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE 15 BEARING CUP (UPPER BEARING) F60204-W100369",2,"Hra",1954.909090909091,"DIA","C",null,{"$f":"+H1610","v":2},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$nulls":3},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$nulls":4},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$nulls":3},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$nulls":4},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$nulls":4},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$nulls":3},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$f":"H1610*3","v":6},{"$nulls":4},{"$f":"H1610*3","v":6},{"$f":"H1610","v":2},{"$f":"H1610","v":2}]
[1604,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE 4 BEARING6 TPRD RLR CUP 9  F60187-W100366 (896)",2,"Hra",1954.909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1605,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE 5 BEARING TPRD CONE 5.3751  F60188-W100368",2,"Hra",1954.909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1608,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE COLLARIN DE CELDA WENCO 1500P3",6,"Hra",1954.909090909091,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[1609,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE FALSO PISO CELDA WENCO 1500P3",10,"Hra",1954.909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,168,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[1611,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE TAPON DE DARDO CELDA WEMCO 1500 P3",2,"Hra",244.36363636363637,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1612,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE TUBO DARDO CELDA WENCO 1500P3",2,"Hra",244.36363636363637,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1614,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA  SULLAIR TS-20 FILTRO PRENSA","CAMBIO DE 010-250034-122 ELEMENTO DE FILTRO SEPARADOR PRIMARIO (SULLAIR)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1615,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA  SULLAIR TS-20 FILTRO PRENSA","CAMBIO DE 010-250034-134 ELEMENTO DE FILTRO SEPARADOR SECUNDARIO (SULLAIR)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1618,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR LS12-50H/A/SUL","CAMBIO DE ELEMENTO DE FILTRO",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1619,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR LS12-50H/A/SUL","CAMBIO DE FILTRO DE AIRE",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1621,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR LS12-50H/A/SUL","CAMBIO DE FILTRO SEPARADOR PRIMARIO",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1622,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR LS12-50H/A/SUL","CAMBIO DE FILTRO SEPARADOR SECUNDARIO",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1624,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR ST 1509","CAMBIO DE FILTRO DE AIRE",4,"Hra",228,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1625,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR ST 1509","CAMBIO DE SEPARADOR DE KIT",2,"Hra",228,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1628,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE ELEMENTO DE FILTRO DE AIRE PRIMARIO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1629,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE ELEMENTO DE FILTRO SEPARADOR PRIMARIO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1631,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE ELEMENTO DE FILTRO SEPARADOR SECUNDARIO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1632,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE FILTRO ACEITE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1634,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE FILTRO DE AIRE PRIMARIO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1635,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE FILTRO DE CONTROL DE AIRE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1637,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE FILTRO SEPARADOR DE AGUA",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1638,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE SEPARADOR DE AGUA AUTOMATICOSMC",2,"Hra",288,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1641,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Compresora Sullair TS-20(02)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1642,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE  FILTRO DE AIRE SECUNDARIO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1644,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE 010250020353 KIT CONTROL SULLICON",2,"Hra",288,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1645,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE 010250025526 ELEMENTO FILTRO ACEITE S12,16,20,TS20.600.750",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1647,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE 010-250034-134 ELEMENTO DE FILTRO SEPARADOR SECUNDARIO (SULLAIR)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1648,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE 010608311001 KIT DE REPARACION DE CILINDRO TS-20",2,"Hra",288,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1651,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE 130-6623-FLUIDRAIN  DREN AUTOMATICO ｽ 115V 232 PSIG",2,"Hra",288,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1652,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE 250025526 FILTRO ACEITE (SULLAIR TS20)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1654,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE ELEMENTO DE FILTRO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1655,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE ELEMENTO DE FILTRO DE AIRE PRIMARIO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1657,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE FILTRO CONTROL ",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1658,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE FILTRO DE AIRE PRIMARIO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1661,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE P116446 FILTRO DE AIRE (COMPRESORA TS 20)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1662,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE SEPARADOR DE AGUA AUTOMATICOSMC",2,"Hra",288,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[1664,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRSA TS20 F.PRENSA","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1665,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRSA TS20 F.PRENSA","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1667,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Espesador Cobre de 20'","MANTENIMIENTO ESPESADOR",48,"Hra",523.6363636363636,"DIA","C",null,48,48,48,{"$nulls":3},48,48,48,{"$nulls":4},48,48,24,{"$nulls":3},48,{"$f":"H1675","v":48},{"$nulls":4},24,48,48,{"$nulls":4},48,48,48,{"$nulls":3},48,48,144,{"$nulls":4},144,48,48]
[1668,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Espesador de Zinc Sanky de 70'","MANTENIMIENTO ESPESADOR",48,"Hra",130.9090909090909,"DIA","C",null,48,168,48,{"$nulls":3},48,48,48,{"$nulls":4},48,48,24,{"$nulls":3},48,{"$f":"H1676","v":48},{"$nulls":4},24,48,48,{"$nulls":4},48,48,48,{"$nulls":3},48,48,144,{"$nulls":4},144,48,48]
[1670,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Espesador de Zinc Sanky de 70'","MANTENIMIENTO ESPESADOR",48,"Hra",523.6363636363636,"DIA","C",null,48,168,48,{"$nulls":3},48,48,48,{"$nulls":4},48,48,24,{"$nulls":3},48,{"$f":"H1678","v":48},{"$nulls":4},24,48,48,{"$nulls":4},48,48,48,{"$nulls":3},48,48,144,{"$nulls":4},144,48,48]
[1671,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE 044A PLACA LENZER MEMBRANA",5,"Hra",1466.1818181818182,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,{"$f":"H1679","v":5},{"$nulls":3},5,{"$f":"H1679","v":5},{"$nulls":4},{"$f":"H1679","v":5},5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1674,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE CID-A18-026 ROCEADOR DE AGUA (304-L)",1.5,"Hra",183.27272727272728,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1675,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE CID-A18-094  CILINDRO HIDRAULICO DE COMPUERTA (OTA-1801010F-001)",5.5,"Hra",1466.1818181818182,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":4},5.5,5.5,5.5,{"$nulls":3},5.5,5.5,16.5,{"$nulls":4},16.5,5.5,5.5]
[1677,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE FILTRO  DE ACEITE RE-090G10B/2 299309",4,"Hra",183.27272727272728,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1678,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE FILTRO DE ACEITE  HDA FTS 110",4,"Hra",183.27272727272728,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1680,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE LONA PARA PLACA MEMBRANA (80 MM CUELLO)",5,"Hra",91.63636363636364,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1681,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE LONA PARA PLACA RIGIDA (55 MM CUELLO)",5,"Hra",91.63636363636364,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1684,{"$f":"CONCATENATE(C1692,D1692)","v":"OPEXMFZ"},"OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE OTA1801010B-001 CID A18-070 CHUMACERA DE PARED",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1685,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE PUMP PFS 1006  RIVETT.",6.5,"Hra",366.54545454545456,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,19.5,{"$nulls":4},19.5,6.5,6.5]
[1687,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE VALVULA DIRECCIONAL 4/2 NGGRRBOBINA 24 VAC NP 28",1.5,"Hra",1466.1818181818182,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1688,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE VALVULA DIRECCIONAL 4/3 NG6 NP 23",1.5,"Hra",1466.1818181818182,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[1690,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Motor Ventilador TS-20  Prensa","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1691,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Motor Ventilador TS-20  Prensa","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1694,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1695,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1697,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1698,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1700,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE BOCINA",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1701,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE COVER PLATE",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1704,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1705,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1707,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE FRAME PLATE",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1708,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE IMPULSOR",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1710,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE ORING",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1711,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1713,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1714,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1717,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE BOCINA",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1718,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE COVER PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1720,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE EJECTOR",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1721,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE END COVER (TAPAS)",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1723,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE EXPELLER",4,"Hra",144,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1724,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE FRAME PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1727,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE ORING",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1728,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A1737+1","v":1730},"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE RODAMIENTO",4,"Hra",576,"DIA","C",null,{"$f":"+H1738","v":4},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$nulls":3},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$nulls":4},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$nulls":3},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$nulls":4},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$nulls":4},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$nulls":3},{"$f":"H1738","v":4},{"$f":"H1738","v":4},{"$f":"H1738*3","v":12},{"$nulls":4},{"$f":"H1738*3","v":12},{"$f":"H1738","v":4},{"$f":"H1738","v":4}]
[1731,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1733,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1734,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE BOCINA",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1737,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE EJECTOR",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1738,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1740,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE EXPELLER",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1741,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE FRAME PLATE",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1743,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE LABERINTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1744,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE ORING",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1746,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE RETEN",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1747,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE RODAMIENTO",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1750,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 VOGT #2 FILTRO PRENSA (BOMBA BULLS)","CAMBIO DE RETEN",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1751,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 VOGT #2 FILTRO PRENSA (BOMBA BULLS)","CAMBIO DE RODAMIENTO",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1753,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1754,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2688,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1756,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",4,"Hra",84,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1757,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1760,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1761,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1763,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",84,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1764,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1766,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1767,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",84,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1770,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1771,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",3072,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1773,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",4,"Hra",24,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1774,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",977.4545454545455,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1776,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1777,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1780,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",24,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1781,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1783,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1784,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",24,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1786,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",71.42857142857143,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1787,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",71.42857142857143,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1789,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1790,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1793,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",4,"Hra",24,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A1801+1","v":1794},"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",977.4545454545455,"DIA","C",null,{"$f":"+H1802","v":4},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$nulls":3},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$nulls":4},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$nulls":3},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$nulls":4},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$nulls":4},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$nulls":3},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$f":"H1802*3","v":12},{"$nulls":4},{"$f":"H1802*3","v":12},{"$f":"H1802","v":4},{"$f":"H1802","v":4}]
[1796,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1797,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1799,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",24,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1800,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",24,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1803,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1804,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",24,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1806,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1807,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1809,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA OVER FLOW\nESPESADOR DE Pb","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1810,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA OVER FLOW\nESPESADOR DE Pb","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1813,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA VOGT #1, ALIMENTACION AL FILTRO PRENSA (DEBAJO DE FILTRO CC-30)","CAMBIO DE LABERINTO",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1814,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA VOGT #1, ALIMENTACION AL FILTRO PRENSA (DEBAJO DE FILTRO CC-30)","CAMBIO DE RETEN",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1816,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA DE FILTRADO ( FILTRO CERAMICO CC-30 DE Zn)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1817,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA DE FILTRADO ( FILTRO CERAMICO CC-30 DE Zn)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1819,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA DE FILTRADO (FILTRO CERAMICO CC6  DE  Pb)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1820,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA DE FILTRADO (FILTRO CERAMICO CC6  DE  Pb)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1822,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA DE H2O( FILTRO CERAMICO CC6  DE  Pb)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1823,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA DE H2O( FILTRO CERAMICO CC6  DE  Pb)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1826,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1827,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1829,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1830,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1832,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1833,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1836,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1837,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1839,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1840,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1842,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1843,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1846,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1847,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1849,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1850,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1852,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1853,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1855,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1856,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1859,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1860,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1862,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1863,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1865,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1866,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1869,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1870,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1872,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1873,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1875,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1876,{"$f":"CONCATENATE(C1884,D1884)","v":"OPEXMEF"},"OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1879,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1880,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1882,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1883,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1885,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1886,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1889,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1890,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1892,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1893,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1895,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1896,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1898,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",105,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1899,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE DISCHARGE PIPE",4,"Hra",1680,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1902,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1903,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1905,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1906,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1908,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1909,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1912,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1913,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1915,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",105,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1916,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE DISCHARGE PIPE",4,"Hra",1680,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1918,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1919,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A1929+1","v":1922},"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,{"$f":"+H1930","v":4},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$nulls":3},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$nulls":4},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$nulls":3},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$nulls":4},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$nulls":4},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$nulls":3},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$f":"H1930*3","v":12},{"$nulls":4},{"$f":"H1930*3","v":12},{"$f":"H1930","v":4},{"$f":"H1930","v":4}]
[1923,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1925,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1926,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1928,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Bomba Vertical #1 courier concentrado de plomo","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1929,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Bomba Vertical #1 courier concentrado de plomo","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1931,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1932,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1935,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1936,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1938,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1939,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1941,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1942,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1945,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1946,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1948,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE CANASTILLA INFERIOR 3.1/2 EN CAUCHO",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1949,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1951,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE COVER PLATE (TAPA 3.1/2\" GALIGHER EN CAUCHO)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1952,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE IMPULSOR VERTICAL GALIGHER 3.1/2\" (11-120)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1955,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE RETEN INFERIOR CR-39934",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1956,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE RETEN SUPERIOR CR-31189",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1958,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE RODAMIENTO CIERRE 22313 E",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1959,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1961,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE TUBO DE DESCARGA (90-240)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1962,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1965,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Bomba vertical costado celda columna Pb (frente al Conc. De Cu) )","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[1966,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",70,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1968,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE 1309 RODAMIENTO",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1969,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1971,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",70,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1972,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1974,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",70,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1975,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1978,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1979,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1981,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1982,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1984,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1985,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1988,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1989,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1991,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1992,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1994,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1995,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1998,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[1999,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2001,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2002,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE COVER BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2004,{"$f":"CONCATENATE(C2012,D2012)","v":"OPEXMEF"},"OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2005,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE IMPULSOR BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2007,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2008,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2011,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2012,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2014,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2015,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2017,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE DISCHARGE PIPE",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2018,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2021,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2022,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",105,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2024,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2025,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2027,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2028,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2031,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2032,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2034,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE DISCHARGE PIPE",4,"Hra",2240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2035,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE IMPULSOR RUBBER (BOMBA VERTICAL 2.5)",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2037,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2038,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2041,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2042,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",896,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2044,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2045,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2047,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2048,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE CANASTILLA SUPERIOR 3.1/2\" EN CAUCHO",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A2057+1","v":2050},"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE IMPULSOR VERTICAL GALIGHER 3.1/2\" (11-120)",4,"Hra",210,"DIA","C",null,{"$f":"+H2058","v":4},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$nulls":3},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$nulls":4},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$nulls":3},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$nulls":4},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$nulls":4},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$nulls":3},{"$f":"H2058","v":4},{"$f":"H2058","v":4},{"$f":"H2058*3","v":12},{"$nulls":4},{"$f":"H2058*3","v":12},{"$f":"H2058","v":4},{"$f":"H2058","v":4}]
[2051,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE MANGUITO H-322",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2054,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE RETEN SUPERIOR CR-31189",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2055,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE RODAMIENTO 22222EK",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2057,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE TUBO DE DESCARGA (90-240)",4,"Hra",1680,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2058,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 DEBAJO DE LA CELDA WEMCO DE CU","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2060,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 DEBAJO DE LA CELDA WEMCO DE CU","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2061,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 DEBAJO DE LA CELDA WEMCO DE CU","CAMBIO DE CANASTILLA SUPERIOR 3.1/2\" EN CAUCHO",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2064,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 DEBAJO DE LA CELDA WEMCO DE CU","CAMBIO DE MANGUITO H-322",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2065,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 DEBAJO DE LA CELDA WEMCO DE CU","CAMBIO DE PUMP CASING (CAJA VERTICAL 3.1/2\" EN CAUCHO)",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2067,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 DEBAJO DE LA CELDA WEMCO DE CU","CAMBIO DE RETEN SUPERIOR CR-31189",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2068,{"$f":"CONCATENATE(C2076,D2076)","v":"OPEXMEF"},"OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 DEBAJO DE LA CELDA WEMCO DE CU","CAMBIO DE RODAMIENTO 22222EK",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2070,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 DEBAJO DE LA CELDA WEMCO DE CU","CAMBIO DE TUBO DE DESCARGA (90-240)",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2071,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2074,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE DISCHARGE PIPE",4,"Hra",3360,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2075,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE IMPULSOR RUBBER (BOMBA VERTICAL 2.5)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2077,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2078,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2080,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2081,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2083,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2084,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2087,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2088,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE DISCHARGE PIPE",4,"Hra",3360,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2090,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2091,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2093,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2094,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2097,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2098,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2100,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2101,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2103,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE IMPULSOR RUBBER (BOMBA VERTICAL 2.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2104,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2107,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2108,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2110,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",806.4,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2111,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",806.4,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2113,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",350,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A2121+1","v":2114},"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",350,"DIA","C",null,{"$f":"+H2122","v":4},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$nulls":3},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$nulls":4},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$nulls":3},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$nulls":4},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$nulls":4},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$nulls":3},{"$f":"H2122","v":4},{"$f":"H2122","v":4},{"$f":"H2122*3","v":12},{"$nulls":4},{"$f":"H2122*3","v":12},{"$f":"H2122","v":4},{"$f":"H2122","v":4}]
[2117,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE IMPULSOR RUBBER (BOMBA VERTICAL 2.5)",4,"Hra",175,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2118,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",700,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2120,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",700,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2121,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",175,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2123,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",350,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2124,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2126,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",700,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2127,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2130,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","DISCO TAMBOR ( FILTRO CERAMICO CC-30 DE Zn)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",320,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2131,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","DISCO TAMBOR ( FILTRO CERAMICO CC-30 DE Zn)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",320,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2133,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","DISCO TAMBOR (FILTRO CERAMICO CC-06-02)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",320,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2134,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","DISCO TAMBOR (FILTRO CERAMICO CC-06-02)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",320,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2136,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE 1213KTVC3   BALL BEARING NTN",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2137,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE BALL BEARING NTN - 1209K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2140,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE CHAIN WHELL RS 80 CNT 17 X 50 MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2141,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE MANGUITO D/MONTAJE H-309",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2143,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE PILLOW BLOCK BEARING FYH-4KP-213+HS-313-",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2144,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[2146,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE RODILLOS DE RETORNO RSD 600-24 MCC",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2147,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE ROLLER CHAIN RS-80",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2150,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC30 de Zn","CAMBIO DE 6413330 O RING 92.0 X 4.0",1.5,"Hra",84,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[2151,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC30 de Zn","CAMBIO DE 6752203  PO-31-2530-2200 FLEXISEAL",1.5,"Hra",84,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[2153,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC30 de Zn","CAMBIO DE AS 220-240-21-16 SEAL RING FOR DISTRIBUTION VALVE",1.5,"Hra",84,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[2154,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC30 de Zn","CAMBIO DE CHUMACERA P214 (SYJ514)",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2156,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC30 de Zn","CAMBIO DE O-RIN G SET FOR DISTRIBUTION VALVE",3,"Hra",84,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2157,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC30 de Zn","CAMBIO DE SPARE HOSE FOR 80",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2159,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC6 de Pb-02","CAMBIO DE 105002404 WEAR PLATE",2.5,"Hra",84,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2160,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC6 de Pb-02","CAMBIO DE CENTRIFUGAL PUMP N25-160 ETACHROM",6.5,"Hra",336,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":4},6.5,6.5,6.5,{"$nulls":3},6.5,6.5,19.5,{"$nulls":4},19.5,6.5,6.5]
[2163,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC6 de Pb-02","CAMBIO DE VACUUM PUMP PARA FILTRO CERAMICO CC-6",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,96,{"$nulls":4},4,4,4,{"$nulls":3},4,96,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2164,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC6 de Pb-03","CAMBIO DE 105002404 WEAR PLATE",2.5,"Hra",84,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2166,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC6 de Pb-03","CAMBIO DE HOSE PINCH VALVE DN 50 DIN PN 10",2.5,"Hra",336,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2167,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC6 de Pb-03","CAMBIO DE LIP SEAL (1513001092)",1.5,"Hra",84,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[2169,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","motor de retorno de Couier #2","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2170,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","motor de retorno de Couier #2","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2173,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","TALLER MECANICO PLANTA","ENGRASE DE EQUIPOS",1,"Hra",30,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2174,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Agitador 04 de Tanque Mars 1","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",333.3333333333333,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2176,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Agitador 04 de Tanque Mars 1","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",333.3333333333333,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2177,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Agitador 05 de Tanque Mars 2","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",333.3333333333333,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2179,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Agitador 05 de Tanque Mars 2","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",333.3333333333333,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2180,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Agitador de tanque Nº4  MARS","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",333.3333333333333,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2183,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","B.V.COCHA DE P.A.A","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2184,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","B.V.COCHA DE P.A.A","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2186,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA #  2 EF 05 MOD SIHI MOD 125-40","CAMBIO DE ANILLO DESGASTE LADO CARCASA",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2187,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA #  2 EF 05 MOD SIHI MOD 125-40","CAMBIO DE ANILLO DESGASTE LADO SUCCION",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2189,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA #  2 EF 05 MOD SIHI MOD 125-40","CAMBIO DE CARCASA PARA BOMBA",4,"Hra",1536,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2190,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA #  2 EF 05 MOD SIHI MOD 125-40","CAMBIO DE EJE",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2193,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA #  2 EF 05 MOD SIHI MOD 125-40","CAMBIO DE RODAMIENTO 63092ZRC3",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2194,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA #  2 EF 05 MOD SIHI MOD 125-40","CAMBIO DE TAPA DE CARCASA",4,"Hra",1536,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2196,{"$f":"CONCATENATE(C2204,D2204)","v":"OPEXMRL"},"OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA #  2 EF 05 MOD SIHI MOD 125-40","CAMBIO DE TAPA RODAMIENTOS",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2197,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA # 1 EF 05 MOD SIHI MOD 125-40","CAMBIO DE ANILLO DESGASTE LADO CARCASA",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2199,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA # 1 EF 05 MOD SIHI MOD 125-40","CAMBIO DE CAMISA DE EJE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2200,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA # 1 EF 05 MOD SIHI MOD 125-40","CAMBIO DE CARCASA PARA BOMBA",4,"Hra",1536,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2202,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA # 1 EF 05 MOD SIHI MOD 125-40","CAMBIO DE IMPULSOR",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2203,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA # 1 EF 05 MOD SIHI MOD 125-40","CAMBIO DE RODAMIENTO 5309ZZ  2RS  ",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2206,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA # 1 EF 05 MOD SIHI MOD 125-40","CAMBIO DE TAPA DE SOPORTE",4,"Hra",1536,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2207,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA # 1 EF 05 MOD SIHI MOD 125-40","CAMBIO DE TAPA RODAMIENTOS",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2209,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba de Agua Hidrostal 01 de Bombas mars","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2210,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba de Agua Hidrostal 01 de Bombas mars","ENGRASE DE EQUIPOS",5,"Hra",31.25,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2212,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba de Agua Hidrostal 02 de Bombas mars","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2213,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba de Agua Hidrostal 02 de Bombas mars","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2216,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba de Agua Hidrostal Rio Torres Nº1","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2217,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba de Agua Hidrostal Rio Torres Nº1","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2219,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de asiento de valvula - 500 HRS",1,"Hra",166.66666666666666,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2220,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de caja de valvula - 4000 HRS",3,"Hra",1333.3333333333333,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2222,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de cubierta de caja de valvula - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2223,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de cuerpo de valvula - 500 HRS",2,"Hra",166.66666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2226,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de espaciadores de bronce - 8000 HRS",1,"Hra",1333.3333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2227,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de guia de valvula superior - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2229,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de looking plate - 8000 HRS",0.5,"Hra",1333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2230,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de Nut for piston rod - 8000 HRS",0.5,"Hra",1333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2232,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de O-ring de piston - 500 HRS",2,"Hra",83.33333333333333,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2233,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de Packing presser - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2235,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de pin cross - 8000 HRS",1,"Hra",1333.3333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2236,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de piston A - 2000 HRS",0.5,"Hra",333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2239,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de resorte - 500 HRS",2,"Hra",83.33333333333333,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2240,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de rodamientos de aguja - 8000 HRS",1,"Hra",1142.857142857143,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[{"$f":"+A2249+1","v":2242},"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de tubería de descarga - 4000 HRS",3,"Hra",666.6666666666666,"DIA","C",null,{"$f":"+H2250","v":3},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$nulls":3},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$nulls":4},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$nulls":3},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$nulls":4},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$nulls":4},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$nulls":3},{"$f":"H2250","v":3},{"$f":"H2250","v":3},{"$f":"H2250*3","v":9},{"$nulls":4},{"$f":"H2250*3","v":9},{"$f":"H2250","v":3},{"$f":"H2250","v":3}]
[2243,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de tubería Z - 4000 HRS",3,"Hra",666.6666666666666,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2245,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de valve rubber presser - 500 HRS",2,"Hra",83.33333333333333,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2246,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de valvula de purga de aire - 4000 HRS",1,"Hra",666.6666666666666,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2249,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de V-Packing de piston - 500 HRS",1,"Hra",166.66666666666666,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2250,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de asiento de valvula - 500 HRS",1,"Hra",166.66666666666666,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2252,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de cross head - 8000 HRS",4,"Hra",1333.3333333333333,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2253,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de cubierta de caja de valvula - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2255,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de Cylinder liner - 8000 HRS",1,"Hra",1333.3333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2256,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de espaciadores de acero  - 8000 HRS",3,"Hra",1333.3333333333333,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2259,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de Lanter ring - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2260,{"$f":"CONCATENATE(C2268,D2268)","v":"OPEXMRL"},"OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de looking plate - 8000 HRS",0.5,"Hra",1333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2262,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de nut for valve body - 500 HRS",2,"Hra",83.33333333333333,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2263,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de O-ring de piston - 500 HRS",2,"Hra",83.33333333333333,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2265,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de Packing receiver - 4000 HRS",0.5,"Hra",666.6666666666666,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2266,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de pin cross - 8000 HRS",1,"Hra",1333.3333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2268,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de piston B - 2000 HRS",0.5,"Hra",333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2269,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de Piston rod - 8000 HRS",0.5,"Hra",1333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2272,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de tapón de aceite - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2273,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de tubería de descarga - 4000 HRS",3,"Hra",666.6666666666666,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2275,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de valve rubber - 500 HRS",2,"Hra",83.33333333333333,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2276,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de valve rubber presser - 500 HRS",2,"Hra",83.33333333333333,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2278,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de valvula de suministro de aceite - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2279,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de V-Packing de gland - 500 HRS",1,"Hra",83.33333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2282,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de caja de valvula - 4000 HRS",3,"Hra",1333.3333333333333,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2283,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de cross head - 8000 HRS",4,"Hra",1333.3333333333333,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2285,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de cuerpo de valvula - 500 HRS",2,"Hra",166.66666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2286,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de Cylinder liner - 8000 HRS",1,"Hra",1333.3333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2288,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de espaciadores de bronce - 8000 HRS",1,"Hra",1333.3333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2289,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de guia de valvula superior - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2292,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de Nut for piston rod - 8000 HRS",0.5,"Hra",1333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2293,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de nut for valve body - 500 HRS",2,"Hra",83.33333333333333,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2295,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de Packing presser - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2296,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de Packing receiver - 4000 HRS",0.5,"Hra",666.6666666666666,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2298,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de piston A - 2000 HRS",0.5,"Hra",333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2299,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de piston B - 2000 HRS",0.5,"Hra",333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":4},0.5,0.5,0.5,{"$nulls":3},0.5,0.5,1.5,{"$nulls":4},1.5,0.5,0.5]
[2302,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de rodamientos de aguja - 8000 HRS",1,"Hra",1142.857142857143,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2303,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de tapón de aceite - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2305,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de tubería Z - 4000 HRS",3,"Hra",666.6666666666666,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[{"$f":"+A2313+1","v":2306},"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de valve rubber - 500 HRS",2,"Hra",83.33333333333333,"DIA","C",null,{"$f":"+H2314","v":2},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$nulls":3},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$nulls":4},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$nulls":3},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$nulls":4},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$nulls":4},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$nulls":3},{"$f":"H2314","v":2},{"$f":"H2314","v":2},{"$f":"H2314*3","v":6},{"$nulls":4},{"$f":"H2314*3","v":6},{"$f":"H2314","v":2},{"$f":"H2314","v":2}]
[2308,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de valvula de purga de aire - 4000 HRS",1,"Hra",666.6666666666666,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2309,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de valvula de suministro de aceite - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2311,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de V-Packing de piston - 500 HRS",1,"Hra",166.66666666666666,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2312,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 016136007 O-RING",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2315,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 041361009  ARANDELA",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2316,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 043155006  PERNO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2318,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 043595006  ANILLO",5,"Hra",192,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2319,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 060526003 O-RING",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2321,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 235582005 O-RING",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2322,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 249344006 O-RING",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2325,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 262287001  PERNO",5,"Hra",192,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2326,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 263272002 SELLOS DE VﾁSTAGO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2328,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 272318009 ELEMENTO FILTRO (VENTILACION)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2329,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 272581001  ANILLO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2331,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 279990006  FILTRO FINISIMO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2332,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 282540003 O-RING",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2335,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 403867 SELLOS DE ANILLO DESLIZANTE",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2336,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 416341 FILTRO DE ASPIRACION",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2338,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 428533 O-RING (94.85 X3.53)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2339,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 43434002 O-RING",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2341,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 441946 DETECTOR DE PISTﾓN",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2342,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 460270 FILTRO DE BAJA PRESION",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2344,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 480511 ANILLO GUIA",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2345,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 527459 CONJUNTO SELLOS TANDEM",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2348,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 545005 ANILLOS GUIA",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2349,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 545006 ANILLOS GUIA",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2351,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 552262  ASIENTO DE VALVULA",5,"Hra",192,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2352,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 609553  PLATILLO DE VALVULA",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2354,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 620665  DISCO DE FIJACION",5,"Hra",192,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2355,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 62814001 ANILLO RASCADOR",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2358,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 66171009 ANILLO RANURADO / COLLARﾍN",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2359,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 67024003 ANILLO RECTANGULAR",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2361,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2362,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE COVER BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2364,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2365,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE IMPULSOR BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2368,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2369,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2371,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2372,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2374,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2375,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2378,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 3 B-MARS","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2379,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 3 B-MARS","CAMBIO DE COVER BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2381,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 3 B-MARS","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1344,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2382,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 3 B-MARS","CAMBIO DE IMPULSOR BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2384,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 3 B-MARS","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2385,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 3 B-MARS","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2387,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 3 B-MARS","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2388,{"$f":"CONCATENATE(C2396,D2396)","v":"OPEXMRL"},"OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 3 B-MARS","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",537.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2391,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2392,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE CANASTILLA INFERIOR 3.1/2 EN CAUCHO",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2394,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE CANASTILLA SUPERIOR 3.1/2\" EN CAUCHO",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2395,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE COVER PLATE (TAPA 3.1/2\" GALIGHER EN CAUCHO)",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2397,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE MANGUITO H-322",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2398,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE PUMP CASING (CAJA VERTICAL 3.1/2\" EN CAUCHO)",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2401,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE RODAMIENTO 22222EK",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2402,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE RODAMIENTO CIERRE 22313 E",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2404,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Espesador de Relave 70'","MANTENIMIENTO ESPESADOR",48,"Hra",65.45454545454545,"DIA","C",null,48,48,48,{"$nulls":3},48,48,48,{"$nulls":4},48,48,24,{"$nulls":3},48,48,{"$nulls":4},24,48,48,{"$nulls":4},48,48,48,{"$nulls":3},48,48,144,{"$nulls":4},144,48,48]
[2405,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Espesador de Relave 70'","MANTENIMIENTO ESPESADOR",48,"Hra",261.8181818181818,"DIA","C",null,48,48,48,{"$nulls":3},48,48,48,{"$nulls":4},48,48,24,{"$nulls":3},48,48,{"$nulls":4},24,48,48,{"$nulls":4},48,48,48,{"$nulls":3},48,48,144,{"$nulls":4},144,48,48]
[2407,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","TALLER ELECTRICO PLANTA","TRABAJOS DE TABLEROS",1,"Hra",120,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2408,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","TALLER MECANICO PLANTA","ENGRASE DE EQUIPOS",1,"Hra",120,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2411,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2412,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE BOCINA",5,"Hra",30,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2414,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE EJE",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2415,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE EJECTOR",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2417,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2418,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE EXPELLER",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2420,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE IMPULSOR",5,"Hra",30,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2421,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE LABERINTO",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2424,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE RETEN",5,"Hra",30,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2425,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE RODAMIENTO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2427,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2428,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2430,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","Extractor de Polvo de tolva de cal","MANTENIMIENTO EXTRACTOR",12,"Hra",240,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[2431,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","Extractor de Polvo de tolva de cal","MANTENIMIENTO EXTRACTOR",12,"Hra",480,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[{"$f":"+A2441+1","v":2434},"OPEXMPC","OPEXM","PC","PLANTA DE CAL","Faja Transportadora de Molino de Cal de 24\" x longitud de 11.5m","CAMBIO DE MANGUITO D/MONTAJE H-309",2,"Hra",672,"DIA","C",null,{"$f":"+H2442","v":2},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$nulls":3},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$nulls":4},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$nulls":3},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$nulls":4},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$nulls":4},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$nulls":3},{"$f":"H2442","v":2},{"$f":"H2442","v":2},{"$f":"H2442*3","v":6},{"$nulls":4},{"$f":"H2442*3","v":6},{"$f":"H2442","v":2},{"$f":"H2442","v":2}]
[2435,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","Faja Transportadora de Molino de Cal de 24\" x longitud de 11.5m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[2437,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","Faja Transportadora de Molino de Cal de 24\" x longitud de 11.5m","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2438,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","Faja Transportadora de Molino de Cal de 24\" x longitud de 11.5m","CAMBIO DE RODILLOS DE RETORNO RSD 600-24 MCC",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2440,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","Faja Transportadora de Molino de Cal de 24\" x longitud de 11.5m","CAMBIO DE SN513=SNK513 PILLOW BLOCK",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":4},4.5,4.5,4.5,{"$nulls":3},4.5,4.5,13.5,{"$nulls":4},13.5,4.5,4.5]
[2441,"OPEXMRC","OPEXM","RC","ZONA DE REACTIVOS","Tanque de Xantato Z-06","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2444,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2445,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2447,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE BOCINA",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2448,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE COVER PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2450,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE EJECTOR",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2451,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE END COVER (TAPAS)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2454,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE FRAME PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2455,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE IMPULSOR",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2457,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE ORING",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2458,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2460,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE RODAMIENTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2461,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2463,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2464,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2467,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE BOCINA",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2468,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE COVER PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2470,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE EJECTOR",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2471,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE END COVER (TAPAS)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2473,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE EXPELLER",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2474,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE FRAME PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2477,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE ORING",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2478,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2480,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE RODAMIENTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2481,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2483,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2484,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2487,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2488,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE IMPULSOR BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2490,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2491,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2493,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2494,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2496,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2497,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 3.5 POZA 4","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2500,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 3.5 POZA 4","CAMBIO DE CANASTILLA SUPERIOR 3.1/2\" EN CAUCHO",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2501,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 3.5 POZA 4","CAMBIO DE COVER PLATE (TAPA 3.1/2\" GALIGHER EN CAUCHO)",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2503,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 3.5 POZA 4","CAMBIO DE MANGUITO H-322",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2504,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 3.5 POZA 4","CAMBIO DE PUMP CASING (CAJA VERTICAL 3.1/2\" EN CAUCHO)",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2506,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 3.5 POZA 4","CAMBIO DE RETEN SUPERIOR CR-31189",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2507,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 3.5 POZA 4","CAMBIO DE RODAMIENTO 22222EK",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2510,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA DE FLOTACION DE COBRE","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2511,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº10","CAMBIO DE DIFUSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2513,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº10","CAMBIO DE IMPULSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2514,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº10","CAMBIO DE PISO DE CELDA",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2516,{"$f":"CONCATENATE(C2524,D2524)","v":"OPEXMFC"},"OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº10","CAMBIO DE RODAMIENTO",3,"Hra",733.0909090909091,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2517,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº10","CAMBIO DE TAPA INFERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2520,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº2","CAMBIO DE EJE",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2521,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº2","CAMBIO DE IMPULSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2523,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº2","CAMBIO DE PISO ENJEBADO",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2524,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº2","CAMBIO DE RODAMIENTO",3,"Hra",733.0909090909091,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2526,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº2","CAMBIO DE TAPA SUPERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2527,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº3","CAMBIO DE DIFUSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2530,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº3","CAMBIO DE PISO DE CELDA",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2531,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº3","CAMBIO DE PISO ENJEBADO",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2533,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº3","CAMBIO DE TAPA INFERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2534,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº3","CAMBIO DE TAPA SUPERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2536,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº4","CAMBIO DE EJE",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2537,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº4","CAMBIO DE IMPULSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2539,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº4","CAMBIO DE PISO ENJEBADO",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2540,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº4","CAMBIO DE RODAMIENTO",3,"Hra",733.0909090909091,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2543,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº5","CAMBIO DE DIFUSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2544,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº5","CAMBIO DE EJE",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2546,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº5","CAMBIO DE PISO DE CELDA",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2547,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº5","CAMBIO DE PISO ENJEBADO",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2549,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº5","CAMBIO DE TAPA INFERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2550,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº5","CAMBIO DE TAPA SUPERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2553,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº6","CAMBIO DE IMPULSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2554,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº6","CAMBIO DE PISO DE CELDA",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2556,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº6","CAMBIO DE RODAMIENTO",3,"Hra",733.0909090909091,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2557,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº6","CAMBIO DE TAPA INFERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2559,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº7","CAMBIO DE DIFUSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2560,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº7","CAMBIO DE EJE",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2563,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº7","CAMBIO DE PISO ENJEBADO",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2564,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº7","CAMBIO DE RODAMIENTO",3,"Hra",733.0909090909091,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2566,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº7","CAMBIO DE TAPA SUPERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2567,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº8","CAMBIO DE DIFUSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2569,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº8","CAMBIO DE IMPULSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2570,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº8","CAMBIO DE PISO DE CELDA",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2572,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº8","CAMBIO DE RODAMIENTO",3,"Hra",733.0909090909091,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2573,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº8","CAMBIO DE TAPA INFERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2576,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº9","CAMBIO DE EJE",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2577,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº9","CAMBIO DE IMPULSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2579,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº9","CAMBIO DE PISO ENJEBADO",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2580,{"$f":"CONCATENATE(C2588,D2588)","v":"OPEXMFC"},"OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº9","CAMBIO DE RODAMIENTO",3,"Hra",733.0909090909091,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2582,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº9","CAMBIO DE TAPA SUPERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2583,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu Banco Nº1","CAMBIO DE DIFUSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,{"$nulls":4},6,6,6,{"$nulls":4},6,6,6,{"$nulls":3},6,6,18,{"$nulls":4},18,6,6]
[2586,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu Banco Nº1","CAMBIO DE PISO DE CELDA",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2587,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu Banco Nº1","CAMBIO DE PISO ENJEBADO",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2589,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu Banco Nº1","CAMBIO DE TAPA INFERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2590,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu Banco Nº1","CAMBIO DE TAPA SUPERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":4},2.5,2.5,2.5,{"$nulls":3},2.5,2.5,7.5,{"$nulls":4},7.5,2.5,2.5]
[2592,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA denver SP18 de Cu banco N°1","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2593,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA denver SP18 de Cu banco N°1","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2596,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA denver SP18 de Cu banco N°2","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2597,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA denver SP18 de Cu banco N°4","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2599,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA denver SP18 de Cu banco N°4","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2600,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA denver SP18 de Cu banco N°5","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2602,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA denver SP18 de Cu banco N°5","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2603,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 01 Cobre","CAMBIO DE CORREAS DE TRANSMISION",2,"Hra",183.27272727272728,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2606,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 01 Cobre","CAMBIO DE RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2607,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 01 Cobre","CAMBIO DE RODAMIENTO Y PISTA",3,"Hra",183.27272727272728,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2609,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 02 Cobre","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2610,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 02 Cobre","CAMBIO DE FAJAS HERMANADAS",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2612,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 02 Cobre","CAMBIO DE RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2613,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 02 Cobre","CAMBIO DE RODAMIENTO Y PISTA",3,"Hra",183.27272727272728,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2615,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 03 Cobre","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2616,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 03 Cobre","CAMBIO DE FAJAS HERMANADAS",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2619,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 03 Cobre","CAMBIO DE RODAMIENTO Y PISTA",3,"Hra",183.27272727272728,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2620,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 04 Cobre","CAMBIO DE CORREAS DE TRANSMISION",2,"Hra",183.27272727272728,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2622,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 04 Cobre","CAMBIO DE FAJAS HERMANADAS",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2623,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 04 Cobre","CAMBIO DE RETEN",1,"Hra",183.27272727272728,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2625,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 04 Cobre","CAMBIO DE RODAMIENTO Y PISTA",3,"Hra",183.27272727272728,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[{"$f":"+A2633+1","v":2626},"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 05 Cobre","CAMBIO DE CORREAS DE TRANSMISION",2,"Hra",183.27272727272728,"DIA","C",null,{"$f":"+H2634","v":2},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$nulls":3},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$nulls":4},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$nulls":3},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$nulls":4},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$nulls":4},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$nulls":3},{"$f":"H2634","v":2},{"$f":"H2634","v":2},{"$f":"H2634*3","v":6},{"$nulls":4},{"$f":"H2634*3","v":6},{"$f":"H2634","v":2},{"$f":"H2634","v":2}]
[2629,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 05 Cobre","CAMBIO DE RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2630,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 05 Cobre","CAMBIO DE RODAMIENTO Y PISTA",3,"Hra",183.27272727272728,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2632,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 06 Cobre","CAMBIO DE FAJAS HERMANADAS",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2633,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 06 Cobre","CAMBIO DE RETEN",1,"Hra",183.27272727272728,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2635,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 06 Cobre","CAMBIO DE RODAMIENTO Y PISTA",3,"Hra",183.27272727272728,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2636,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 07 Cobre","CAMBIO DE CORREAS DE TRANSMISION",2,"Hra",183.27272727272728,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2639,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 07 Cobre","CAMBIO DE RETEN",1,"Hra",183.27272727272728,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2640,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 07 Cobre","CAMBIO DE RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2642,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 08 Cobre","CAMBIO DE CORREAS DE TRANSMISION",2,"Hra",183.27272727272728,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2643,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 08 Cobre","CAMBIO DE FAJAS HERMANADAS",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2645,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 08 Cobre","CAMBIO DE RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2646,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 08 Cobre","CAMBIO DE RODAMIENTO Y PISTA",3,"Hra",183.27272727272728,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2647,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu  Nº1","CAMBIO DE 1213KTVC3   BALL BEARING NTN",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2648,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu  Nº1","CAMBIO DE BALL BEARING NTN - 1209K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2649,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu  Nº1","CAMBIO DE CHAIN WHEEL RS-80-C-NT-76X50MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2650,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu  Nº1","CAMBIO DE CHAIN WHELL RS 80 CNT 17 X 50 MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2651,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu  Nº1","CAMBIO DE ROLLER CHAIN RS-80",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,{"$nulls":4},3,3,3,{"$nulls":4},3,3,3,{"$nulls":3},3,3,9,{"$nulls":4},9,3,3]
[2652,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu Nº2 de 19\" x longitud 14.8m","CAMBIO DE CONVEYOR BELTS 750MM X 3P X 3.2 X 1.6 X 30\"",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,{"$nulls":4},12,12,12,{"$nulls":4},12,12,12,{"$nulls":3},12,12,36,{"$nulls":4},36,12,12]
[2653,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu Nº2 de 19\" x longitud 14.8m","CAMBIO DE MANGUITO D/MONTAJE H-309",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2654,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu Nº2 de 19\" x longitud 14.8m","CAMBIO DE PILLOW BLOCK BEARING FYH-4KP-213+HS-313-",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2655,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu Nº3 de 19\" x longitud de 12m","CAMBIO DE PILLOW BLOCK BEARING FYH-4KP-213+HS-313-",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,{"$nulls":4},2,2,2,{"$nulls":4},2,2,2,{"$nulls":3},2,2,6,{"$nulls":4},6,2,2]
[2656,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu Nº3 de 19\" x longitud de 12m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,{"$nulls":4},8,8,8,{"$nulls":4},8,8,8,{"$nulls":3},8,8,24,{"$nulls":4},24,8,8]
[2657,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu Nº3 de 19\" x longitud de 12m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":4},1.5,1.5,1.5,{"$nulls":3},1.5,1.5,4.5,{"$nulls":4},4.5,1.5,1.5]
[2658,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","MOLINO DE CAL 4\" X 8\"","CAMBIO DE CASQUILLO DE BRONCE (ENTRADA Y SALIDA)",10,"Hra",1680,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,{"$nulls":4},10,10,10,{"$nulls":4},10,10,10,{"$nulls":3},10,10,30,{"$nulls":4},30,10,10]
[2659,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","MOLINO DE CAL 4\" X 8\"","CAMBIO DE CONTRA EJE CON PIÑON GEAR",24,"Hra",1680,"DIA","C",null,24,24,24,{"$nulls":3},24,24,24,{"$nulls":4},24,24,24,{"$nulls":3},24,24,{"$nulls":4},24,24,24,{"$nulls":4},24,24,24,{"$nulls":3},24,24,72,{"$nulls":4},72,24,24]
[2660,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","MOLINO DE CAL 4\" X 8\"","CAMBIO DE FORRO CABEZAL CARGA Y DESCARGA - GETS",16,"Hra",6720,"DIA","C",null,16,16,16,{"$nulls":3},16,16,16,{"$nulls":4},16,16,16,{"$nulls":3},16,16,{"$nulls":4},16,16,16,{"$nulls":4},16,16,16,{"$nulls":3},16,16,48,{"$nulls":4},48,16,16]
[2661,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","MOLINO DE CAL 4\" X 8\"","CAMBIO DE JUEGO DE FORRO METALICO PARTE CILINDRICA - GETS",16,"Hra",6720,"DIA","C",null,16,16,16,{"$nulls":3},16,16,16,{"$nulls":4},16,16,16,{"$nulls":3},16,16,{"$nulls":4},16,16,16,{"$nulls":4},16,16,16,{"$nulls":3},16,16,48,{"$nulls":4},48,16,16]
[2662,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","MOLINO DE CAL 4\" X 8\"","CAMBIO DE SPOUT",4,"Hra",6720,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2663,"OPEXMOT","OPEXM","OT","OTROS","TALLER ELECTRICO PLANTA","TRABAJOS DE TABLEROS",1,"Hra",30,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2664,"OPEXMOT","OPEXM","OT","OTROS","TALLER ELECTRICO PLANTA","TRABAJOS DE TABLEROS",1,"Hra",120,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2665,"OPEXMOT","OPEXM","OT","OTROS","TALLER MECANICO PLANTA","ENGRASE DE EQUIPOS",1,"Hra",30,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2666,"OPEXMOT","OPEXM","OT","OTROS","TALLER MECANICO PLANTA","ENGRASE DE EQUIPOS",1,"Hra",60,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2667,"OPEXMOT","OPEXM","OT","OTROS","TALLER MECANICO PLANTA","ENGRASE DE EQUIPOS",1,"Hra",120,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,{"$nulls":4},1,1,1,{"$nulls":4},1,1,1,{"$nulls":3},1,1,3,{"$nulls":4},3,1,1]
[2668,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador Clarificador # 01","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2669,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador Clarificador # 02","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2670,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador Clarificador # 03","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2671,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor 98TGK0418 N° 02","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2672,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor 98TGK0418 N° 02","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2673,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor 98TGK0418 N° 02","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2674,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor 98TGK0418 N° 03","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2675,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor 98TGK0418 N° 03","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2676,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor 98TGK0418 N° 03","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2677,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor N° 0","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2678,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor N° 0","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2679,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor N° 0","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2680,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor N° 04","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2681,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor N° 04","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2682,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor N° 04","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2683,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE ANILLO DE PISTON",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2684,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE BEARING  6535/6580(RODAMIENTO)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2685,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE BOCINA (SHAFT SLEEVE)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2686,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE COVER PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2687,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE DISTRIBUIDOR DE AGUA (E118 LANTERN RESTRICTOR)",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2688,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE E005XLM SHAFT (EJE)",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2689,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE E-025 END COVER SHIM SET (LAINA)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A2697+1","v":2690},"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE E08910 BEARING SEAL",4,"Hra",384,"DIA","C",null,{"$f":"+H2698","v":4},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$nulls":3},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$nulls":4},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$nulls":3},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$nulls":4},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$nulls":4},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$nulls":3},{"$f":"H2698","v":4},{"$f":"H2698","v":4},{"$f":"H2698*3","v":12},{"$nulls":4},{"$f":"H2698*3","v":12},{"$f":"H2698","v":4},{"$f":"H2698","v":4}]
[2691,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE E117 SHAFT SPACER (ESPACIADOR)",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2692,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE EXPELLER",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2693,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE FRAME PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2694,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE GLAND O PRENSA ESTOPA",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2695,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE IMPELLER O'RING",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2696,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE IMPULSOR DE METAL PARA BOMBA WARMAN (BOMBA LODOS 01)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2697,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE LABYRINTH (LABERINTO)",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2698,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE LABYRINTH LOCKNUT",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2699,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE RETENEDOR DE GRASA",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2700,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",142.85714285714286,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2701,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",142.85714285714286,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2702,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE STUFFING BOX",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2703,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE TROAT BUSH",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2704,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",142.85714285714286,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2705,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE ANILLO DE PISTON",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2706,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE BEARING  6535/6580(RODAMIENTO)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2707,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE BOCINA (SHAFT SLEEVE)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2708,{"$f":"CONCATENATE(C2716,D2716)","v":"OPEXMPA"},"OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE COVER PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2709,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE DISTRIBUIDOR DE AGUA (E118 LANTERN RESTRICTOR)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2710,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE E005XLM SHAFT (EJE)",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2711,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE E-025 END COVER SHIM SET (LAINA)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2712,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE E08910 BEARING SEAL",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2713,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE E117 SHAFT SPACER (ESPACIADOR)",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2714,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE EXPELLER",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2715,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE GLAND O PRENSA ESTOPA",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2716,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE IMPELLER O'RING",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2717,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE IMPULSOR (BOMBA WARMAN 6 X 4 EAH)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2718,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE LABYRINTH (LABERINTO)",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2719,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE LABYRINTH LOCKNUT",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2720,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE RETENEDOR DE GRASA",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2721,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE STUFFING BOX",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2722,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE TROAT BUSH",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2723,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","FRAME PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2724,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE ANILLO DE PISTON",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2725,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE BEARING  6535/6580(RODAMIENTO)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2726,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE BOCINA (SHAFT SLEEVE)",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2727,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE COVER PLATE",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2728,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE DISTRIBUIDOR DE AGUA (E118 LANTERN RESTRICTOR)",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2729,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE E005XLM SHAFT (EJE)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2730,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE E-025 END COVER SHIM SET (LAINA)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2731,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE E08910 BEARING SEAL",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2732,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE E117 SHAFT SPACER (ESPACIADOR)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2733,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE EXPELLER",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2734,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE FRAME PLATE LINER BOMBA ESPIASA 6 X 4 EAH (BOMBA DE LODOS 02)",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2735,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE GLAND O PRENSA ESTOPA",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2736,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE IMPELLER O'RING",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2737,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE IMPULSOR (BOMBA WARMAN 6 X 4 EAH)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2738,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE LABYRINTH (LABERINTO)",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2739,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE LABYRINTH LOCKNUT",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2740,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE RETENEDOR DE GRASA",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2741,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",142.85714285714286,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2742,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",142.85714285714286,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2743,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE STUFFING BOX",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2744,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE TROAT BUSH",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2745,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",142.85714285714286,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2746,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE ANILLO DE PISTON",4,"Hra",160,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2747,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE BEARING  6535/6580(RODAMIENTO)",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2748,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE BOCINA (SHAFT SLEEVE)",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2749,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE COVER PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2750,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE DISTRIBUIDOR DE AGUA (E118 LANTERN RESTRICTOR)",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2751,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE E005XLM SHAFT (EJE)",4,"Hra",640,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2752,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE E-025 END COVER SHIM SET (LAINA)",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2753,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE E08910 BEARING SEAL",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A2761+1","v":2754},"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE E117 SHAFT SPACER (ESPACIADOR)",4,"Hra",160,"DIA","C",null,{"$f":"+H2762","v":4},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$nulls":3},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$nulls":4},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$nulls":3},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$nulls":4},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$nulls":4},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$nulls":3},{"$f":"H2762","v":4},{"$f":"H2762","v":4},{"$f":"H2762*3","v":12},{"$nulls":4},{"$f":"H2762*3","v":12},{"$f":"H2762","v":4},{"$f":"H2762","v":4}]
[2755,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE EXPELLER",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2756,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE GLAND O PRENSA ESTOPA",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2757,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE IMPELLER O'RING",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2758,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE IMPULSOR (BOMBA WARMAN 6 X 4 EAH)",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2759,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE LABYRINTH (LABERINTO)",4,"Hra",160,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2760,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE LABYRINTH LOCKNUT",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2761,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE RETENEDOR DE GRASA",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2762,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",142.85714285714286,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2763,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",142.85714285714286,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2764,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE STUFFING BOX",4,"Hra",160,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2765,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE TROAT BUSH",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2766,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","FRAME PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2767,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",142.85714285714286,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2768,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2769,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2770,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2771,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE BOCINA",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2772,{"$f":"CONCATENATE(C2780,D2780)","v":"OPEXMPA"},"OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE COVER PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2773,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EJE",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2774,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EJECTOR",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2775,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2776,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2777,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EXPELLER",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2778,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2779,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE IMPULSOR",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2780,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE LABERINTO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2781,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE ORING",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2782,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2783,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE RETEN",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2784,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2785,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2786,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2787,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2788,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE BOCINA",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2789,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE COVER PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2790,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EJE",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2791,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EJECTOR",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2792,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2793,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2794,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EXPELLER",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2795,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2796,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE IMPULSOR",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2797,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE LABERINTO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2798,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE ORING",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2799,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2800,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE RETEN",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2801,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2802,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 01","CAMBIO DE ESTATOR DE CAUCHO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2803,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 01","CAMBIO DE ROTOR DE ACERO",4,"Hra",960,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2804,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 01","CAMBIO DE TEMPLADOR DE ESTATOR",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2805,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 02","CAMBIO DE ESTATOR DE CAUCHO",5,"Hra",120,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2806,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 02","CAMBIO DE ROTOR DE ACERO",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2807,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 02","CAMBIO DE TEMPLADOR DE ESTATOR",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2808,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 03","CAMBIO DE ESTATOR DE CAUCHO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2809,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 03","CAMBIO DE ROTOR DE ACERO",4,"Hra",960,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2810,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 03","CAMBIO DE TEMPLADOR DE ESTATOR",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2811,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Bomba vertical (bajando las escaleras hacia PTAA)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2812,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Bomba vertical (bajando las escaleras hacia PTAA)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2813,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Bomba vertical (bajando las escaleras hacia PTAA)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2814,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2815,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2816,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2817,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A2825+1","v":2818},"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,{"$f":"+H2826","v":4},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$nulls":3},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$nulls":4},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$nulls":3},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$nulls":4},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$nulls":4},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$nulls":3},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$f":"H2826*3","v":12},{"$nulls":4},{"$f":"H2826*3","v":12},{"$f":"H2826","v":4},{"$f":"H2826","v":4}]
[2819,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2820,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2821,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2822,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2823,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2824,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2825,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2826,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2827,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2828,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2829,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2830,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2831,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2832,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2833,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2834,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE DISCHARGE PIPE",4,"Hra",3360,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2835,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE IMPULSOR RUBBER (BOMBA VERTICAL 2.5)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2836,{"$f":"CONCATENATE(C2844,D2844)","v":"OPEXMPA"},"OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2837,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2838,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2839,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2840,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2841,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2842,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2843,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2844,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2845,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2846,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2847,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE 1309 RODAMIENTO",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2848,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2849,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2850,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2851,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2852,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2853,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2854,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2855,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2856,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2857,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2858,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2859,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE RODAMIENTO 1308",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2860,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2861,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2862,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2863,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2864,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE COVER BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2865,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE DISCHARGE PIPE",4,"Hra",1680,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2866,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1680,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2867,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE IMPULSOR BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2868,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2869,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2870,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2871,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2872,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2873,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2874,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2875,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2876,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2877,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2878,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2879,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE DISCHARGE PIPE",4,"Hra",3360,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2880,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE IMPULSOR RUBBER (BOMBA VERTICAL 2.5)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2881,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[{"$f":"+A2889+1","v":2882},"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,{"$f":"+H2890","v":4},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$nulls":3},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$nulls":4},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$nulls":3},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$nulls":4},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$nulls":4},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$nulls":3},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$f":"H2890*3","v":12},{"$nulls":4},{"$f":"H2890*3","v":12},{"$f":"H2890","v":4},{"$f":"H2890","v":4}]
[2883,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2884,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2885,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2886,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2887,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2888,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2889,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2890,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","SOPLADOR IR INGERSOLL RAND HILBON CENTRIFUGAL NEUTRALIZACIÓN","CAMBIO DE  FILTRO DE AIRE",4,"Hra",224,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]
[2891,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","SOPLADOR IR INGERSOLL RAND HILBON CENTRIFUGAL NEUTRALIZACIÓN","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2892,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","SOPLADOR IR INGERSOLL RAND HILBON CENTRIFUGAL NEUTRALIZACIÓN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2893,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","SOPLADOR IR INGERSOLL RAND HILBON CENTRIFUGAL NEUTRALIZACIÓN","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,{"$nulls":4},5,5,5,{"$nulls":4},5,5,5,{"$nulls":3},5,5,15,{"$nulls":4},15,5,5]
[2894,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","SOPLADOR SPENCER Nº2 CENTERFUGA BLOWER (PLANTA NEUTRALIZACION)","CAMBIO DE  FILTRO DE AIRE",4,"Hra",224,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,{"$nulls":4},4,4,4,{"$nulls":4},4,4,4,{"$nulls":3},4,4,12,{"$nulls":4},12,4,4]

{"sheet":"PROYECCION ACTIVIDADES PARADAS","index":9,"n_rows":2902,"n_cols":313,"rows_kept":1125,"cut":true,"merged":[[2,64,2,68],[2,69,2,73],[2,74,2,78],[2,79,2,83],[2,84,2,88],[2,89,2,93],[2,94,2,98],[2,99,2,103],[2,104,2,109],[2,110,2,114],[2,115,2,119],[2,120,2,124],[2,125,2,129],[2,130,2,134],[2,135,2,139],[2,140,2,144],[2,145,2,149],[2,150,2,154],[2,155,2,159],[2,160,2,164],[2,165,2,170],[2,171,2,175],[2,176,2,180],[2,181,2,185],[2,186,2,190],[2,191,2,195],[2,196,2,200],[2,201,2,205],[2,206,2,210],[2,211,2,215],[2,216,2,220],[2,221,2,225],[2,226,2,231],[2,232,2,236],[2,237,2,241],[2,242,2,246],[2,247,2,251],[2,252,2,256],[2,257,2,261],[2,262,2,266],[2,267,2,271],[2,272,2,276],[2,277,2,281],[2,282,2,286],[2,287,2,292],[2,293,2,297],[2,298,2,302],[2,303,2,307],[3,12,3,15],[3,16,3,19],[3,20,3,24],[3,25,3,28],[3,29,3,33],[3,38,3,41],[3,42,3,46],[3,47,3,50],[3,51,3,54],[3,55,3,59],[3,60,3,63],[5,12,5,15],[5,16,5,19],[5,20,5,24],[5,25,5,28],[5,29,5,33],[5,34,5,37],[5,38,5,41],[5,42,5,46],[5,47,5,50],[5,51,5,54],[5,55,5,59],[5,60,5,63]],"bounds":{"rows_first":500,"rows_last":125,"rows_between":500,"halvings":2}}
[{"$nulls":4},"ACTIVIDADES DE PARADAS TOTALES PLANTA CONCENTRADORAS x 52 SEMANAS - 2024"]
[{"$nulls":64},2015,{"$nulls":60},2016,{"$nulls":60},2017,{"$nulls":60},2018]
[{"$nulls":4},"BUDGET PLANNING AND MAINTENANCE CONCENTRATING PLANT",{"$nulls":7},2024,{"$nulls":51},"ENERO",{"$nulls":4},"FEBRERO",{"$nulls":4},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":4},"MAYO",{"$nulls":4},"JUNIO",{"$nulls":4},"JULIO",{"$nulls":4},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":5},"OCTUBRE",{"$nulls":4},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE",{"$nulls":4},"ENERO",{"$nulls":4},"FEBRERO",{"$nulls":4},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":4},"MAYO",{"$nulls":4},"JUNIO",{"$nulls":4},"JULIO",{"$nulls":4},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":5},"OCTUBRE",{"$nulls":4},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE",{"$nulls":4},"ENERO",{"$nulls":4},"FEBRERO",{"$nulls":4},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":4},"MAYO",{"$nulls":4},"JUNIO",{"$nulls":4},"JULIO",{"$nulls":4},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":5},"OCTUBRE",{"$nulls":4},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE",{"$nulls":4},"ENERO",{"$nulls":4},"FEBRERO",{"$nulls":4},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":4},"MAYO",{"$nulls":4},"JUNIO",{"$nulls":4},"JULIO",{"$nulls":4},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":5},"OCTUBRE",{"$nulls":4},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE"]
[{"$nulls":4},"HUANZALA",{"$nulls":7},"ENERO",{"$nulls":3},"FEBRERO",{"$nulls":3},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":3},"MAYO",{"$nulls":4},"JUNIO",{"$nulls":3},"JULIO",{"$nulls":3},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":3},"OCTUBRE",{"$nulls":3},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE",{"$nulls":3},1,2,3,4,5,5,6,7,8,9,9,10,11,12,13,14,15,16,17,18,18,19,20,21,22,22,23,24,25,26,27,28,29,30,31,31,32,33,34,35,35,36,37,38,39,40,40,41,42,43,44,44,45,46,47,48,48,49,50,51,52,1,2,3,4,5,5,6,7,8,9,9,10,11,12,13,14,15,16,17,18,18,19,20,21,22,22,23,24,25,26,27,28,29,30,31,31,32,33,34,35,35,36,37,38,39,40,40,41,42,43,44,44,45,46,47,48,48,49,50,51,52,1,2,3,4,5,5,6,7,8,9,9,10,11,12,13,14,15,16,17,18,18,19,20,21,22,22,23,24,25,26,27,28,29,30,31,31,32,33,34,35,35,36,37,38,39,40,40,41,42,43,44,44,45,46,47,48,48,49,50,51,52,1,2,3,4,5,5,6,7,8,9,9,10,11,12,13,14,15,16,17,18,18,19,20,21,22,22,23,24,25,26,27,28,29,30,31,31,32,33,34,35,35,36,37,38,39,40,40,41,42,43,44,44,45,46,47,48,48,49,50,51,52]
[{"$nulls":12},1,{"$f":"M5+1","v":2},{"$f":"N5+1","v":3},{"$f":"O5+1","v":4},5,6,7,8,9,10,11,{"$f":"W5+1","v":12},{"$f":"X5+1","v":13},14,15,16,{"$f":"AB5+1","v":17},{"$f":"AC5+1","v":18},19,20,21,22,23,24,{"$f":"AJ5+1","v":25},{"$f":"AK5+1","v":26},27,28,29,30,{"$f":"AP5+1","v":31},32,33,{"$f":"AS5+1","v":34},{"$f":"AT5+1","v":35},36,37,38,39,40,41,42,43,{"$f":"BC5+1","v":44},45,46,{"$f":"BF5+1","v":47},{"$f":"BG5+1","v":48},49,50,51,52]
["PLANTA BENEFICIO HUANZALA",{"$nulls":11},"01ENE24 - 28ENE24",{"$nulls":3},"29ENE24 - 25FEB24",{"$nulls":3},"26FEB24 - 31MAR24",{"$nulls":4},"01ABR24 - 28ABR24",{"$nulls":3},"29ABR24 - 26MAY24",{"$nulls":4},"27MAY24 - 30JUN24",{"$nulls":3},"01JUL24 - 28JUL23",{"$nulls":3},"29JUL24 - 25AGO24",{"$nulls":4},"26AGO24 - 29SET24",{"$nulls":3},"30SET24 - 27OCT24",{"$nulls":3},"28OCT24 - 24NOV24",{"$nulls":4},"24NOV24 - 29DIC24"]
["PARADA TOTAL",{"$nulls":6},"H PRD",null,"SEM",null,null,{"$f":"MAX(M9:M5000)","v":0},{"$f":"MAX(N9:N5000)","v":144},168,48,0,0,0,65.5,168,120,0,0,0,0,0,120,96,0,0,0,39.5,168,168,24,0,0,168,120,0,0,72,168,48,0,0,144,144,0,0,48,168,72,0,0,120,168,0,0,24,168,96,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"MAX(BZ9:BZ5000)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"MAX(EL9:EL5000)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"MAX(GX9:GX5000)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"MAX(JJ9:JJ5000)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
["ITEM","CLASE1","CLASE","AREA1","AREA","EQUIPO","DESCRIPCION DE LA ACTIVIDAD","TIEMPO","UNID.","FREC.","UNID.","TIPO",{"$f":"+M5","v":1},{"$f":"+N5","v":2},3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"E",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",{"$nulls":3},"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"E",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",{"$nulls":3},"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"E",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",{"$nulls":3},"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"E",null,null,"A",null,"A",null,null,"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A",{"$nulls":3},"A",null,"A",null,null,"A",null,"C",null,null,"A",null,"A"]
[1,{"$f":"CONCATENATE(C9,D9)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion Chancadora secundaria sanvick","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","H",null,{"$f":"+H9","v":5},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$nulls":3},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$nulls":5},{"$f":"H9","v":5},5,{"$nulls":3},{"$f":"H9","v":5},{"$f":"H9","v":5},{"$f":"H9","v":5},5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[{"$f":"+A9+1","v":2},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion Chancadora secundaria sanvick","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","C",null,{"$f":"+H10","v":5},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$nulls":3},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$nulls":5},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$nulls":3},{"$f":"H10","v":5},{"$f":"H10","v":5},{"$f":"H10","v":5},5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[3,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion Chancadora secundaria sanvick","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[4,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion chancadora Terciario sanvick","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[5,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion chancadora Terciario sanvick","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[6,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","bomba de lubricacion chancadora Terciario sanvick","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[7,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[8,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[9,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE COVER BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[10,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE DISCHARGE PIPE",4,"Hra",1344,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[11,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1344,"DIA","F",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[12,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE IMPULSOR BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[13,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",672,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[14,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",672,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[15,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[16,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[17,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",336,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[18,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",336,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[19,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[20,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA DE CHANCADO PRIMARIO","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[21,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CADENA ALIMENTADORA ( APRON FEEDER) QA1548","MANTTO DE CADENA APRON FEEDER",5,"Hra",1620,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[22,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CADENA ALIMENTADORA ( APRON FEEDER) QA1548","MANTTO DE CADENA APRON FEEDER",5,"Hra",2046.3125,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[23,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CADENA ALIMENTADORA ( APRON FEEDER) QA1548","MANTTO DE CADENA APRON FEEDER",5,"Hra",5400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[24,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Cedazo # 01 - Vibratorio de alta frecuencia YOKAYAMI","CAMBIO DE MALLA",6,"Hra",130.9090909090909,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[25,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Cedazo # 02 - Vibratorio Simplicity 7x14","CAMBIO DE MALLA",6,"Hra",65.45454545454545,"DIA","E",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[26,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Cedazo # 02 - Vibratorio Simplicity 7x14","CAMBIO DE MALLA",6,"Hra",130.9090909090909,"DIA","E",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[27,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Cedazo # 02 - Vibratorio Simplicity 7x14","CAMBIO DE MALLA",6,"Hra",261.8181818181818,"DIA","E",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[28,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Cedazo # 02 - Vibratorio Simplicity 7x14","CAMBIO DE MALLA",6,"Hra",523.6363636363636,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[29,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 1151 FORRO LATERAL SUPER. DERE./IZQUI. (JGO X 02 PZAS)",4.5,"Hra",1282.5,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[30,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 1161 FORRO LATERAL INFER. DERE./IZQUI. (JGO X 02 PZAS)",4.5,"Hra",1282.5,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[31,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 1191 FIXED JAW PLATE (M-1796-01)",2.5,"Hra",641.25,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,48,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[32,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2059-1 SQUARE HEAD BOLT M48X650X130MM",2.5,"Hra",1282.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[33,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2059-2 SQUARE BOLTS M-48X700X130",2.5,"Hra",641.25,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[34,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2059-3 SQUARE LOWER BOLT M48 X 940 X 130  CON DOBLE TUERCA",2.5,"Hra",641.25,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[35,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2059-3 SQUARE LOWER BOLT M48X940X130MM",2.5,"Hra",641.25,"DIA","D",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[36,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2061 JAW PLATE STOPPER",6.5,"Hra",2565,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":5},6.5,6.5,{"$nulls":3},6.5,6.5,6.5,6.5,null,null,6.5,6.5,null,null,6.5,6.5,6.5,null,null,6.5,19.5,null,null,19.5,6.5,6.5,null,null,19.5,6.5,null,null,6.5,6.5,6.5]
[37,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 2081 MOVABLE JAW PLATE (M-1796-02)",2.5,"Hra",641.25,"DIA","F",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,48,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[38,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 3029 ROLLERBEARING SKF22356C3(FRAME)",12,"Hra",20520,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[39,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 3061 LABYRINTH COLLAR",18,"Hra",20520,"DIA","D",null,18,18,18,{"$nulls":3},18,18,18,{"$nulls":5},18,18,{"$nulls":3},18,18,18,18,null,null,18,18,null,null,18,18,18,null,null,18,54,null,null,48,18,18,null,null,54,18,null,null,18,18,18]
[40,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 3161 LABYRINTH COLLAR INNER SIDE",18,"Hra",20520,"DIA","D",null,18,18,18,{"$nulls":3},18,18,18,{"$nulls":5},18,18,{"$nulls":3},18,18,18,18,null,null,18,18,null,null,18,18,18,null,null,18,54,null,null,48,18,18,null,null,54,18,null,null,18,18,18]
[41,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 4021 TOGGLE HEAD",12,"Hra",1282.5,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[42,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 4021-2 TOGGLE SEAT",12,"Hra",1282.5,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[43,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 4241 TENSION ROD. M-48X1040",2.5,"Hra",641.25,"DIA","D",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[44,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 4251 SPRING F/TENSION ORD",2.5,"Hra",641.25,"DIA","D",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[45,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 4331 TOGGLE BLOCK SPRING",6.5,"Hra",2565,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":5},6.5,6.5,{"$nulls":3},6.5,6.5,6.5,6.5,null,null,6.5,6.5,null,null,6.5,6.5,6.5,null,null,6.5,19.5,null,null,19.5,6.5,6.5,null,null,19.5,6.5,null,null,6.5,6.5,6.5]
[46,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 442793201 RING",2.5,"Hra",1282.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[47,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 900064800 ADAPTER G1BXG3/4B",3,"Hra",1282.5,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[48,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE 900065500 ADAPTER G3/4BXG3/4B",3,"Hra",1282.5,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[49,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE BOLT F/CHECK PLATE M42X170X100MM P1059",2.5,"Hra",641.25,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[50,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE COIL SPRING F/BOLT JAW FIXED MOVABLE",2.5,"Hra",1282.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[51,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE E-405 V-BELTS",3.5,"Hra",2565,"DIA","E",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[52,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA PRIMARIA OTSUKA FS4840","CAMBIO DE PIN DE TENSION ROD",4.5,"Hra",1282.5,"DIA","E",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[53,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442.8017-01 DUST SEAL RING",3.5,"Hra",285,"DIA","E",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[54,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442647001 SEAL RING (CHANCAD. SANDV)",2.5,"Hra",142.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[55,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442647301 SPIDER BUSHING",12,"Hra",285,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[56,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442789201   HYDR.CYL. BUSCHING",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[57,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442789301 PISTON WEARING PL",6,"Hra",285,"DIA","D",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[58,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442789401 STEP WASHER",3.5,"Hra",285,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[59,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442789501 MAIN SHAFT STEP",6,"Hra",285,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[60,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442791101 BURNING RING",2,"Hra",142.5,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[61,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442791200 HEAD NUT WITH BUR",3.5,"Hra",570,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[62,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442791301 MAIN SHAFT SLEEVE",6,"Hra",285,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[63,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442791401 PROTECTION OF WEARING DOWN FOR ARM",4.5,"Hra",570,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[64,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442791501 PROTECTION OF WEARING DWN IN BOX OF NECKLACE",4.5,"Hra",570,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[65,{"$f":"CONCATENATE(C73,D73)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442793101 SEAL RING INNER",3,"Hra",1140,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[{"$f":"+A73+1","v":66},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442793401 GASKET",3,"Hra",570,"DIA","C",null,{"$f":"+H74","v":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$nulls":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$nulls":5},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$nulls":3},{"$f":"H74","v":3},{"$f":"H74","v":3},{"$f":"H74","v":3},3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[67,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442797601 SPIDER CAP",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[68,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442798600 FEED HOPPER CONE LH",4,"Hra",570,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[69,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442798690 FEED HOPPER CONE RH",4,"Hra",570,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[70,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442798901 MANTLE B (CHANCAD. SANDV)",6,"Hra",142.5,"DIA","G",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[71,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442802101 RETAINER",6,"Hra",1140,"DIA","D",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[72,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442802201 SCRAPER",5.5,"Hra",1140,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":5},5.5,5.5,{"$nulls":3},5.5,5.5,5.5,5.5,null,null,5.5,5.5,null,null,5.5,5.5,5.5,null,null,5.5,16.5,null,null,16.5,5.5,5.5,null,null,16.5,5.5,null,null,5.5,5.5,5.5]
[73,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442824901 CONCAVE EC-EC2",8,"Hra",142.5,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[74,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886401 WEARING DOWN PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[75,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886501 WEARING DOWN PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[76,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886601   WEARING PLATE",3,"Hra",570,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,120,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[77,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886701    WEARING PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[78,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886801  WEARING PLATE",3,"Hra",570,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[79,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442886901    WEARING PLATE",3,"Hra",570,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[80,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4428870  BOTTOM SHELL LINERS KIT PARENT NO",2,"Hra",285,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[81,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 442993601  PINION SHAFT",6,"Hra",1140,"DIA","D",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[82,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4524188001  ECCENTRIC WEARING PLATE",3,"Hra",1140,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[83,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4524190001 BOTTOM SHELL BUSHING",4,"Hra",1140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[84,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4524191001 ECCENTRIC BUSCHING THROW 16+19+22",7,"Hra",1140,"DIA","C",null,7,7,7,{"$nulls":3},7,7,7,{"$nulls":5},7,7,{"$nulls":3},7,7,7,7,null,null,7,7,null,null,7,7,7,null,null,7,21,null,null,21,7,7,null,null,21,7,null,null,7,7,7]
[85,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4524193001 ECCENTRIC BUSHING THROW 29+32+34+36",7,"Hra",1140,"DIA","D",null,7,7,7,{"$nulls":3},7,7,7,{"$nulls":5},7,7,{"$nulls":3},7,7,7,7,null,null,7,7,null,null,7,7,7,null,null,7,21,null,null,21,7,7,null,null,21,7,null,null,7,7,7]
[86,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4525542901 FILTER KIT CH/CS420/CS430",1.5,"Hra",71.25,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[87,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4525574901 EA REPAIR KIT PINION SHAFT  HOUSING",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[88,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4525777901  BOTTOMSHELL ARM LINER KIT CH / CS 430",5.5,"Hra",285,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":5},5.5,5.5,{"$nulls":3},5.5,5.5,5.5,5.5,null,null,5.5,5.5,null,null,5.5,5.5,5.5,null,null,5.5,16.5,null,null,16.5,5.5,5.5,null,null,16.5,5.5,null,null,5.5,5.5,5.5]
[89,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4525791901  FASTENER KIT CONCAVE CH430",3,"Hra",570,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[90,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 4525797901 LOCATING BAR KIT CH/ CS430",3.5,"Hra",1140,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[91,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 873.0833-00 O-RING 379, 3 X 5, 7 SMS 1586",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[92,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 873111200 SEALING COMPOUND ( CHANCAD. SANDV) 2440450",2.5,"Hra",142.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[93,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 906-0140-00 LUBRICATING OIL PUMP",6.5,"Hra",570,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":5},6.5,6.5,{"$nulls":3},6.5,6.5,6.5,6.5,null,null,6.5,6.5,null,null,6.5,6.5,6.5,null,null,6.5,19.5,null,null,19.5,6.5,6.5,null,null,19.5,6.5,null,null,6.5,6.5,6.5]
[94,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 912.0139-00 FILTER CARTRIDGE",1.5,"Hra",142.5,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[95,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE 912015500 FILTER CARTRIDGE",1.5,"Hra",142.5,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[96,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE ARM SHIELD ",5.5,"Hra",285,"DIA","D",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":5},5.5,5.5,{"$nulls":3},5.5,5.5,5.5,5.5,null,null,5.5,5.5,null,null,5.5,5.5,5.5,null,null,5.5,16.5,null,null,16.5,5.5,5.5,null,null,16.5,5.5,null,null,5.5,5.5,5.5]
[97,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE DOWEL PIN",4,"Hra",570,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[98,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE DUST SEAL RETAINING RING",3,"Hra",1140,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[99,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE HYDROSET PUMP ASS.",6,"Hra",570,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[100,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE INNER HEAD NUT",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[101,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE LUBRICATION PUMP ASS.",6.5,"Hra",570,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":5},6.5,6.5,{"$nulls":3},6.5,6.5,6.5,6.5,null,null,6.5,6.5,null,null,6.5,6.5,6.5,null,null,6.5,19.5,null,null,19.5,6.5,6.5,null,null,19.5,6.5,null,null,6.5,6.5,6.5]
[102,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE MAINSHAFT ASS.EXCL. MANTLE",8,"Hra",4560,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[103,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE PINIONSHAFT HOUSING ASS. EXCL.PULLEY",8,"Hra",4560,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[104,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[105,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[106,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE SPIDER BUSHING",3.5,"Hra",570,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[107,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE STEP BEARING SET",5.5,"Hra",1140,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":5},5.5,5.5,{"$nulls":3},5.5,5.5,5.5,5.5,null,null,5.5,5.5,null,null,5.5,5.5,5.5,null,null,5.5,16.5,null,null,16.5,5.5,5.5,null,null,16.5,5.5,null,null,5.5,5.5,5.5]
[108,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","CAMBIO DE TOP SHELL ASS. EXCL. CONCAVE",4,"Hra",4560,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[109,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","ENGRASE DE EQUIPOS",2,"Hra",71.25,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[110,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA SECUNDARIA SANDVIK CONE CRUSHER CH430","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[111,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 3090-1 ESPACIADOR  DE CONTRA EJE",1.5,"Hra",2280,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[112,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442 7984 01 ARM SHIELD",5.5,"Hra",285,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":5},5.5,5.5,{"$nulls":3},5.5,5.5,5.5,5.5,null,null,5.5,5.5,null,null,5.5,5.5,5.5,null,null,5.5,16.5,null,null,16.5,5.5,5.5,null,null,16.5,5.5,null,null,5.5,5.5,5.5]
[113,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442.8017-01 DUST SEAL RING",3.5,"Hra",285,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[114,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442647001 SEAL RING (CHANCAD. SANDV)",2.5,"Hra",142.5,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[115,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442647301 SPIDER BUSHING",12,"Hra",285,"DIA","D",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[116,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442719301 OIL SEAL REING (CHANCAD. SANDV)",3.5,"Hra",285,"DIA","D",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[117,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442789301 PISTON WEARING PL",6,"Hra",285,"DIA","D",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[118,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442789401 STEP WASHER",3.5,"Hra",285,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[119,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442789501 MAIN SHAFT STEP",6,"Hra",285,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[120,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442791101 BURNING RING",2,"Hra",142.5,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[121,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442791200 HEAD NUT WITH BUR",3.5,"Hra",570,"DIA","F",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[122,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442791301 MAIN SHAFT SLEEVE",6,"Hra",285,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[123,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442791401 PROTECTION OF WEARING DOWN FOR ARM",4.5,"Hra",570,"DIA","D",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[124,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442791501 PROTECTION OF WEARING DWN IN BOX OF NECKLACE",4.5,"Hra",570,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[125,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 4427925-01 EXCENTRIC BUSHING 29+32+34+36",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[126,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442792901 DUST COLLAR",4,"Hra",1140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[127,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442793401 GASKET",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[128,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 4427935-01 BOTTOM SHELL BUSHING",4,"Hra",1140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[129,{"$f":"CONCATENATE(C137,D137)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442797601 SPIDER CAP",12,"Hra",285,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[{"$f":"+A137+1","v":130},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442798600 FEED HOPPER CONE LH",4,"Hra",570,"DIA","D",null,{"$f":"+H138","v":4},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$nulls":3},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$nulls":5},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$nulls":3},{"$f":"H138","v":4},{"$f":"H138","v":4},{"$f":"H138","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[131,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442798690 FEED HOPPER CONE RH",4,"Hra",570,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[132,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442798901 MANTLE B (CHANCAD. SANDV)",6,"Hra",142.5,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[133,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442802201 SCRAPER",5.5,"Hra",1140,"DIA","D",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":5},5.5,5.5,{"$nulls":3},5.5,5.5,5.5,5.5,null,null,5.5,5.5,null,null,5.5,5.5,5.5,null,null,5.5,16.5,null,null,16.5,5.5,5.5,null,null,16.5,5.5,null,null,5.5,5.5,5.5]
[134,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886401 WEARING DOWN PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[135,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886501 WEARING DOWN PLATE",3,"Hra",570,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[136,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886601   WEARING PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,72,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[137,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886701    WEARING PLATE",3,"Hra",570,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[138,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886801  WEARING PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[139,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 442886901    WEARING PLATE",3,"Hra",570,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[140,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 4521216001 CONCAVE MF M1",8,"Hra",142.5,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[141,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 840103400 SCREW",2.5,"Hra",142.5,"DIA","D",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[142,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 847001600 WASHER",1.5,"Hra",142.5,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[143,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 863003200 DISC SPRING 71X36X4",2,"Hra",285,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[144,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 868079000 RODAMIENTO 22219E/C3",2.5,"Hra",285,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[145,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 873.0833-00 O-RING 379, 3 X 5, 7 SMS 1586",6,"Hra",1140,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[146,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 873111200 SEALING COMPOUND ( CHANCAD. SANDV) 2440450",2.5,"Hra",142.5,"DIA","D",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[147,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 906-0140-00 LUBRICATING OIL PUMP",6.5,"Hra",570,"DIA","C",null,6.5,6.5,6.5,{"$nulls":3},6.5,6.5,6.5,{"$nulls":5},6.5,6.5,{"$nulls":3},6.5,6.5,6.5,6.5,null,null,6.5,6.5,null,null,6.5,6.5,6.5,null,null,6.5,19.5,null,null,19.5,6.5,6.5,null,null,19.5,6.5,null,null,6.5,6.5,6.5]
[148,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 912.0139-00 FILTER CARTRIDGE",1.5,"Hra",142.5,"DIA","F",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[149,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE 912015500 FILTER CARTRIDGE",1.5,"Hra",142.5,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[150,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE CFW-F2 BAF SF SLO.5 DRWX7 18-30-6/4.5 RETEN",3.5,"Hra",570,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[151,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE FILTRO",4,"Hra",142.5,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[152,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE FILTRO DEL HIDROSET",4,"Hra",142.5,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[153,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE FILTRO DEL LUBRICADOR",4,"Hra",142.5,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[154,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[155,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[156,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","ENGRASE DE EQUIPOS",2,"Hra",71.25,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[157,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","CHANCADORA TERCIARIA SANDVIK H3800","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",31.25,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[158,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRENSORA SULLAIR LS12-60H/A/SUL y tanque de aire comprimido","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[159,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRENSORA SULLAIR LS12-60H/A/SUL y tanque de aire comprimido","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[160,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRENSORA SULLAIR LS12-60H/A/SUL y tanque de aire comprimido","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[161,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA GARDEN DENVER EXTRACTOR DE POLVO PRIMARIO","CAMBIO DE FILTRO DE ACEITE",4,"Hra",228,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[162,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA GARDEN DENVER EXTRACTOR DE POLVO PRIMARIO","CAMBIO DE FILTRO DE AIRE",4,"Hra",228,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[163,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA GARDEN DENVER EXTRACTOR DE POLVO PRIMARIO","CAMBIO DE SEPARADOR DE KIT",2,"Hra",228,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[164,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR 10B-40HP/AC/STD CELDAS WENCO","CAMBIO DE FILTRO DE ACEITE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[165,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR 10B-40HP/AC/STD CELDAS WENCO","CAMBIO DE FILTRO DE AGUA",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[166,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR 10B-40HP/AC/STD CELDAS WENCO","CAMBIO DE FILTRO DE AIRE ",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[167,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR 10B-40HP/AC/STD CELDAS WENCO","CAMBIO DE FILTRO DE ELEMENTO",4,"Hra",288,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[168,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR 10B-40HP/AC/STD CELDAS WENCO","CAMBIO DE FILTRO ELEMENTO SEPARADOR",4,"Hra",288,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[169,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR LS12 -60H/A/SUL","CAMBIO DE ELEMENTO DE FILTRO",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[170,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR LS12 -60H/A/SUL","CAMBIO DE FILTRO DE AIRE",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[171,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR LS12 -60H/A/SUL","CAMBIO DE FILTRO SEPARADOR DE AGUA",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[172,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR LS12 -60H/A/SUL","CAMBIO DE FILTRO SEPARADOR PRIMARIO",4,"Hra",201.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[173,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","COMPRESORA SULLAIR LS12 -60H/A/SUL","CAMBIO DE FILTRO SEPARADOR SECUNDARIO",4,"Hra",201.6,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[174,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","estractor de polvo zona chancado  secundario","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[175,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","estractor de polvo zona chancado  secundario","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[176,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","estractor de polvo zona chancado  secundario","ENGRASE DE EQUIPOS",5,"Hra",15.625,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[177,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","estractor de polvo zona chancado  secundario","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[178,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[179,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[180,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[181,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","MANTENIMIENTO EXTRACTOR",12,"Hra",90,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[182,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","MANTENIMIENTO EXTRACTOR",12,"Hra",180,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[183,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Extractor de polvo Zona Chancado secundario(BOMBA)","MANTENIMIENTO EXTRACTOR",12,"Hra",360,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[184,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","G",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[185,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[186,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[187,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[188,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[189,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[190,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[191,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[192,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[193,{"$f":"CONCATENATE(C201,D201)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[{"$f":"+A201+1","v":194},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4A de 30\" x longitud de 14m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","G",null,{"$f":"+H202","v":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$nulls":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$nulls":5},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$nulls":3},{"$f":"H202","v":3},{"$f":"H202","v":3},{"$f":"H202","v":3},3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[195,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[196,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[197,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[198,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[199,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE CONVEYOR BELTS 750MM X 3P X 3.2 X 1.6 X 30\"",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[200,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[201,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[202,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[203,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[204,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 4B de 25\" x longitud de 25m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[205,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[206,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[207,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE BANDA DE 30\"",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[208,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[209,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[210,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[211,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","D",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[212,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[213,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[214,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5A de 30\" x longitud de 53m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[215,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[216,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[217,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","D",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[218,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[219,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[220,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[221,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","D",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[222,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[223,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[224,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5B de 30\" x longitud de 13m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[225,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[226,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[227,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[228,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[229,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[230,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[231,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[232,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[233,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[234,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",13333.333333333334,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[235,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[236,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[237,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[238,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora 5C de 30\" x  longitud de 14.5m","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",13333.333333333334,"DIA","G",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[239,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",666.6666666666666,"DIA","G",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[240,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\"","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",666.6666666666666,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[241,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",666.6666666666666,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[242,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[243,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE BALL BEARING NK-318-K",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[244,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[245,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE CHAIN WHEEL RS-140-C-NT-25X80MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[246,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE CHAIN WHELL RS-140-C-NT-17X80MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[247,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE H318 MANGUITO",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[248,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE PILLOW BLOCK FYH- P318",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[249,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE POLEA MATRIZ ENJEBADO 720X850X80X1370MM",8,"Hra",1344,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[250,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",168,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[251,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[252,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 01 de 30\" x Longitud de 26 m","CAMBIO DE ROLLER CHAIN RS-140 WROL (CON PASADOR)",3,"Hra",336,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[253,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",266,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[254,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE BALL BEARING NK-318-K",2,"Hra",1064,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[255,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",532,"DIA","D",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[256,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE CHAIN WHEEL RS-140-C-NT-25X80MM. DIAM.",3,"Hra",1064,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[257,{"$f":"CONCATENATE(C265,D265)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE CHAIN WHELL RS-140-C-NT-17X80MM. DIAM.",3,"Hra",1064,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[{"$f":"+A265+1","v":258},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE H318 MANGUITO",2,"Hra",1064,"DIA","C",null,{"$f":"+H266","v":2},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$nulls":3},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$nulls":5},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$nulls":3},{"$f":"H266","v":2},{"$f":"H266","v":2},{"$f":"H266","v":2},2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[259,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE PILLOW BLOCK FYH- P318",4.5,"Hra",1064,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[260,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE POLEA MATRIZ ENJEBADO 720X850X80X1370MM",8,"Hra",2128,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[261,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",266,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[262,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",266,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[263,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 02 de 30\" x longitud de 150m","CAMBIO DE ROLLER CHAIN RS-140 WROL (CON PASADOR)",3,"Hra",532,"DIA","G",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[264,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[265,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[266,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE BANDA TRANSPORTADORA 30",12,"Hra",336,"DIA","D",null,12,12,12,{"$nulls":3},12,12,120,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[267,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[268,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[269,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[270,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[271,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[272,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[273,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE RODILLOS DE CARGA CNT 90MM.X210MM 24-1 520-24MCC",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[274,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 06 de 26\" x longitud de 51.60m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[275,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","G",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[276,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","G",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[277,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[278,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[279,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE CONVEYOR BELTS 750MM X 3P X 3.2 X 1.6 X 30\"",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[280,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[281,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","D",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[282,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[283,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[284,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE RODILLOS DE CARGA CNT 90MM.X210MM 24-1 520-24MCC",2,"Hra",168,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[285,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 07 de 40\" x longitud de 63.2 m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[286,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[287,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE BALL BEARING FYH-UK-313-K",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[288,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","D",null,12,12,12,{"$nulls":3},12,12,120,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[289,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[290,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","E",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[291,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",2,"Hra",672,"DIA","E",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[292,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[293,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[294,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE POLIN DE CARGA LISO DIAMETRO 5 1/2\" X 350 MM",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[295,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[296,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 08 de 30\" Hacia Tolva de finos x longitud,38m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[297,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE 1212K   BALL BEARING",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[298,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE 1215KTVC3  BALL BEARING",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[299,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[300,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE CARRIER ROLLER 5\" CGA.D/IMPACTO 24\"",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[301,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE CHAIN WHEEL RS 100 CNT 17 X 45MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[302,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE CHAIN WHEEL RS 100 CNT 24 X 55 MM",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[303,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE H212 (55MM)",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[304,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE HA2313 (H2313.203)  (2 3/16)   MANGUITO D/MONTAJE",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[305,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE PILLOW BLOCK UKP 313",4.5,"Hra",672,"DIA","D",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[306,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE POLEA TRACTORA 420X850X50X1190MM",8,"Hra",1344,"DIA","D",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[307,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE POLIN DE CARGA LISO DIAMETRO 5 1/2\" X 350 MM",1.5,"Hra",168,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[308,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[309,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE RODILLOS DE RETORNO RSD 600-24 MCC",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[310,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 09 de 30,\" de tolva de finos x longitud .11m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",336,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[311,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE 1217KTVC3  BALL BEARING",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[312,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE BANDA TRANSPORTADORA DE 42",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[313,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE MANGUITO D/MONTAJE H-2317",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[314,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE POLEA MATRIZ ENJEBADO 720X850X80X1370MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[315,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE POLIN DE CARGA PARA FAJA DE 42\"",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[316,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE POLIN DE RETORNO PARA FAJA DE 42\"",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[317,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[318,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE ROLLER CHAIN RS-100",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[319,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora N° 3 de 42\" x longitud de 41m","CAMBIO DE SN517  PILLOW BLOCK BALL BEARING",2,"Hra",672,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[320,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE 30-2 POLINES SIMPLE C/DISCO DE JEBE",1.5,"Hra",199.5,"DIA","D",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[321,{"$f":"CONCATENATE(C329,D329)","v":"OPEXMCH"},"OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE BALL BEARING NK-318-K",2,"Hra",798,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[{"$f":"+A329+1","v":322},"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE BANDA TRANSPORTADORA DE 30",12,"Hra",399,"DIA","C",null,{"$f":"+H330","v":12},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$nulls":3},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$nulls":5},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$nulls":3},{"$f":"H330","v":12},{"$f":"H330","v":12},{"$f":"H330","v":12},12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[323,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE CHAIN WHEEL RS-140-C-NT-25X80MM. DIAM.",3,"Hra",798,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[324,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE CHAIN WHELL RS-140-C-NT-17X80MM. DIAM.",3,"Hra",798,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[325,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE H318 MANGUITO",2,"Hra",798,"DIA","E",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[326,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE PILLOW BLOCK FYH- P318",4.5,"Hra",798,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[327,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE POLEA MATRIZ ENJEBADO 720X850X80X1370MM",8,"Hra",1596,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[328,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",4000,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[329,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",4000,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[330,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",199.5,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[331,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",199.5,"DIA","D",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[332,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","CAMBIO DE ROLLER CHAIN RS-140 WROL (CON PASADOR)",3,"Hra",399,"DIA","D",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[333,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora Nº5D de Chancadora Terciario Sandvik","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",4000,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[334,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 4 A  de 30\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",1066.6666666666667,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[335,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 4 A  de 30\"","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",1066.6666666666667,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[336,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 4 A  de 30\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",1066.6666666666667,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[337,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 5B  de 30\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[338,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 5B  de 30\"","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[339,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Faja Transportadora\n 5B  de 30\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[340,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancado terciario","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[341,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancado terciario","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[342,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancado terciario","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[343,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancadora secundaria ","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[344,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancadora secundaria ","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[345,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","motor de sobre presión chancadora secundaria ","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[346,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","MOTOREDUCTOR FAJA TRANSPORTADORA 4 B 24\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[347,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","MOTOREDUCTOR FAJA TRANSPORTADORA 4 B 24\"","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[348,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","MOTOREDUCTOR FAJA TRANSPORTADORA 4 B 24\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",13333.333333333334,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[349,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","TALLER ELECTRICO PLANTA","CONEXIONADO DE MOTORES",5,"Hra",30,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[350,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","TALLER ELECTRICO PLANTA","HERMETIZADO DE MOTOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[351,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","TALLER ELECTRICO PLANTA","TRABAJOS DE TABLEROS",1,"Hra",30,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[352,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","TALLER ELECTRICO PLANTA","TRABAJOS DE TABLEROS",1,"Hra",120,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[353,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","TALLER MECANICO PLANTA","ENGRASE DE EQUIPOS",1,"Hra",30,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[354,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","VALVULA ROTATIVA ","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",666.6666666666666,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[355,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","VALVULA ROTATIVA ","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",666.6666666666666,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[356,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","VALVULA ROTATIVA ","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",666.6666666666666,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[357,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chanacdo Secundario","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",41.666666666666664,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[358,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chanacdo Secundario","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",41.666666666666664,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[359,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chanacdo Secundario","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",41.666666666666664,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[360,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chancado Terciario","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[361,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chancado Terciario","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[362,"OPEXMCH","OPEXM","CH","CHANCADORA Y TRITURADORA","Ventilador del sistema de Lubricacion de Chancado Terciario","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",62.5,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[363,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",5,"Hra",40,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[364,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[365,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",1280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[366,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[367,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[368,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[369,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[370,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[371,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",160,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[372,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",80,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[373,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[374,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[375,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[376,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE ORING",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[377,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",160,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[378,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",5,"Hra",40,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[379,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[380,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[381,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[382,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",1280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[383,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",4,"Hra",20,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[384,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",4,"Hra",20,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[385,{"$f":"CONCATENATE(C393,D393)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",640,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[{"$f":"+A393+1","v":386},"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",80,"DIA","D",null,{"$f":"+H394","v":4},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$nulls":3},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$nulls":5},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$nulls":3},{"$f":"H394","v":4},{"$f":"H394","v":4},{"$f":"H394","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[387,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",320,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[388,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",320,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[389,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",80,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[390,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[391,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",20,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[392,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",160,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[393,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE ORING",4,"Hra",20,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[394,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[395,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[396,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA  1 DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",320,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[397,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE ANILLO DE PISTON",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[398,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE CAJA DE EMPAQUETADURA (CAJA DE EXPELLER)",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[399,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE COVER PLATE",4,"Hra",84,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[400,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE EJE",4,"Hra",2688,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[401,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE EXPELLER",4,"Hra",168,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[402,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE EXPELLER RING",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[403,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",84,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[404,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE IMPELLER O'RING",4,"Hra",84,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[405,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE IMPULSOR",4,"Hra",84,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[406,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE LABERINTO",4,"Hra",672,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[407,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE LANTERN RING (DISTRIBUIDOR DE AGUA)",4,"Hra",84,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[408,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE NECK RING",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[409,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE OILSEAL DE TAPA LATERAL",4,"Hra",672,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[410,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE RETENEDOR DE GRASA",4,"Hra",2688,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[411,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[412,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[413,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE ROLLER BEARING 938+932 (RODAMIENTO)",4,"Hra",336,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[414,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE SHAFT SLEEVE (BOCINA)",4,"Hra",84,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[415,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE SHAFT SLEEVE O-RING",4,"Hra",84,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[416,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE TAPA LATERAL",4,"Hra",672,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[417,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","CAMBIO DE TROAT BUSH",4,"Hra",84,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[418,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1  MOLINO FULLER 8 X 6 FAH WARMAN","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[419,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE 129-4 BUJE CIERRE HIDRAULICO (DISTRIBUIDOR DE AGUA)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[420,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE ANILLO DE NEOPRENO DE BAJA",4,"Hra",96,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[421,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE ANILLO NEOPRENE",4,"Hra",96,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[422,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE BEARING  5318WBR = 3318(RODAMIENTO)",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[423,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE BOTADOR D/AGUA LADO IMPULSOR",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[424,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE BOTADOR D/AGUA LADO TRANSMISION (A)",4,"Hra",192,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[425,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE CAJA DE PRENSA ESTOPAS",4,"Hra",3072,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[426,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE COVER PLATE",4,"Hra",48,"DIA","G",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[427,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE EJE",4,"Hra",3072,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[428,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE FORRO LADO DE PRENSA ESTOPA BOMBA 8 X 6 DENVER (FRAME PLATE)",4,"Hra",48,"DIA","F",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[429,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE IMPULSOR CERRADO PARA BOMBA DENVER 8 X 6",4,"Hra",48,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[430,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE MANGA PARA EJE (BOCINA)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[431,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE OIL SEAL ( C )",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[432,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE OIL SEAL (D)",4,"Hra",192,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[433,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE PERNOS D/LA PLACA D/SELLO",4,"Hra",192,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[434,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE PLACA D/SELLO",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[435,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE PLATO DE SUCCION BOMBA DENVER 8 X 6 (TROAT BUSH)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[436,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","D",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[437,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[438,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (A)",4,"Hra",384,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[439,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (B)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[440,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE TUBERIA DE SUCCION BRIDADA BOMBA 8X6 SRL",4,"Hra",96,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[441,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","F",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[442,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",40,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[443,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[444,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",1280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[445,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[446,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[447,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",640,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[448,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",80,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[449,{"$f":"CONCATENATE(C457,D457)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[{"$f":"+A457+1","v":450},"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",320,"DIA","C",null,{"$f":"+H458","v":4},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$nulls":3},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$nulls":5},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$nulls":3},{"$f":"H458","v":4},{"$f":"H458","v":4},{"$f":"H458","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[451,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",80,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[452,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",20,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[453,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[454,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",160,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[455,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE ORING",4,"Hra",20,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[456,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[457,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",20,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[458,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 1 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",320,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[459,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",60,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[460,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",120,"DIA","D",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[461,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",1920,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[462,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[463,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE COVER PLATE",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[464,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",1221.8181818181818,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[465,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[466,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[467,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[468,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[469,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[470,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[471,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[472,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE ORING",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[473,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[474,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RETEN",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[475,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[476,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[477,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[478,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2  DE MOLINO N° 01 6X4 EG NISSO WARMAN","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[479,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE ANILLO DE PISTON",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[480,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE CAJA DE EMPAQUETADURA (CAJA DE EXPELLER)",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[481,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE COVER PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[482,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE EJE",4,"Hra",3072,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[483,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE EXPELLER",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[484,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE EXPELLER RING",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[485,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[486,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE IMPELLER O'RING",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[487,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE IMPULSOR",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[488,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE LABERINTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[489,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE LANTERN RING (DISTRIBUIDOR DE AGUA)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[490,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE NECK RING",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[491,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE OILSEAL DE TAPA LATERAL",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[492,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE RETENEDOR DE GRASA",4,"Hra",1536,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[494,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[498,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 CELDA SK-240 8X6 FAH WARMAN","CAMBIO DE TAPA LATERAL",4,"Hra",768,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[505,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE BOTADOR D/AGUA LADO IMPULSOR",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[508,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE COVER PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[512,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE MANGA PARA EJE (BOCINA)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[517,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","CAMBIO DE PLATO DE SUCCION BOMBA DENVER 8 X 6 (TROAT BUSH)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[523,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE 8X6 SRL DENVER DE MOLINO 8'X11' MARCY","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[527,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[530,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[537,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA CENTRIFUGA 2 DE MOLINO N° 02 6X4 EG NISSO WARMAN","CAMBIO DE ORING",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[542,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA DE LUBRICACIÓN ALTA PARA MOLINO FULLER (2 UNIDADES)","CAMBIO DE FILTRO LAVABLE EN MALLA ACERO INOXI 40MI",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[543,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA DE LUBRICACIÓN BAJA PARA MOLINO FULLER (2 UNIDADES)","CAMBIO DE ELEMENTO DE FILTRO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[547,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[554,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE RETEN SUPERIOR CR-31189",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[557,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL 3.5 COCHA DE EMERGENCIA DEL MOLINO 8X11","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[561,"OPEXMMO","OPEXM","MO","MOLIENDA","BOMBA VERTICAL DE MOLINO FULLER","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[567,"OPEXMMO","OPEXM","MO","MOLIENDA","Celda de Flotación SK-240","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[572,"OPEXMMO","OPEXM","MO","MOLIENDA","CICLON DE CAL  D-10","CAMBIO DE CABEZAL DE CAUCHO",4,"Hra",224,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[576,"OPEXMMO","OPEXM","MO","MOLIENDA","CICLON DE CAL  D-10","CAMBIO DE VORTEX",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[582,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE PILLOW BLOCK BEARING FYH-4KP-213+HS-313-",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[585,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora Alimento Molino 8 x 11 de 26\" tunel 5","CAMBIO DE POLINES RECTAS D/IMPACTO 102X686X25X890",1.5,"Hra",168,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[592,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",5,"Hra",672,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[596,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","CAMBIO DE POLINES D/CARGA TRIPLE IMPACTO D/JEBE 30",5,"Hra",168,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[601,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 20\" de Molino N° 02","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[603,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE BANDA TRANSPORTADORA DE 24",12,"Hra",336,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[606,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de 24\" de Molino N° 01 - alimento M1-M2","CAMBIO DE CHAIN WHEEL RS-100-1C-NT-24X60MM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[614,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora de Molino de Cal de 24\" x longitud de 11.5m","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",100,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[616,"OPEXMMO","OPEXM","MO","MOLIENDA","Faja Transportadora N 4 MOLINO FULLER DE 24\"","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[621,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE CONTRA EJE PIÑON DEL MOLINO FULLER DIAM. 9.6' X 14'",24,"Hra",5864.727272727273,"DIA","C",null,24,24,24,{"$nulls":3},24,24,24,{"$nulls":5},24,96,{"$nulls":3},39.5,24,24,24,null,null,24,24,null,null,72,24,24,null,null,24,72,null,null,48,24,24,null,null,72,24,null,null,24,24,24]
[627,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE LEVANTADOR TAPA DE ALIMENTACION",2,"Hra",183.27272727272728,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[631,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE REPLACEMENT FRICTION LINING & FASTENERS",3.5,"Hra",183.27272727272728,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,168,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[634,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO FULLER 9.6' X 14'","CAMBIO DE SPOUT FEEDER  MOLINO FULLER - GETS",4.5,"Hra",183.27272727272728,"DIA","C",null,4.5,4.5,4.5,{"$nulls":3},4.5,4.5,4.5,{"$nulls":5},4.5,4.5,{"$nulls":3},4.5,4.5,4.5,4.5,null,null,4.5,4.5,null,null,4.5,4.5,4.5,null,null,4.5,13.5,null,null,13.5,4.5,4.5,null,null,13.5,4.5,null,null,4.5,4.5,4.5]
[641,{"$f":"CONCATENATE(C649,D649)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE 110 TRUNNION METAL F/CHARGE SIDE - GETS",12,"Hra",2932.3636363636365,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[645,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE BOLT F/LINER",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[650,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE LINER TYPE \"B\"",12,"Hra",366.54545454545456,"DIA","C",null,12,12,12,{"$nulls":3},24,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[652,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CILINDRICO MARCY 8' X 11'","CAMBIO DE PERNO PARA FORRO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},24,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[660,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE EMPAQUETADURA D/LANA 1/2\"X0.80MTSX1.20MT\"",2.5,"Hra",70,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[661,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO CABEZAL DESCARGA TIPO G - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[669,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE HEAD PLATE",6,"Hra",280,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[670,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE HEAD PLATES ANILLO \"B\"",12,"Hra",280,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[676,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 1 OTZUKA C-249 8' X 3'","CAMBIO DE ROLLER BEARING",6,"Hra",1920,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[680,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE EMPAQUETADURA DE LANA",2.5,"Hra",70,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[687,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE FORRO TIPO E - GETS",12,"Hra",560,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},39.5,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[690,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE HEAD PLATES ANILLO \"B\"",6,"Hra",280,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[694,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO CONICO 2 OTZUKA C-249 8' X 3'","CAMBIO DE PERNOS PARA ACOPLA.MIENTO CONTRA EJE",6,"Hra",480,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[700,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO DE CAL 4\" X 8\"","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",100,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[705,{"$f":"CONCATENATE(C713,D713)","v":"OPEXMMO"},"OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE FORRO TIPO \"I\" - GETS",12,"Hra",576,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[707,"OPEXMMO","OPEXM","MO","MOLIENDA","MOLINO REMOLIENDA CÓNICA OTZUKA C249  8' X 13'","CAMBIO DE LIFTER BARS CILINDRO + ELEM. SUJ.",12,"Hra",576,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[715,"OPEXMMO","OPEXM","MO","MOLIENDA","Motor de lubricacion 02 molino 8x11","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[718,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE BRIDA Y CONEXION DE ALIMENTAD",5,"Hra",112,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[720,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE EMPAQUETADURA P/ABRAZADERA VITAULICA 6\"",2,"Hra",224,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[725,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN  D-15 DE MOLINO FULLER","CAMBIO DE TAPA DE FE. DEL CABEZAL",3.5,"Hra",448,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[729,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE BRIDA Y CONEXION DE ALIMENTAD",1,"Hra",112,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[736,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 03 D-15 DE MOLINO 8'X11'","CAMBIO DE TAPA DE FE. DEL CABEZAL",3.5,"Hra",448,"DIA","C",null,3.5,3.5,3.5,{"$nulls":3},3.5,3.5,3.5,{"$nulls":5},3.5,3.5,{"$nulls":3},3.5,3.5,3.5,3.5,null,null,3.5,3.5,null,null,3.5,3.5,3.5,null,null,3.5,10.5,null,null,10.5,3.5,3.5,null,null,10.5,3.5,null,null,3.5,3.5,3.5]
[739,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE  BRIDA DE DESCARGA",1,"Hra",168,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[745,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE FORRO DE JEBE CONICO 12 GRADOS",5.5,"Hra",672,"DIA","C",null,5.5,5.5,5.5,{"$nulls":3},5.5,5.5,5.5,{"$nulls":5},5.5,5.5,{"$nulls":3},5.5,5.5,5.5,5.5,null,null,5.5,5.5,null,null,5.5,5.5,5.5,null,null,5.5,16.5,null,null,16.5,5.5,5.5,null,null,16.5,5.5,null,null,5.5,5.5,5.5]
[749,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° 04 D-6 REMOLIENDA","CAMBIO DE PLACA SEPARADORA",3,"Hra",168,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[754,"OPEXMMO","OPEXM","MO","MOLIENDA","NIDO DE CICLÓN N° DE MOLINOS 01 Y 02 - (D-10)","CAMBIO DE BRIDA Y CONEXION DESCARGA",1,"Hra",168,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[760,"OPEXMMO","OPEXM","MO","MOLIENDA","TALLER ELECTRICO PLANTA","CONEXIONADO DE MOTORES",5,"Hra",30,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[764,"OPEXMMO","OPEXM","MO","MOLIENDA","TALLER ELECTRICO PLANTA","TRABAJOS DE TABLEROS",1,"Hra",120,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[767,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","B. V. N°9 concentrado de plomo","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[774,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE CAMISA DE EJE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[778,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE FRAME PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[779,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 1   6X4 AH WARMAN #77A","CAMBIO DE IMPULSOR (BOMBA WARMAN 6 X 4 EAH)",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[784,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE BEARING  6535/6580(RODAMIENTO)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[791,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE IMPULSOR (BOMBA WARMAN 6 X 4 EAH)",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[794,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 2   6X4 AH WARMAN #77B","CAMBIO DE SHAFT SLEEVE SPACER",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[798,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE ANILLO NEOPRENE",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[803,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE COVER PLATE",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[809,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE OIL SEAL (D)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[813,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 A 8X6 SRL DENVER","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (A)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[816,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE 129-4 BUJE CIERRE HIDRAULICO (DISTRIBUIDOR DE AGUA)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[823,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE COVER PLATE",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[827,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE MANGA PARA EJE (BOCINA)",4,"Hra",60,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[833,{"$f":"CONCATENATE(C841,D841)","v":"OPEXMFP"},"OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA 52 B 8X6 SRL DENVER","CAMBIO DE TAPA CAJA D/RODA. LADO IMPULSOR (A)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[838,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[840,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE COVER PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[843,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[851,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA Nª1 FLOTACION DE PLOMO 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE PLOMO)","CAMBIO DE RETEN",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[853,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[858,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE EJE",4,"Hra",576,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[862,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE EXPELLER",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[869,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[872,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[878,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[882,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA CENTRIFUGA NRO 3 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE LABERINTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[887,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Bomba espumas plomo","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[889,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Bomba espumas plomo","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[897,{"$f":"CONCATENATE(C905,D905)","v":"OPEXMFP"},"OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[900,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[902,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL  ESPIASA DE 2.5 AF LADO 52A 52B","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",537.6,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[907,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[912,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[917,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL DE FLOTACIÓN DE PLOMO DE ANALIZADOR DE LEYES DE 1.5 FIMA","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[924,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL GALIN GHER DE 2.5 LADO 61 (BOMBA VERTICAL 85)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[927,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[931,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[937,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[942,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 2 DE RELAVE BULK CONCENTRADO DE ZINC 20 HP  DE 1.5 X36 P\" ","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[946,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[949,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[956,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 3 CONCENTRADO BULK 10 HPDE 1.5 P\" MARCA","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[961,{"$f":"CONCATENATE(C969,D969)","v":"OPEXMFP"},"OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[{"$f":"+A969+1","v":962},"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,{"$f":"+H970","v":4},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$nulls":3},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$nulls":5},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$nulls":3},{"$f":"H970","v":4},{"$f":"H970","v":4},{"$f":"H970","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[966,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[973,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[976,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 4 RELAVE GENERAL 20 HP DELCROSA DE 1.5 P","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[980,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[986,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[991,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 5 CONCETRADO BULK 20 HP MARCA DELCROSSA DE 1.5 P\"","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[996,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1001,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1004,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 6 RELAVE GENERAL 10 HP DE 2.5 P\" MARCA ES","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1011,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1015,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1020,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1022,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 7 CONCETRADO DE ZINC 10 HP DE 1.5 X 36 P\" M","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1025,{"$f":"CONCATENATE(C1033,D1033)","v":"OPEXMFP"},"OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1033,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1035,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 8 DE RELAVE 1 10 HP DE 2.5 X36 P\" MARCA ES","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1040,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1046,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1050,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1053,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","BOMBA VERTICAL N° 9 CONCETRADO DE PLOMO 10 HP DE 1.5 X 36 P","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1060,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº1","CAMBIO DE MANGUITO DE MONTAJE INFERIOR H3122 CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[1064,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº1","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1070,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº2","CAMBIO DE 140MM X 170MM X 15MM RETEN INFERIOR D/CAJA D/ RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1071,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº2","CAMBIO DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1079,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº2","CAMBIO DE TAPA SUPERIOR DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1080,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº3","CAMBIO DE CAJA DE RODAMIENTOS ",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1088,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº3","CAMBIO DE ROTOR CELDA OK 10",5,"Hra",183.27272727272728,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[{"$f":"+A1097+1","v":1090},"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celda  OK 10 Plomo Nº3","CAMBIO DE TAPA SUPERIOR DE CAJA DE RODAMIENTOS",5,"Hra",977.4545454545455,"DIA","C",null,{"$f":"+H1098","v":5},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$nulls":3},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$nulls":5},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$nulls":3},{"$f":"H1098","v":5},{"$f":"H1098","v":5},{"$f":"H1098","v":5},5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1095,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA DE FLOTACION WEMCO ROUGHER PLOMO ( Nº 2)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1099,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA DE FLOTACION WEMCO ROUGHER PLOMO ( Nº 3)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1106,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA FLOTA DR- 500 Pb PLOMO ( Nº 1)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1109,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","CELDA FLOTA DR- 500 Pb PLOMO ( Nº 2)","ENGRASE DE EQUIPOS",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1113,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb # 03","CAMBIO DE 25 IMPELLER POLIURETANO DR-500",4,"Hra",224,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1119,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #01","CAMBIO DE 05 EJE",10,"Hra",896,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":5},10,10,{"$nulls":3},10,10,10,10,null,null,10,10,null,null,10,10,10,null,null,10,30,null,null,30,10,10,null,null,30,10,null,null,10,10,10]
[1124,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #01","CAMBIO DE SECTOR DIFUSOR POLIURETANO CELDA DENVER",6,"Hra",224,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[1126,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #01","CAMBIO DE V-BELTS B-98 OPTIBELT DR-500",2,"Hra",112,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1134,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Celdas Denver de Flotación DR-500 Pb #02","CAMBIO DE V-BELTS B-98 OPTIBELT DR-500",2,"Hra",112,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1137,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 01 de 30\" x longitud de 16m","CAMBIO DE BALL BEARING NK-318-K",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1139,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 01 de 30\" x longitud de 16m","CAMBIO DE CHAIN WHEEL RS-140-C-NT-25X80MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[1144,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 01 de 30\" x longitud de 16m","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1149,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 02 de 22\" x longitud 34m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[1155,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Faja Transportadora de Conc Pb N° 03 de 30\" x longitud 29.80m","CAMBIO DE RODILLOS DE IMPACTO DE JEBE CTI 520-24 MCC 24-1",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1158,"OPEXMFP","OPEXM","FP","FLOTACION PLOMO","Motor de Acondicionador de Pb 01","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1162,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Acondicionador 10x10","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1168,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1173,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1179,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE LABERINTO",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1183,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. DE ESPUMAS OK N°2 (MIXTOS) - 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1186,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1193,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE EXPELLER",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1197,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE ORING",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1198,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°10, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1204,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE BOCINA",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1207,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE EJECTOR",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1213,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE LABERINTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1217,{"$f":"CONCATENATE(C1225,D1225)","v":"OPEXMFZ"},"OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°11, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1223,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1228,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1232,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE IMPULSOR",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1235,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°8, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1242,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE COVER PLATE",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1246,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1252,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIF. N°9, FLOTACION OK DE ZINC 6X4 EG NISSO WARMAN (DEBAJO OK 10 DE ZINC)","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1257,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIFUGA 77 A  10X8 E-M","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1259,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA CENTRIFUGA NRO 2 DE PLOMO 6X4  EG (DEBAJO DE OK 10 DE PLOMO)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",114.28571428571429,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1262,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1270,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1272,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1277,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF  PISO DE CELDA OK-10 ZINC","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[{"$f":"+A1289+1","v":1282},"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1120,"DIA","C",null,{"$f":"+H1290","v":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$nulls":3},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$nulls":5},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$nulls":3},{"$f":"H1290","v":4},{"$f":"H1290","v":4},{"$f":"H1290","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1288,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1291,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 AF #85","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1297,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1301,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL  ESPIASA DE 2.5 STD DEBAJO 1ERA CELDA WENCO DE ZINC","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1306,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1308,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1316,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL 3.5 SCV CLEANER DE ZN","CAMBIO DE RODAMIENTO 22222EK",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1319,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1321,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1326,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1331,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL DE 2.5 LADO DE CELDAS DENVER SUB A24","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1336,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE DISCHARGE PIPE",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1343,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[{"$f":"+A1353+1","v":1346},"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","BOMBA VERTICAL N° 85 DE ALTA EFICIENCIA 2.5 (DEBAJO DEL ACODICIONADOR DE C","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",560,"DIA","C",null,{"$f":"+H1354","v":4},{"$f":"H1354","v":4},{"$f":"H1354","v":4},{"$nulls":3},{"$f":"H1354","v":4},{"$f":"H1354","v":4},{"$f":"H1354","v":4},{"$nulls":5},{"$f":"H1354","v":4},{"$f":"H1354","v":4},{"$nulls":3},{"$f":"H1354","v":4},{"$f":"H1354","v":4},{"$f":"H1354","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1350,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE 100MM X 125MM X 12MM RETEN SUPERIOR D/CAJA D/RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1356,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE RODAMIENTO INFERIOR  CELDA OK 10",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[1361,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº1","CAMBIO DE TAPA INFERIOR  DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1365,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE 140MM X 170MM X 15MM RETEN INFERIOR D/CAJA D/ RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1368,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE MANGUITO DE  MONTAJE SUPERIOR  CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[1375,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE TAPA INFERIOR  DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1376,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº2","CAMBIO DE TAPA SUPERIOR DE CAJA DE RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",977.4545454545455,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1381,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº3","CAMBIO DE DIFUSOR CELDA OK10",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[1385,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº3","CAMBIO DE RODAMIENTO SUPERIOR CELDA  OK 10 (2312CE1 AKM )",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[1392,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE 100MM X 125MM X 12MM RETEN SUPERIOR D/CAJA D/RODAMIENTOS DEL UPPER SHAFT CELDA OK 10",5,"Hra",244.36363636363637,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1395,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE DIFUSOR CELDA OK10",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[1399,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","CAMBIO DE RODAMIENTO SUPERIOR CELDA  OK 10 (2312CE1 AKM )",3,"Hra",244.36363636363637,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[1405,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº4","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[{"$f":"+A1417+1","v":1410},"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","CAMBIO DE MANGUITO DE  MONTAJE SUPERIOR  CELDA OK 10",1.5,"Hra",244.36363636363637,"DIA","C",null,{"$f":"+H1418","v":1.5},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$nulls":3},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$nulls":5},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$nulls":3},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},{"$f":"H1418","v":1.5},1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[1415,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda  Ok 10 Zinc  Nº5","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",160,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1420,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #02","CAMBIO DE 05 EJE D/IMPULSOR",10,"Hra",977.4545454545455,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":5},10,10,{"$nulls":3},10,10,10,10,null,null,10,10,null,null,10,10,10,null,null,10,30,null,null,30,10,10,null,null,30,10,null,null,10,10,10]
[1423,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #02","CAMBIO DE DIFUSOR CELDA DENVER SUBA-24",6,"Hra",244.36363636363637,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[1430,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Comesa  SUB A-24 Limpieza de Cu #03","CAMBIO DE DIFUSOR CELDA DENVER SUBA-24",6,"Hra",244.36363636363637,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[1434,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 03 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[1435,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 03 - WEMCO 500","CAMBIO DE 6535/6580 RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[1441,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 03 - WEMCO 500","CAMBIO DE RING, SUPPORT",1.5,"Hra",366.54545454545456,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[1444,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 05 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[1452,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 05 - WEMCO 500","CAMBIO DE RODAMIENTO 941/932",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[1454,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 06 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[1459,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc # 06 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1465,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #01 - WEMCO 500","CAMBIO DE 6535/6580 RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[1469,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #01 - WEMCO 500","CAMBIO DE FAJAS DE TRANSMISION HERMANADAS",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1472,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #01 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1479,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #02 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1483,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #02 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1489,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #04 - WEMCO 500","CAMBIO DE 6535/6580 RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[1490,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #04 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1494,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota  Wemco en Rougher Zinc #04 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1501,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC # 06","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1503,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC #02","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1509,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (11 MOTOR CELDAS WEMCO)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1514,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (12 MOTOR CELDAS WEMCO)\n","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1518,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (3 MOTOR CELDAS WEMCO)\n","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1525,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (7MOTOR CELDAS WEMCO)\n","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1528,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (7MOTOR CELDAS WEMCO)\n","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1532,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN ROUGHER ZINC (8 MOTOR CELDAS WEMCO)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[{"$f":"+A1545+1","v":1538},"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc # 12 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,{"$f":"+H1546","v":2},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$nulls":3},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$nulls":5},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$nulls":3},{"$f":"H1546","v":2},{"$f":"H1546","v":2},{"$f":"H1546","v":2},2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1543,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #07 - WEMCO 500","CAMBIO DE 31313-RR2 SECTOR DISPERSOR HOOD",2.5,"Hra",366.54545454545456,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[1548,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #07 - WEMCO 500","CAMBIO DE FALSE BOTTOM DRAFT TUBE - 20\" SUB P.N. 63143-08",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1553,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN SCAVENGER ZINC #08","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1556,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #08 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1558,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #08 - WEMCO 500","CAMBIO DE COLLAR ASSEMBLY  STL/RUBBER  P.N.63276-05",6,"Hra",1466.1818181818182,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[1563,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #08 - WEMCO 500","CAMBIO DE RODAMIENTO 941/932",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[1568,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #09 - WEMCO 500","CAMBIO DE 69625-01 DISPERSOR",4,"Hra",733.0909090909091,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1574,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #09 - WEMCO 500","CAMBIO DE RING, SUPPORT",1.5,"Hra",366.54545454545456,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[1577,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","CELDA FLOTA WEMCO EN SCAVENGER ZINC #10","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1581,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #10 - WEMCO 500","CAMBIO DE 69806-01 STAND PIPE AND FLANGE PLATE 6\" LONGER",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1587,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #10 - WEMCO 500","CAMBIO DE RODAMIENTO 941/932",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[1593,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #11 - WEMCO 500","CAMBIO DE COLLAR ASSEMBLY  STL/RUBBER  P.N.63276-05",6,"Hra",1466.1818181818182,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[1598,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda Flota Wemco en Scavenger Zinc #11 - WEMCO 500","CAMBIO DE W62154-01 END CAP AND SEAL ASSY",2,"Hra",733.0909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[{"$f":"+A1609+1","v":1602},"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE 15 BEARING CUP (UPPER BEARING) F60204-W100369",2,"Hra",1954.909090909091,"DIA","C",null,{"$f":"+H1610","v":2},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$nulls":3},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$nulls":5},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$nulls":3},{"$f":"H1610","v":2},{"$f":"H1610","v":2},{"$f":"H1610","v":2},2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1605,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE 5 BEARING TPRD CONE 5.3751  F60188-W100368",2,"Hra",1954.909090909091,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1612,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Celda WENCO de Flota de Zinc de 1500 p3","CAMBIO DE TUBO DARDO CELDA WENCO 1500P3",2,"Hra",244.36363636363637,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1616,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA  SULLAIR TS-20 FILTRO PRENSA","CAMBIO DE 010608311001 KIT DE REPARACION DE CILINDRO TS-20",2,"Hra",288,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1617,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA  SULLAIR TS-20 FILTRO PRENSA","CAMBIO DE 130-6623-FLUIDRAIN  DREN AUTOMATICO ｽ 115V 232 PSIG",2,"Hra",288,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[1623,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR ST 1509","CAMBIO DE FILTRO DE ACEITE",4,"Hra",228,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1627,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE ELEMENTO DE FILTRO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1632,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE FILTRO ACEITE",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1636,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS-20 # 02","CAMBIO DE FILTRO SEPARADOR AIRE ACEITE SECUNDARIO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1642,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE  FILTRO DE AIRE SECUNDARIO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1647,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE 010-250034-134 ELEMENTO DE FILTRO SEPARADOR SECUNDARIO (SULLAIR)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1652,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE 250025526 FILTRO ACEITE (SULLAIR TS20)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1654,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE ELEMENTO DE FILTRO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1661,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","COMPRESORA SULLAIR TS20-1","CAMBIO DE P116446 FILTRO DE AIRE (COMPRESORA TS 20)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1665,{"$f":"CONCATENATE(C1673,D1673)","v":"OPEXMFZ"},"OPEXM","FZ","FLOTACION ZINC","COMPRSA TS20 F.PRENSA","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1671,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE 044A PLACA LENZER MEMBRANA",5,"Hra",1466.1818181818182,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,{"$f":"H1679","v":5},{"$nulls":3},{"$f":"H1679","v":5},5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1676,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE CILINDRO PISTON COMPLETO FILTRO PRENSA",4,"Hra",1466.1818181818182,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1678,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE FILTRO DE ACEITE  HDA FTS 110",4,"Hra",183.27272727272728,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1681,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE LONA PARA PLACA RIGIDA (55 MM CUELLO)",5,"Hra",91.63636363636364,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1689,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","FILTRO PRENSA DE 1500 ZINC","CAMBIO DE VALVULA DIRECCIONAL 4/3 NG6DBCH/24 VDC NP 16",1.5,"Hra",1466.1818181818182,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[1691,"OPEXMFZ","OPEXM","FZ","FLOTACION ZINC","Motor Ventilador TS-20  Prensa","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1696,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF ESPESADOR TUNEL DE  CAL 6X4 EG NISSO WARMAN","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1701,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE COVER PLATE",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1707,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE FRAME PLATE",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1710,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIF. TUNEL DEL ESPESADOR DE COBRE, 6X4 EG NISSO WARMAN.","CAMBIO DE ORING",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1716,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2304,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1720,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE EJECTOR",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1726,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE LABERINTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1727,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 EG ESPESADOR OVER FLOW","CAMBIO DE ORING",4,"Hra",72,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1735,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE COVER PLATE",4,"Hra",36,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,{"$f":"H1743","v":4},{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1738,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE END COVER (TAPAS)",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1740,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE EXPELLER",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1745,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA 6X4 EG N° 01 RETORNO DE COURIER DE CABEZA","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",288,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1750,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRÍFUGA 6X4 VOGT #2 FILTRO PRENSA (BOMBA BULLS)","CAMBIO DE RETEN",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1755,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE BOCINA",4,"Hra",84,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1762,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",84,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1765,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESP. MIXTO DE PB Y ZN 6X4 EG NISSO WARMAN","CAMBIO DE ORING",4,"Hra",84,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1769,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1775,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE EJECTOR",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1780,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE IMPULSOR",4,"Hra",24,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1785,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1787,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE PB ( 104 ) 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",71.42857142857143,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[{"$f":"+A1801+1","v":1794},"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE EJE",4,"Hra",977.4545454545455,"DIA","C",null,{"$f":"+H1802","v":4},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$nulls":3},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$f":"H1802","v":4},{"$nulls":5},{"$f":"H1802","v":4},4,{"$nulls":3},{"$f":"H1802","v":4},{"$f":"H1802","v":4},4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1798,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE EXPELLER",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1799,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",24,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,{"$f":"H1807","v":4},{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1805,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA ESPESADOR DE ZINC ( 106 ) 6X4 EG NISSO WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1811,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA OVER FLOW\nESPESADOR DE Pb","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1814,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA CENTRIFUGA VOGT #1, ALIMENTACION AL FILTRO PRENSA (DEBAJO DE FILTRO CC-30)","CAMBIO DE RETEN",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1818,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA DE FILTRADO ( FILTRO CERAMICO CC-30 DE Zn)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1824,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA DE H2O( FILTRO CERAMICO CC6  DE  Pb)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1829,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1834,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1836,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1844,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 #  4 COURIER  RELAVE GENERAL","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1849,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1853,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1854,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1860,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 2 COURIER CONCENTRADO DE ZINC","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1863,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,{"$f":"H1871","v":4},{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1871,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1873,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1878,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 3 COURIER  RELAVE 1","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1883,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1888,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1891,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  1.5 # 9 COURIER RETORNO A ESPESADOR DE RELAVE","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1898,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",105,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1902,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1908,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1909,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 # 6 COURIER RETORNO ROUGHER DE ZINC","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1913,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1920,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[{"$f":"+A1929+1","v":1922},"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL  2.5 X 48\" # 8 COURIER RETORNO A CELDA OK2 DE PB","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,{"$f":"+H1930","v":4},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$nulls":3},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$f":"H1930","v":4},{"$nulls":5},{"$f":"H1930","v":4},4,{"$nulls":3},{"$f":"H1930","v":4},{"$f":"H1930","v":4},4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1928,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Bomba Vertical #1 courier concentrado de plomo","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1933,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1938,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1944,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 1.5 DEBAJO DE LA CELDA DENVER SP18","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1947,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1951,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE COVER PLATE (TAPA 3.1/2\" GALIGHER EN CAUCHO)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1957,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","CAMBIO DE RODAMIENTO 22222EK",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1962,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL 3.5 COCHA DE CARGUIO DE ZINC.(LADO DE LA COMPRESORA SULLAI","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",500,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[1967,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",70,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1972,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1975,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1977,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",70,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1982,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 EN EL CLARIFICADOR N°1","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1987,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,{"$f":"H1995","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1993,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[1997,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 1.5 N° 3 COURIER ALIMENTO DE RELAVE 1(CELDA OK 10 DE ZIN Y WEMCO 500 P3)","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2000,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2006,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2012,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMENGENCIA DE ESPESADOR DE ZINC","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",448,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2017,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE DISCHARGE PIPE",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2021,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2024,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA DE EMERGENCIA ESPESADOR DE PLOMO","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2031,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2035,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE IMPULSOR RUBBER (BOMBA VERTICAL 2.5)",4,"Hra",140,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2036,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2042,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 2.5 GALIGHER DEBAJO DE FILTROS CERAMICOS","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",896,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2046,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE CANASTILLA INFERIOR 3.1/2 EN CAUCHO",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2051,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE MANGUITO H-322",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,{"$f":"H2059","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2055,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 (PAICHAE), CANCHA DE COBRE","CAMBIO DE RODAMIENTO 22222EK",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,{"$f":"H2063","v":4},{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2061,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 DEBAJO DE LA CELDA WEMCO DE CU","CAMBIO DE CANASTILLA SUPERIOR 3.1/2\" EN CAUCHO",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2066,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL DE 3.5 DEBAJO DE LA CELDA WEMCO DE CU","CAMBIO DE RETEN INFERIOR CR-39934",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2071,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2073,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2080,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2084,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER 2.5 N° 1 DE LAVADERO, CONCENTRADO DE PLOMO (CAN","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2090,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2091,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2097,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 COCHA ESPESADOR DE PB","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2100,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2108,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2110,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5 N° 2 (CANCHA DE PLOMO Y CANCHA DE ZINC","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",806.4,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2115,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",175,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,{"$f":"H2123","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2120,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",700,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2126,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","BOMBA VERTICAL GALIGHER DE 2.5, DEBAJO DE LA SUB ESTACION DE FILTROS","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",700,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2130,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","DISCO TAMBOR ( FILTRO CERAMICO CC-30 DE Zn)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",320,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2133,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","DISCO TAMBOR (FILTRO CERAMICO CC-06-02)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",320,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2139,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE CHAIN WHEEL RS-80-C-NT-76X50MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[2145,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2146,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Faja Transportadora de Conc de Zinc N° 01 de 30\"","CAMBIO DE RODILLOS DE RETORNO RSD 600-24 MCC",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2150,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC30 de Zn","CAMBIO DE 6413330 O RING 92.0 X 4.0",1.5,"Hra",84,"DIA","C",null,1.5,1.5,1.5,{"$nulls":3},1.5,1.5,1.5,{"$nulls":5},1.5,1.5,{"$nulls":3},1.5,1.5,1.5,1.5,null,null,1.5,1.5,null,null,1.5,1.5,1.5,null,null,1.5,4.5,null,null,4.5,1.5,1.5,null,null,4.5,1.5,null,null,1.5,1.5,1.5]
[2157,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC30 de Zn","CAMBIO DE SPARE HOSE FOR 80",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2159,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC6 de Pb-02","CAMBIO DE 105002404 WEAR PLATE",2.5,"Hra",84,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[2164,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","Filtro Ceramico CC6 de Pb-03","CAMBIO DE 105002404 WEAR PLATE",2.5,"Hra",84,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[2169,"OPEXMEF","OPEXM","EF","ESPESADORES Y FILTROS","motor de retorno de Couier #2","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2175,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Agitador 04 de Tanque Mars 1","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",333.3333333333333,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2179,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Agitador 05 de Tanque Mars 2","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",333.3333333333333,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,{"$f":"H2187","v":5},5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2184,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","B.V.COCHA DE P.A.A","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2188,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA #  2 EF 05 MOD SIHI MOD 125-40","CAMBIO DE CAMISA DE EJE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2194,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA #  2 EF 05 MOD SIHI MOD 125-40","CAMBIO DE TAPA DE CARCASA",4,"Hra",1536,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2199,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA # 1 EF 05 MOD SIHI MOD 125-40","CAMBIO DE CAMISA DE EJE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2204,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA # 1 EF 05 MOD SIHI MOD 125-40","CAMBIO DE RODAMIENTO 63092ZRC3",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2206,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA CENTRIFUGA # 1 EF 05 MOD SIHI MOD 125-40","CAMBIO DE TAPA DE SOPORTE",4,"Hra",1536,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2209,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba de Agua Hidrostal 01 de Bombas mars","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2217,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba de Agua Hidrostal Rio Torres Nº1","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2218,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba de Agua Hidrostal Rio Torres Nº1","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2224,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de Cylinder liner - 8000 HRS",1,"Hra",1333.3333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2230,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de Nut for piston rod - 8000 HRS",0.5,"Hra",1333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":5},0.5,0.5,{"$nulls":3},0.5,0.5,0.5,0.5,null,null,0.5,0.5,null,null,0.5,0.5,0.5,null,null,0.5,1.5,null,null,1.5,0.5,0.5,null,null,1.5,0.5,null,null,0.5,0.5,0.5]
[2233,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de Packing presser - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2237,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de piston B - 2000 HRS",0.5,"Hra",333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":5},0.5,0.5,{"$nulls":3},0.5,0.5,0.5,0.5,null,null,0.5,0.5,null,null,0.5,0.5,0.5,null,null,0.5,1.5,null,null,1.5,0.5,0.5,null,null,1.5,0.5,null,null,0.5,0.5,0.5]
[2243,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de tubería Z - 4000 HRS",3,"Hra",666.6666666666666,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,{"$f":"H2251","v":3},3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[2248,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 1","Cambio de V-Packing de gland - 500 HRS",1,"Hra",83.33333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2253,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de cubierta de caja de valvula - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2255,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de Cylinder liner - 8000 HRS",1,"Hra",1333.3333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2263,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de O-ring de piston - 500 HRS",2,"Hra",83.33333333333333,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2268,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de piston B - 2000 HRS",0.5,"Hra",333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":5},0.5,0.5,{"$nulls":3},0.5,0.5,0.5,0.5,null,null,0.5,0.5,null,null,0.5,0.5,0.5,null,null,0.5,1.5,null,null,1.5,0.5,0.5,null,null,1.5,0.5,null,null,0.5,0.5,0.5]
[2272,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de tapón de aceite - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2273,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de tubería de descarga - 4000 HRS",3,"Hra",666.6666666666666,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[2279,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 2","Cambio de V-Packing de gland - 500 HRS",1,"Hra",83.33333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2283,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de cross head - 8000 HRS",4,"Hra",1333.3333333333333,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2290,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de Lanter ring - 4000 HRS",2,"Hra",666.6666666666666,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2292,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de Nut for piston rod - 8000 HRS",0.5,"Hra",1333.3333333333333,"DIA","C",null,0.5,0.5,0.5,{"$nulls":3},0.5,0.5,0.5,{"$nulls":5},0.5,0.5,{"$nulls":3},0.5,0.5,0.5,0.5,null,null,0.5,0.5,null,null,0.5,0.5,0.5,null,null,0.5,1.5,null,null,1.5,0.5,0.5,null,null,1.5,0.5,null,null,0.5,0.5,0.5]
[2297,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de pin cross - 8000 HRS",1,"Hra",1333.3333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2302,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de rodamientos de aguja - 8000 HRS",1,"Hra",1142.857142857143,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2308,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de valvula de purga de aire - 4000 HRS",1,"Hra",666.6666666666666,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2310,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Mars L-180 - 4","Cambio de V-Packing de gland - 500 HRS",1,"Hra",83.33333333333333,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2317,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 043458004  ANILLO",5,"Hra",192,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2321,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 235582005 O-RING",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2327,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 264637002 SELLOS DE VﾁSTAGO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2328,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 272318009 ELEMENTO FILTRO (VENTILACION)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2332,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 282540003 O-RING",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2339,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 43434002 O-RING",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2342,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 460270 FILTRO DE BAJA PRESION",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2347,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 545004 JUNTA LABIAL PISTﾓN DE BOMBEO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2352,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 609553  PLATILLO DE VALVULA",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2357,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Bomba Putzmeister 01","CAMBIO DE 65977000 ANILLO GUIA DE VﾁSTAGO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2363,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE DISCHARGE PIPE",4,"Hra",1120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2366,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[{"$f":"+A2377+1","v":2370},"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",280,"DIA","C",null,{"$f":"+H2378","v":4},{"$f":"H2378","v":4},{"$f":"H2378","v":4},{"$nulls":3},{"$f":"H2378","v":4},{"$f":"H2378","v":4},{"$f":"H2378","v":4},{"$nulls":5},{"$f":"H2378","v":4},4,{"$nulls":3},{"$f":"H2378","v":4},{"$f":"H2378","v":4},4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2376,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 2 B-MARS","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",125,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2381,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 3 B-MARS","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1344,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2386,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA, POZA N° 3 B-MARS","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2391,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2394,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE CANASTILLA SUPERIOR 3.1/2\" EN CAUCHO",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2396,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE IMPULSOR VERTICAL GALIGHER 3.1/2\" (11-120)",4,"Hra",168,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2401,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","BOMBA VERTICAL DE 3.5 FIMA, POZA N° 1 B-MARS","CAMBIO DE RODAMIENTO 22222EK",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2406,"OPEXMRL","OPEXM","RL","Relaves (bombas MARS)","Espesador de Relave 70'","MANTENIMIENTO ESPESADOR",48,"Hra",523.6363636363636,"DIA","C",null,48,48,48,{"$nulls":3},48,48,48,{"$nulls":5},48,96,{"$nulls":3},39.5,48,48,24,null,null,48,48,null,null,72,48,48,null,null,48,144,null,null,48,48,72,null,null,120,48,null,null,24,48,96]
[2412,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE BOCINA",5,"Hra",30,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2416,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE END COVER (TAPAS)",4,"Hra",120,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2419,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE FRAME PLATE",5,"Hra",30,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2425,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","BOMBA CENTRIF 6X4 EG NISSON WARMAN (CICLÓN DE CAL)","CAMBIO DE RODAMIENTO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2431,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","Extractor de Polvo de tolva de cal","MANTENIMIENTO EXTRACTOR",12,"Hra",480,"DIA","C",null,12,12,12,{"$nulls":3},12,12,12,{"$nulls":5},12,12,{"$nulls":3},12,12,12,12,null,null,12,12,null,null,12,12,12,null,null,12,36,null,null,36,12,12,null,null,36,12,null,null,12,12,12]
[2436,"OPEXMPC","OPEXM","PC","PLANTA DE CAL","Faja Transportadora de Molino de Cal de 24\" x longitud de 11.5m","CAMBIO DE RODILLO DE CARGA NORMAL DE 6\" FAJA 30",2,"Hra",168,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2441,"OPEXMRC","OPEXM","RC","ZONA DE REACTIVOS","Tanque de Xantato Z-06","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2443,"OPEXMRC","OPEXM","RC","ZONA DE REACTIVOS","Tanque de Xantato Z-06","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2450,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE EJECTOR",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2454,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE FRAME PLATE",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2455,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE IMPULSOR",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2461,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIF. N° 2 ESPUMAS BULK  DE LA DENVER SUB A 24 - 6X4 EG (FAJA 2 DE COBRE)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2465,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2472,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2475,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE IMPULSOR",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2480,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA CENTRIFUGA N° 1  ESPUMAS BULK DE LA DENVER SUB A24- 6X4 EG WARMAN ","CAMBIO DE RODAMIENTO",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2485,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2490,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2492,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 2.5 AF N°2 DE CU","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",280,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2500,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 3.5 POZA 4","CAMBIO DE CANASTILLA SUPERIOR 3.1/2\" EN CAUCHO",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2503,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 3.5 POZA 4","CAMBIO DE MANGUITO H-322",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,{"$f":"H2511","v":4},{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2509,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","BOMBA VERTICAL 3.5 POZA 4","CAMBIO DE TUBO DE DESCARGA (90-240)",4,"Hra",1344,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2510,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA DE FLOTACION DE COBRE","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2514,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº10","CAMBIO DE PISO DE CELDA",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":5},10,10,{"$nulls":3},10,10,10,10,null,null,10,10,null,null,10,10,10,null,null,10,30,null,null,30,10,10,null,null,30,10,null,null,10,10,10]
[2519,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº2","CAMBIO DE DIFUSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[2527,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº3","CAMBIO DE DIFUSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[2529,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº3","CAMBIO DE IMPULSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[2534,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº3","CAMBIO DE TAPA SUPERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[2539,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº4","CAMBIO DE PISO ENJEBADO",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":5},10,10,{"$nulls":3},10,10,10,10,null,null,10,10,null,null,10,10,10,null,null,10,30,null,null,30,10,10,null,null,30,10,null,null,10,10,10]
[2545,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº5","CAMBIO DE IMPULSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[2549,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº5","CAMBIO DE TAPA INFERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[2552,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº6","CAMBIO DE EJE",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":5},10,10,{"$nulls":3},10,10,10,10,null,null,10,10,null,null,10,10,10,null,null,10,30,null,null,30,10,10,null,null,30,10,null,null,10,10,10]
[2559,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº7","CAMBIO DE DIFUSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[2564,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº7","CAMBIO DE RODAMIENTO",3,"Hra",733.0909090909091,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[2565,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº7","CAMBIO DE TAPA INFERIOR",2.5,"Hra",733.0909090909091,"DIA","C",null,2.5,2.5,2.5,{"$nulls":3},2.5,2.5,2.5,{"$nulls":5},2.5,2.5,{"$nulls":3},2.5,2.5,2.5,2.5,null,null,2.5,2.5,null,null,2.5,2.5,2.5,null,null,2.5,7.5,null,null,7.5,2.5,2.5,null,null,7.5,2.5,null,null,2.5,2.5,2.5]
[2569,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº8","CAMBIO DE IMPULSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[2576,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº9","CAMBIO DE EJE",10,"Hra",733.0909090909091,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":5},10,10,{"$nulls":3},10,10,10,10,null,null,10,10,null,null,10,10,10,null,null,10,30,null,null,30,10,10,null,null,30,10,null,null,10,10,10]
[2578,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu banco  Nº9","CAMBIO DE PISO DE CELDA",10,"Hra",183.27272727272728,"DIA","C",null,10,10,10,{"$nulls":3},10,10,10,{"$nulls":5},10,10,{"$nulls":3},10,10,10,10,null,null,10,10,null,null,10,10,10,null,null,10,30,null,null,30,10,10,null,null,30,10,null,null,10,10,10]
[2583,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu Banco Nº1","CAMBIO DE DIFUSOR",6,"Hra",183.27272727272728,"DIA","C",null,6,6,6,{"$nulls":3},6,6,6,{"$nulls":5},6,6,{"$nulls":3},6,6,6,6,null,null,6,6,null,null,6,6,6,null,null,6,18,null,null,18,6,6,null,null,18,6,null,null,6,6,6]
[2588,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Denver  SP 18 de Cu Banco Nº1","CAMBIO DE RODAMIENTO",3,"Hra",733.0909090909091,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[2594,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA denver SP18 de Cu banco N°2","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2598,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","CELDA denver SP18 de Cu banco N°4","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2603,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 01 Cobre","CAMBIO DE CORREAS DE TRANSMISION",2,"Hra",183.27272727272728,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2607,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 01 Cobre","CAMBIO DE RODAMIENTO Y PISTA",3,"Hra",183.27272727272728,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[2613,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 02 Cobre","CAMBIO DE RODAMIENTO Y PISTA",3,"Hra",183.27272727272728,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[2618,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 03 Cobre","CAMBIO DE RODAMIENTO",3,"Hra",366.54545454545456,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[2623,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 04 Cobre","CAMBIO DE RETEN",1,"Hra",183.27272727272728,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2625,{"$f":"CONCATENATE(C2633,D2633)","v":"OPEXMFC"},"OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 04 Cobre","CAMBIO DE RODAMIENTO Y PISTA",3,"Hra",183.27272727272728,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[2628,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 05 Cobre","CAMBIO DE RETEN",1,"Hra",183.27272727272728,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2636,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 07 Cobre","CAMBIO DE CORREAS DE TRANSMISION",2,"Hra",183.27272727272728,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2637,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 07 Cobre","CAMBIO DE FAJAS HERMANADAS",2,"Hra",65.45454545454545,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2643,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Celda Wemco 150p3 No 08 Cobre","CAMBIO DE FAJAS HERMANADAS",2,"Hra",366.54545454545456,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2649,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu  Nº1","CAMBIO DE CHAIN WHEEL RS-80-C-NT-76X50MM. DIAM.",3,"Hra",672,"DIA","C",null,3,3,3,{"$nulls":3},3,3,3,{"$nulls":5},3,3,{"$nulls":3},3,3,3,3,null,null,3,3,null,null,3,3,3,null,null,3,9,null,null,9,3,3,null,null,9,3,null,null,3,3,3]
[2653,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu Nº2 de 19\" x longitud 14.8m","CAMBIO DE MANGUITO D/MONTAJE H-309",2,"Hra",672,"DIA","C",null,2,2,2,{"$nulls":3},2,2,2,{"$nulls":5},2,2,{"$nulls":3},2,2,2,2,null,null,2,2,null,null,2,2,2,null,null,2,6,null,null,6,2,2,null,null,6,2,null,null,2,2,2]
[2656,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","Faja Transportadora Concentrado de Cu Nº3 de 19\" x longitud de 12m","CAMBIO DE POLEA MATRIZ ENJEBADO 420X660X60X1280MM",8,"Hra",1344,"DIA","C",null,8,8,8,{"$nulls":3},8,8,8,{"$nulls":5},8,8,{"$nulls":3},8,8,8,8,null,null,8,8,null,null,8,8,8,null,null,8,24,null,null,24,8,8,null,null,24,8,null,null,8,8,8]
[2662,"OPEXMFC","OPEXM","FC","FLOTACION DE COBRE","MOLINO DE CAL 4\" X 8\"","CAMBIO DE SPOUT",4,"Hra",6720,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2667,"OPEXMOT","OPEXM","OT","OTROS","TALLER MECANICO PLANTA","ENGRASE DE EQUIPOS",1,"Hra",120,"DIA","C",null,1,1,1,{"$nulls":3},1,1,1,{"$nulls":5},1,1,{"$nulls":3},1,1,1,1,null,null,1,1,null,null,1,1,1,null,null,1,3,null,null,3,1,1,null,null,3,1,null,null,1,1,1]
[2672,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor 98TGK0418 N° 02","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",200,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2674,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor 98TGK0418 N° 03","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2682,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Agitador de Reactor N° 04","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2687,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE DISTRIBUIDOR DE AGUA (E118 LANTERN RESTRICTOR)",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2691,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE E117 SHAFT SPACER (ESPACIADOR)",4,"Hra",96,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,{"$f":"H2699","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2692,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE EXPELLER",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2698,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE LABYRINTH LOCKNUT",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2702,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE STUFFING BOX",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2709,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE DISTRIBUIDOR DE AGUA (E118 LANTERN RESTRICTOR)",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2712,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE E08910 BEARING SEAL",4,"Hra",384,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2716,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE IMPELLER O'RING",4,"Hra",48,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2721,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 1 CLARIFICADOR 2 6X4  EAH","CAMBIO DE STUFFING BOX",4,"Hra",192,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2727,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE COVER PLATE",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2729,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE E005XLM SHAFT (EJE)",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2736,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE IMPELLER O'RING",4,"Hra",30,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2740,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA # 2 CLARIFICADOR 1 6X4 EAH ","CAMBIO DE RETENEDOR DE GRASA",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2746,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE ANILLO DE PISTON",4,"Hra",160,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2747,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE BEARING  6535/6580(RODAMIENTO)",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2751,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE E005XLM SHAFT (EJE)",4,"Hra",640,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2758,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE IMPULSOR (BOMBA WARMAN 6 X 4 EAH)",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2761,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","CAMBIO DE RETENEDOR DE GRASA",4,"Hra",320,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2766,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA #2 CLARIFICADOR 3 #6 6X4 EAH","FRAME PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2770,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2771,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE BOCINA",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2772,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE COVER PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2773,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EJE",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2774,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EJECTOR",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2775,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2776,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2777,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EXPELLER",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2778,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2779,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE IMPULSOR",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2780,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE LABERINTO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2781,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE ORING",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2782,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2783,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE RETEN",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2784,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 4 CLARIFICADOR 2 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2785,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE 08 BEARING SLEEVE",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2786,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE 29 EXPELLER RING \"R\"",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2787,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE 32 FORRO P/TAPA ARMADURA",4,"Hra",2560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2788,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE BOCINA",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2789,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE COVER PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2790,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EJE",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2791,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EJECTOR",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2792,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE END COVER (TAPAS)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2793,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE END COVER SHIM (LAINA)",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2794,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE EXPELLER",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2795,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE FRAME PLATE",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2796,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE IMPULSOR",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2797,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE LABERINTO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2798,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE ORING",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2799,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE PERNOS CAJA DE RODAMIENTO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2800,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE RETEN",4,"Hra",40,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2801,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS 5 CLARIFICADOR 3 CENTRIFUGA  - 6X4 EG NISSON WARMAN","CAMBIO DE RODAMIENTO",4,"Hra",560,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2802,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 01","CAMBIO DE ESTATOR DE CAUCHO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2803,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 01","CAMBIO DE ROTOR DE ACERO",4,"Hra",960,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2804,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 01","CAMBIO DE TEMPLADOR DE ESTATOR",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2805,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 02","CAMBIO DE ESTATOR DE CAUCHO",5,"Hra",120,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2806,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 02","CAMBIO DE ROTOR DE ACERO",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2807,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 02","CAMBIO DE TEMPLADOR DE ESTATOR",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2808,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 03","CAMBIO DE ESTATOR DE CAUCHO",4,"Hra",240,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2809,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 03","CAMBIO DE ROTOR DE ACERO",4,"Hra",960,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2810,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA DE LODOS DE TORNILLO NOVA CONTAYCOCHA 03","CAMBIO DE TEMPLADOR DE ESTATOR",4,"Hra",480,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2811,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Bomba vertical (bajando las escaleras hacia PTAA)","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2812,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Bomba vertical (bajando las escaleras hacia PTAA)","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2813,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","Bomba vertical (bajando las escaleras hacia PTAA)","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",250,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2814,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2815,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2816,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE 1309 RODAMIENTO",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2817,{"$f":"CONCATENATE(C2825,D2825)","v":"OPEXMPA"},"OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[{"$f":"+A2825+1","v":2818},"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",252,"DIA","C",null,{"$f":"+H2826","v":4},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$nulls":3},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$f":"H2826","v":4},{"$nulls":5},{"$f":"H2826","v":4},4,{"$nulls":3},{"$f":"H2826","v":4},{"$f":"H2826","v":4},4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2819,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,{"$f":"H2827","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2820,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",1008,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2821,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2822,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2823,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,{"$f":"H2831","v":4},{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2824,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2825,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",63,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2826,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2827,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",126,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2828,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE RODAMIENTO 1308",4,"Hra",504,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2829,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2830,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL 1.5 #1 COURIER CONCENTRADO DE PLOMO","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",403.2,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2831,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2832,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2833,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2834,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE DISCHARGE PIPE",4,"Hra",3360,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2835,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE IMPULSOR RUBBER (BOMBA VERTICAL 2.5)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2836,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2837,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2838,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2839,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2840,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2841,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2842,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2843,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2844,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE  2.5  COCHA DE CLARIFICADOR 2 DE 36\"","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2845,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE (COVER PLATE) TAPA PARA CAJA DE BOMBA (BOMBA 1.5)",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2846,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE (PUMP CASING) CAJA DE BOMBA (BOMBA 1.5)",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2847,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE 1309 RODAMIENTO",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2848,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE CANASTILLA INFERIOR (BOMBA VERTICAL 1.5)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2849,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE CANASTILLA SUPERIOR (BOMBA VERTICAL 1.5)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2850,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE COVER BOMBA VERTICAL 1.5 ESPIASA",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2851,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE EJE  BOMBA VERTICAL 1.5 ESPIASA",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2852,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE IMPULSOR BOMBA VERTICAL 1.5 ESPIASA",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2853,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE IMPULSOR GALIGHER (CHICO 1.1/2 11-100)",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2854,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE MANGUITO D/MONTAJE H 308 104 (HE 308)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2855,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE MANGUITO DE MONTAJE H309 107 (HA 309)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2856,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE PUMP CASING BOMBA VERTICAL 1.5 ESPIASA",5,"Hra",210,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2857,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE RETEN INFERIOR 36.51X57.15X7.93",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2858,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE RETEN SUPERIOR (B1SL  31.75 X 50.80 X 6.35  C/R)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2859,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE RODAMIENTO 1308",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2860,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE RODAMIENTO 1308 EKTN9 SKF",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2861,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 1.5 (BAJANDO LAS ESCALERAS HACIA LA PTAA)","CAMBIO DE RODAMIENTO 1309 EKTN9 SKF",4,"Hra",336,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2862,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2863,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2864,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE COVER BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2865,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE DISCHARGE PIPE",4,"Hra",1680,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2866,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE EJE 2 1/2\" X 48 BOMBA VERTICAL ALTA EFICIENCIA  NP 15",4,"Hra",1680,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2867,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE IMPULSOR BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2868,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2869,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2870,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE PUM CASING BOMBA 2.5 ALTA EFICIENCIA",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2871,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2872,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2873,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2874,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2875,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 ALTA EFICIENCIA (BAJANDO LAS ESCALERAS HACIA LA PTAA","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2876,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE CANASTILLA INFERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2877,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE CANASTILLA SUPERIOR",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2878,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE COVER PLATE LINER BOMBA VERTICAL 2 1/2\" (07)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2879,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE DISCHARGE PIPE",4,"Hra",3360,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2880,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE IMPULSOR RUBBER (BOMBA VERTICAL 2.5)",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2881,{"$f":"CONCATENATE(C2889,D2889)","v":"OPEXMPA"},"OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE MANGUITO H2313 (EJE 60 MM)",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[{"$f":"+A2889+1","v":2882},"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE MANGUITO HA-2311 (1 5/16\")",4,"Hra",840,"DIA","C",null,{"$f":"+H2890","v":4},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$nulls":3},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$f":"H2890","v":4},{"$nulls":5},{"$f":"H2890","v":4},4,{"$nulls":3},{"$f":"H2890","v":4},{"$f":"H2890","v":4},4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2883,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE MANGUITO HA-2313 (2 5/16\")",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,{"$f":"H2891","v":4},4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2884,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE PUMP CASING BOMBA 2.1/2 VERTICAL ",4,"Hra",210,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2885,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE RETEN INFERIOR (55.56X82.55X11.11)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2886,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE RETEN SUPERIOR CR-19359 (2020220014 RETEN 19359 BV-2.5-022)",4,"Hra",420,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2887,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE RODAMIENTO 22311 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,{"$f":"H2895","v":4},{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2888,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",672,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2889,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","BOMBA VERTICAL DE 2.5 COCHA DE EMERGENCIA DE REACTORES","CAMBIO DE RODAMIENTO 22313 KCJW",4,"Hra",840,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2890,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","SOPLADOR IR INGERSOLL RAND HILBON CENTRIFUGAL NEUTRALIZACIÓN","CAMBIO DE  FILTRO DE AIRE",4,"Hra",224,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]
[2891,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","SOPLADOR IR INGERSOLL RAND HILBON CENTRIFUGAL NEUTRALIZACIÓN","CAMBIO DE RODAMIENTOS    DELANTERO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2892,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","SOPLADOR IR INGERSOLL RAND HILBON CENTRIFUGAL NEUTRALIZACIÓN","CAMBIO DE RODAMIENTOS   POSTERIOR",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2893,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","SOPLADOR IR INGERSOLL RAND HILBON CENTRIFUGAL NEUTRALIZACIÓN","LIMPIEZA DE ARROLLAMIENTO ",5,"Hra",400,"DIA","C",null,5,5,5,{"$nulls":3},5,5,5,{"$nulls":5},5,5,{"$nulls":3},5,5,5,5,null,null,5,5,null,null,5,5,5,null,null,5,15,null,null,15,5,5,null,null,15,5,null,null,5,5,5]
[2894,"OPEXMPA","OPEXM","PA","PLANTA DE TRATAMIENTO DE AGUA ACIDAD","SOPLADOR SPENCER Nº2 CENTERFUGA BLOWER (PLANTA NEUTRALIZACION)","CAMBIO DE  FILTRO DE AIRE",4,"Hra",224,"DIA","C",null,4,4,4,{"$nulls":3},4,4,4,{"$nulls":5},4,4,{"$nulls":3},4,4,4,4,null,null,4,4,null,null,4,4,4,null,null,4,12,null,null,12,4,4,null,null,12,4,null,null,4,4,4]

{"sheet":"HORAS PARADAS","index":10,"n_rows":75,"n_cols":55,"rows_kept":75,"merged":[[1,3,1,54],[2,0,26,0],[2,3,2,6],[2,7,2,10],[2,11,2,15],[2,16,2,19],[2,20,2,24],[2,25,2,28],[2,29,2,32],[2,33,2,37],[2,38,2,41],[2,42,2,45],[2,46,2,50],[2,51,2,54],[4,3,4,6],[4,7,4,10],[4,11,4,15],[4,16,4,19],[4,20,4,24],[4,25,4,28],[4,29,4,32],[4,33,4,37],[4,38,4,41],[4,42,4,45],[4,46,4,50],[4,51,4,54],[25,3,25,6],[25,7,25,10],[25,11,25,14],[25,15,25,18],[25,19,25,23],[25,24,25,27],[25,28,25,31],[25,32,25,36],[25,37,25,40],[25,41,25,45],[25,46,25,49],[25,50,25,54],[26,3,26,6],[26,7,26,10],[26,11,26,14],[26,15,26,18],[26,19,26,23],[26,24,26,27],[26,28,26,31],[26,32,26,36],[26,37,26,40],[26,41,26,45],[26,46,26,49],[26,50,26,54],[28,0,50,0],[28,3,28,6],[28,7,28,10],[28,11,28,15],[28,16,28,19],[28,20,28,24],[28,25,28,28],[28,29,28,32],[28,33,28,37],[28,38,28,41],[28,42,28,45],[28,46,28,50],[28,51,28,54],[49,3,49,6],[49,7,49,10],[49,11,49,14],[49,15,49,18],[49,19,49,23],[49,24,49,27],[49,28,49,31],[49,32,49,36],[49,37,49,40],[49,41,49,45],[49,46,49,49],[49,50,49,54],[50,3,50,6],[50,7,50,10],[50,11,50,14],[50,15,50,18],[50,19,50,23],[50,24,50,27],[50,28,50,31],[50,32,50,36],[50,37,50,40],[50,41,50,45],[50,46,50,49],[50,50,50,54],[52,0,74,0],[52,3,52,6],[52,7,52,10],[52,11,52,15],[52,16,52,19],[52,20,52,24],[52,25,52,28],[52,29,52,32],[52,33,52,37],[52,38,52,41],[52,42,52,45],[52,46,52,50],[52,51,52,54],[73,3,73,6],[73,7,73,10],[73,11,73,14],[73,15,73,18],[73,19,73,23],[73,24,73,27],[73,28,73,31],[73,32,73,36],[73,37,73,40],[73,41,73,45],[73,46,73,49],[73,50,73,54],[74,3,74,6],[74,7,74,10],[74,11,74,14],[74,15,74,18],[74,19,74,23],[74,24,74,27],[74,28,74,31],[74,32,74,36],[74,37,74,40],[74,41,74,45],[74,46,74,49],[74,50,74,54]]}
["HORAS PARADAS",null,null,{"$f":"+'PLAN ACTIVIDADES PARADAS'!M7","v":0}]
[{"$f":"+'PLAN ACTIVIDADES PARADAS'!A6","v":"PLANTA BENEFICIO HUANZALA"},null,null,{"$f":"+'PLAN ACTIVIDADES PARADAS'!M3","v":2024}]
["PLAN",null,"MES","ENERO",{"$nulls":3},"FEBRERO",{"$nulls":3},"MARZO",{"$nulls":4},"ABRIL",{"$nulls":3},"MAYO",{"$nulls":4},"JUNIO",{"$nulls":3},"JULIO",{"$nulls":3},"AGOSTO",{"$nulls":4},"SEPTIEMBRE",{"$nulls":3},"OCTUBRE",{"$nulls":3},"NOVIEMBRE",{"$nulls":4},"DICIEMBRE"]
[null,null,"SEMANA",1,{"$f":"D4+1","v":2},{"$f":"E4+1","v":3},{"$f":"F4+1","v":4},{"$f":"G4+1","v":5},6,7,8,9,10,11,{"$f":"N4+1","v":12},{"$f":"O4+1","v":13},14,15,16,{"$f":"S4+1","v":17},{"$f":"T4+1","v":18},19,20,{"$f":"W4+1","v":21},{"$f":"X4+1","v":22},{"$f":"Y4+1","v":23},24,{"$f":"AA4+1","v":25},{"$f":"AB4+1","v":26},27,28,29,30,{"$f":"AG4+1","v":31},32,33,{"$f":"AJ4+1","v":34},{"$f":"AK4+1","v":35},36,37,38,39,40,41,42,43,{"$f":"AT4+1","v":44},45,46,{"$f":"AW4+1","v":47},{"$f":"AX4+1","v":48},49,50,51,{"$f":"BB4+1","v":52}]
[null,null,"FECHA","01ENE24 - 28ENE24",{"$nulls":3},"29ENE24 - 25FEB24",{"$nulls":3},"26FEB24 - 31MAR24",{"$nulls":4},"01ABR24 - 28ABR24",{"$nulls":3},"29ABR24 - 26MAY24",{"$nulls":4},"27MAY24 - 30JUN24",{"$nulls":3},"01JUL24 - 28JUL23",{"$nulls":3},"29JUL24 - 25AGO24",{"$nulls":4},"26AGO24 - 29SET24",{"$nulls":3},"30SET24 - 27OCT24",{"$nulls":3},"28OCT24 - 24NOV24",{"$nulls":4},"24NOV24 - 29DIC24"]
[null,null,"TOTAL",72,{"$nulls":3},48,48,null,null,24,48,{"$nulls":3},120,{"$nulls":3},120,0,0,0,0,48,72,null,0,120,null,null,0,96,24,0,0,24,96,null,null,0,120,{"$nulls":3},72,48,null,null,24,48]
[null,1,"CHANCADO PRIMARIO",{"$f":"+D$6*0.07","v":5.040000000000001},0,0,0,3.3600000000000003,3.3600000000000003,0,0,1.6800000000000002,3.3600000000000003,0,0,0,8.4,0,0,{"$f":"+T$6*0.07","v":0},8.4,0,0,0,0,3.3600000000000003,5.040000000000001,0,0,8.4,0,0,0,6.720000000000001,1.6800000000000002,0,0,1.6800000000000002,6.720000000000001,0,0,0,8.4,0,0,0,5.040000000000001,3.3600000000000003,0,0,1.6800000000000002,3.3600000000000003,0,0,0]
[null,2,"CHANCADO SECUNDARIO",{"$f":"+D$6*0.07","v":5.040000000000001},{"$f":"+E$6*0.07","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,1.6800000000000002,3.3600000000000003,0,0,0,8.4,0,0,0,8.4,0,0,0,0,3.3600000000000003,5.040000000000001,0,0,8.4,0,0,0,6.720000000000001,1.6800000000000002,0,0,1.6800000000000002,6.720000000000001,0,0,0,8.4,0,0,0,5.040000000000001,3.3600000000000003,0,0,1.6800000000000002,3.3600000000000003,0,0,0]
[null,3,"CHANCADO TERCIARIO",{"$f":"+D$6*0.07","v":5.040000000000001},{"$f":"+E$6*0.07","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,1.6800000000000002,3.3600000000000003,0,0,0,8.4,0,0,0,8.4,0,0,0,0,3.3600000000000003,5.040000000000001,0,0,8.4,0,0,0,6.720000000000001,1.6800000000000002,0,0,1.6800000000000002,6.720000000000001,0,0,0,8.4,0,0,0,5.040000000000001,3.3600000000000003,0,0,1.6800000000000002,3.3600000000000003,0,0,0]
[null,4,"MOLIENDA",{"$f":"+D$6*0.06","v":4.32},{"$f":"+E$6*0.06","v":0},{"$f":"+F$6*0.06","v":0},0,2.88,2.88,{"$f":"+J$6*0.06","v":0},0,1.44,2.88,0,0,0,7.199999999999999,0,0,0,7.199999999999999,0,0,0,0,2.88,4.32,0,0,7.199999999999999,0,0,0,5.76,1.44,0,0,1.44,5.76,0,0,0,7.199999999999999,0,0,0,4.32,2.88,0,0,1.44,2.88,0,0,0]
[null,5,"PLANTA DE CAL",{"$f":"+D$6*0.025","v":1.8},{"$f":"+E$6*0.025","v":0},{"$f":"+F$6*0.025","v":0},0,1.2000000000000002,1.2000000000000002,0,0,0.6000000000000001,1.2000000000000002,0,0,0,3,0,0,0,3,0,0,0,0,1.2000000000000002,1.8,0,0,3,0,0,0,2.4000000000000004,0.6000000000000001,0,0,0.6000000000000001,2.4000000000000004,0,0,0,3,0,0,0,1.8,1.2000000000000002,0,0,0.6000000000000001,1.2000000000000002,0,0,0]
[null,6,"ABASTECIMIENTO DE AGUA",{"$f":"+D$6*0.07","v":5.040000000000001},{"$f":"+E$6*0.07","v":0},{"$f":"+F$6*0.07","v":0},0,3.3600000000000003,3.3600000000000003,0,0,1.6800000000000002,3.3600000000000003,0,0,0,8.4,0,0,0,8.4,0,0,0,0,3.3600000000000003,5.040000000000001,0,0,8.4,0,0,0,6.720000000000001,1.6800000000000002,0,0,1.6800000000000002,6.720000000000001,0,0,0,8.4,0,0,0,5.040000000000001,3.3600000000000003,0,0,1.6800000000000002,3.3600000000000003,0,0,0]
[null,7,"REACTIVOS",{"$f":"+D$6*0.025","v":1.8},{"$f":"+E$6*0.025","v":0},{"$f":"+F$6*0.025","v":0},0,1.2000000000000002,1.2000000000000002,0,0,0.6000000000000001,1.2000000000000002,0,0,0,3,0,0,0,3,0,0,0,0,1.2000000000000002,1.8,0,0,3,0,0,0,2.4000000000000004,0.6000000000000001,0,0,0.6000000000000001,2.4000000000000004,0,0,0,3,0,0,0,1.8,1.2000000000000002,0,0,0.6000000000000001,1.2000000000000002,0,0,0]
[null,8,"FLOTACION Pb",{"$f":"+D$6*0.05","v":3.6},0,0,0,2.4000000000000004,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0,6,0,0,{"$f":"+T$6*0.05","v":0},6,0,0,0,0,2.4000000000000004,3.6,0,0,6,0,0,0,4.800000000000001,1.2000000000000002,0,0,1.2000000000000002,4.800000000000001,0,0,0,6,0,0,0,3.6,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0]
[null,9,"FLOTACION Cu",{"$f":"+D$6*0.05","v":3.6},0,0,0,2.4000000000000004,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0,6,0,0,0,6,0,0,0,0,2.4000000000000004,3.6,0,0,6,0,0,0,4.800000000000001,1.2000000000000002,0,0,1.2000000000000002,4.800000000000001,0,0,0,6,0,0,0,3.6,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0]
[null,10,"FLOTACION Zn",{"$f":"+D$6*0.05","v":3.6},0,0,0,2.4000000000000004,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0,6,0,0,0,6,0,0,0,0,2.4000000000000004,3.6,0,0,6,0,0,0,4.800000000000001,1.2000000000000002,0,0,1.2000000000000002,4.800000000000001,0,0,0,6,0,0,0,3.6,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0]
[null,11,"FLOTACION Bulk",{"$f":"+D$6*0.05","v":3.6},{"$f":"+E$6*0.05","v":0},0,0,2.4000000000000004,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0,6,0,0,0,6,0,0,0,0,2.4000000000000004,3.6,0,0,6,0,0,0,4.800000000000001,1.2000000000000002,0,0,1.2000000000000002,4.800000000000001,0,0,0,6,0,0,0,3.6,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0]
[null,12,"ESPESADORES",{"$f":"+D$6*0.07","v":5.040000000000001},{"$f":"+E$6*0.07","v":0},{"$f":"+F$6*0.07","v":0},0,3.3600000000000003,3.3600000000000003,0,0,1.6800000000000002,3.3600000000000003,0,0,0,8.4,0,0,0,8.4,0,0,0,0,3.3600000000000003,5.040000000000001,0,0,8.4,0,0,0,6.720000000000001,1.6800000000000002,0,0,1.6800000000000002,6.720000000000001,0,0,0,8.4,0,0,0,5.040000000000001,3.3600000000000003,0,0,1.6800000000000002,3.3600000000000003,0,0,0]
[null,13,"FILTRADO Pb",{"$f":"+D$6*0.04","v":2.88},{"$f":"+E$6*0.04","v":0},{"$f":"+F$6*0.04","v":0},0,1.92,1.92,0,0,0.96,1.92,0,0,0,4.8,0,0,0,4.8,0,0,0,0,1.92,2.88,0,0,4.8,0,0,0,3.84,0.96,0,0,0.96,3.84,0,0,0,4.8,0,0,0,2.88,1.92,0,0,0.96,1.92,0,0,0]
[null,14,"FILTRADO Cu",{"$f":"+D$6*0.05","v":3.6},0,0,0,2.4000000000000004,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0,6,0,0,{"$f":"+T$6*0.05","v":0},6,0,0,0,0,2.4000000000000004,3.6,0,0,6,0,0,0,4.800000000000001,1.2000000000000002,0,0,1.2000000000000002,4.800000000000001,0,0,0,6,0,0,0,3.6,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0]
[null,15,"FILTRADO Zn",{"$f":"+D$6*0.05","v":3.6},0,0,0,2.4000000000000004,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0,6,0,0,0,6,0,0,0,0,2.4000000000000004,3.6,0,0,6,0,0,0,4.800000000000001,1.2000000000000002,0,0,1.2000000000000002,4.800000000000001,0,0,0,6,0,0,0,3.6,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0]
[null,16,"FILTRADO Bulk",{"$f":"+D$6*0.05","v":3.6},{"$f":"+E$6*0.05","v":0},0,0,2.4000000000000004,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0,6,0,0,0,6,0,0,0,0,2.4000000000000004,3.6,0,0,6,0,0,0,4.800000000000001,1.2000000000000002,0,0,1.2000000000000002,4.800000000000001,0,0,0,6,0,0,0,3.6,2.4000000000000004,0,0,1.2000000000000002,2.4000000000000004,0,0,0]
[null,17,"PLANTA DE NEUTRALIZACION",{"$f":"+D$6*0.06","v":4.32},{"$f":"+E$6*0.06","v":0},0,0,2.88,2.88,0,0,1.44,2.88,0,0,0,7.199999999999999,0,0,0,7.199999999999999,0,0,0,0,2.88,4.32,0,0,7.199999999999999,0,0,0,5.76,1.44,0,0,1.44,5.76,0,0,0,7.199999999999999,0,0,0,4.32,2.88,0,0,1.44,2.88,0,0,0]
[null,18,"BOMBAS DE RELAVE",{"$f":"+D$6*0.09","v":6.4799999999999995},{"$f":"+E$6*0.09","v":0},{"$f":"+F$6*0.09","v":0},0,4.32,4.32,0,0,2.16,4.32,0,0,0,10.799999999999999,0,0,0,10.799999999999999,0,0,0,0,4.32,6.4799999999999995,0,0,10.799999999999999,0,0,0,8.64,2.16,0,0,2.16,8.64,0,0,0,10.799999999999999,0,0,0,6.4799999999999995,4.32,0,0,2.16,4.32,0,0,0]
[null,null,"HORAS POR SEMANA",{"$f":"SUM(D7:D24)","v":72.00000000000001},{"$f":"SUM(E7:E24)","v":0},0,0,47.99999999999999,47.99999999999999,{"$f":"SUM(J7:J24)","v":0},0,23.999999999999996,47.99999999999999,0,null,0,120.00000000000001,0,0,0,120.00000000000001,0,0,0,0,47.99999999999999,72.00000000000001,null,0,120.00000000000001,0,0,0,95.99999999999999,{"$f":"SUM(AI7:AI24)","v":23.999999999999996},0,0,23.999999999999996,95.99999999999999,0,0,0,120.00000000000001,0,0,0,72.00000000000001,47.99999999999999,0,0,23.999999999999996,47.99999999999999,0,0,{"$f":"SUM(BC7:BC24)","v":0}]
[null,null,"HORAS POR MES",{"$f":"+SUM(D25:G25)","v":72.00000000000001},{"$nulls":3},{"$f":"+SUM(H25:K25)","v":95.99999999999999},{"$nulls":3},{"$f":"SUM(L25:O25)","v":71.99999999999999},{"$nulls":3},{"$f":"+SUM(P25:S25)","v":120.00000000000001},{"$nulls":3},{"$f":"SUM(T25:X25)","v":120.00000000000001},{"$nulls":4},{"$f":"SUM(Y25:AB25)","v":120},{"$nulls":3},{"$f":"+SUM(AC25:AF25)","v":120.00000000000001},{"$nulls":3},{"$f":"SUM(AG25:AK25)","v":119.99999999999999},{"$nulls":4},{"$f":"+SUM(AL25:AO25)","v":119.99999999999999},{"$nulls":3},{"$f":"+SUM(AP25:AT25)","v":120.00000000000001},{"$nulls":4},{"$f":"SUM(AU25:AX25)","v":120},{"$nulls":3},{"$f":"+SUM(AY25:BC25)","v":71.99999999999999}]
[null,null,"HORAS ACUMULADAS",{"$f":"+D26","v":72.00000000000001},{"$nulls":3},{"$f":"H26+D27","v":168},{"$nulls":3},{"$f":"+L26+H27","v":240},{"$nulls":3},{"$f":"+P26+L27","v":360},{"$nulls":3},{"$f":"T26+P27","v":480},{"$nulls":4},{"$f":"Y26+T27","v":600},{"$nulls":3},{"$f":"AC26+Y27","v":720},{"$nulls":3},{"$f":"AG26+AC27","v":840},{"$nulls":4},{"$f":"AL26+AG27","v":960},{"$nulls":3},{"$f":"+AP26+AL27","v":1080},{"$nulls":4},{"$f":"AU26+AP27","v":1200},{"$nulls":3},{"$f":"+AY26+AU27","v":1272}]
[{"$nulls":3},{"$f":"+'PROYECCION ACTIVIDADES PARADAS'!M7","v":0}]
["PROYECCION",null,"FECHA","01ENE24 - 28ENE24",{"$nulls":3},"29ENE24 - 25FEB24",{"$nulls":3},"26FEB24 - 31MAR24",{"$nulls":4},"01ABR24 - 28ABR24",{"$nulls":3},"29ABR24 - 26MAY24",{"$nulls":4},"27MAY24 - 30JUN24",{"$nulls":3},"01JUL24 - 28JUL23",{"$nulls":3},"29JUL24 - 25AGO24",{"$nulls":4},"26AGO24 - 29SET24",{"$nulls":3},"30SET24 - 27OCT24",{"$nulls":3},"28OCT24 - 24NOV24",{"$nulls":4},"24NOV24 - 29DIC24"]
[null,null,"TOTAL",96,{"$nulls":3},48,48,null,null,72,null,null,0,0,{"$nulls":3},0,null,null,0,0,{"$nulls":8},0,null,null,0,0,{"$nulls":3},0,null,null,0,0,0,{"$nulls":6},0]
[null,1,{"$f":"+C7","v":"CHANCADO PRIMARIO"},{"$f":"+D$30*0.07","v":6.720000000000001},{"$f":"+E$30*0.07","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,2,{"$f":"+C8","v":"CHANCADO SECUNDARIO"},{"$f":"+D$30*0.07","v":6.720000000000001},0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,3,"CHANCADO TERCIARIO",{"$f":"+D$30*0.07","v":6.720000000000001},0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,4,"MOLIENDA",{"$f":"+D$30*0.06","v":5.76},{"$f":"+E$30*0.06","v":0},0,0,2.88,2.88,0,0,4.32,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,5,"PLANTA DE CAL",{"$f":"+D$30*0.025","v":2.4000000000000004},{"$f":"+E$30*0.025","v":0},0,0,1.2000000000000002,1.2000000000000002,0,0,1.8,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,6,"ABASTECIMIENTO DE AGUA",{"$f":"+D$30*0.07","v":6.720000000000001},{"$f":"+E$30*0.07","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,7,"REACTIVOS",{"$f":"+D$30*0.025","v":2.4000000000000004},{"$f":"+E$30*0.025","v":0},0,0,1.2000000000000002,1.2000000000000002,0,0,1.8,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,8,"FLOTACION Pb",{"$f":"+D$30*0.05","v":4.800000000000001},{"$f":"+E$30*0.05","v":0},0,0,2.4000000000000004,2.4000000000000004,0,0,3.6,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,9,"FLOTACION Cu",{"$f":"+D$30*0.05","v":4.800000000000001},0,0,0,2.4000000000000004,2.4000000000000004,0,0,3.6,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,10,"FLOTACION Zn",{"$f":"+D$30*0.05","v":4.800000000000001},0,0,0,2.4000000000000004,2.4000000000000004,0,0,3.6,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,11,"FLOTACION Bulk",{"$f":"+D$30*0.05","v":4.800000000000001},0,0,0,2.4000000000000004,2.4000000000000004,0,0,3.6,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,12,"ESPESADORES",{"$f":"+D$30*0.07","v":6.720000000000001},{"$f":"+E$30*0.07","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,13,"FILTRADO Pb",{"$f":"+D$30*0.04","v":3.84},{"$f":"+E$30*0.04","v":0},0,0,1.92,1.92,0,0,2.88,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,14,"FILTRADO Cu",{"$f":"+D$30*0.05","v":4.800000000000001},{"$f":"+E$30*0.05","v":0},0,0,2.4000000000000004,2.4000000000000004,0,0,3.6,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,15,"FILTRADO Zn",{"$f":"+D$30*0.05","v":4.800000000000001},0,0,0,2.4000000000000004,2.4000000000000004,0,0,3.6,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,16,"FILTRADO Bulk",{"$f":"+D$30*0.05","v":4.800000000000001},0,0,0,2.4000000000000004,2.4000000000000004,0,0,3.6,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,17,"PLANTA DE NEUTRALIZACION",{"$f":"+D$30*0.06","v":5.76},{"$f":"+E$30*0.06","v":0},0,0,2.88,2.88,0,0,4.32,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,18,"BOMBAS DE RELAVE",{"$f":"+D$30*0.09","v":8.64},{"$f":"+E$30*0.09","v":0},0,0,4.32,4.32,0,0,6.4799999999999995,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,"HORAS POR SEMANA",{"$f":"SUM(D31:D48)","v":95.99999999999999},0,0,0,47.99999999999999,47.99999999999999,0,0,72.00000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,"HORAS POR MES",{"$f":"+SUM(D49:G49)","v":95.99999999999999},{"$nulls":3},{"$f":"+SUM(H49:K49)","v":95.99999999999999},{"$nulls":3},{"$f":"SUM(L49:O49)","v":72.00000000000001},{"$nulls":3},{"$f":"+SUM(P49:S49)","v":0},{"$nulls":3},{"$f":"SUM(T49:X49)","v":0},{"$nulls":4},{"$f":"SUM(Y49:AB49)","v":0},{"$nulls":3},{"$f":"+SUM(AC49:AF49)","v":0},{"$nulls":3},{"$f":"SUM(AG49:AK49)","v":0},{"$nulls":4},{"$f":"+SUM(AL49:AO49)","v":0},{"$nulls":3},{"$f":"+SUM(AP49:AT49)","v":0},{"$nulls":4},{"$f":"SUM(AU49:AX49)","v":0},{"$nulls":3},{"$f":"+SUM(AY49:BC49)","v":0}]
[null,null,"HORAS ACUMULADAS",{"$f":"+D50","v":95.99999999999999},{"$nulls":3},{"$f":"H50+D51","v":191.99999999999997},{"$nulls":3},{"$f":"+L50+H51","v":264},{"$nulls":3},{"$f":"+P50+L51","v":264},{"$nulls":3},{"$f":"T50+P51","v":264},{"$nulls":4},{"$f":"Y50+T51","v":264},{"$nulls":3},{"$f":"AC50+Y51","v":264},{"$nulls":3},{"$f":"AG50+AC51","v":264},{"$nulls":4},{"$f":"AL50+AG51","v":264},{"$nulls":3},{"$f":"+AP50+AL51","v":264},{"$nulls":4},{"$f":"AU50+AP51","v":264},{"$nulls":3},{"$f":"+AY50+AU51","v":264}]
[]
["REAL",null,"FECHA","01ENE24 - 28ENE24",{"$nulls":3},"29ENE24 - 25FEB24",{"$nulls":3},"26FEB24 - 31MAR24",{"$nulls":4},"01ABR24 - 28ABR24",{"$nulls":3},"29ABR24 - 26MAY24",{"$nulls":4},"27MAY24 - 30JUN24",{"$nulls":3},"01JUL24 - 28JUL23",{"$nulls":3},"29JUL24 - 25AGO24",{"$nulls":4},"26AGO24 - 29SET24",{"$nulls":3},"30SET24 - 27OCT24",{"$nulls":3},"28OCT24 - 24NOV24",{"$nulls":4},"24NOV24 - 29DIC24"]
[null,null,"TOTAL",96,null,{"$f":"SUM(F55:F72)","v":0},{"$f":"SUM(G55:G72)","v":0},48,48,null,{"$f":"SUM(K55:K72)","v":0},72,null,null,0,0,null,null,0,0,null,null,0,0,null,null,0,0,0,null,null,0,0,null,0,0,0,null,0,0,0,0,null,0,0,0,null,0,0,0,0,0,0,0,0]
[null,1,{"$f":"+C7","v":"CHANCADO PRIMARIO"},{"$f":"+D$30*0.07","v":6.720000000000001},{"$f":"+E$30*0.07","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.07","v":0}]
[null,2,{"$f":"+C8","v":"CHANCADO SECUNDARIO"},{"$f":"+D$30*0.07","v":6.720000000000001},0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,3,"CHANCADO TERCIARIO",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,4,"MOLIENDA",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.06","v":0}]
[null,5,"PLANTA DE CAL",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.025","v":0}]
[null,6,"ABASTECIMIENTO DE AGUA",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.07","v":0}]
[null,7,"REACTIVOS",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.025","v":0}]
[null,8,"FLOTACION Pb",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.05","v":0}]
[null,9,"FLOTACION Cu",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,10,"FLOTACION Zn",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,11,"FLOTACION Bulk",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,12,"ESPESADORES",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.07","v":0}]
[null,13,"FILTRADO Pb",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.04","v":0}]
[null,14,"FILTRADO Cu",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.05","v":0}]
[null,15,"FILTRADO Zn",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,16,"FILTRADO Bulk",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,17,{"$f":"+C23","v":"PLANTA DE NEUTRALIZACION"},6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.06","v":0}]
[null,18,"BOMBAS DE RELAVE",6.720000000000001,0,0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+BC$30*0.09","v":0}]
[null,null,"HORAS POR SEMANA",{"$f":"SUM(D55:D72)","v":120.96},{"$f":"SUM(E55:E72)","v":0},0,0,60.48,60.48,0,0,90.72000000000003,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,"HORAS POR MES",{"$f":"+SUM(D73:G73)","v":120.96},{"$nulls":7},{"$f":"SUM(L73:O73)","v":90.72000000000003},{"$nulls":3},{"$f":"+SUM(P73:S73)","v":0},{"$nulls":3},{"$f":"SUM(T73:X73)","v":0},{"$nulls":4},{"$f":"SUM(Y73:AB73)","v":0},{"$nulls":3},{"$f":"+SUM(AC73:AF73)","v":0},{"$nulls":3},{"$f":"SUM(AG73:AK73)","v":0},{"$nulls":4},{"$f":"+SUM(AL73:AO73)","v":0},{"$nulls":3},{"$f":"+SUM(AP73:AT73)","v":0},{"$nulls":4},{"$f":"SUM(AU73:AX73)","v":0},{"$nulls":3},{"$f":"+SUM(AY73:BC73)","v":0}]
[null,null,"HORAS ACUMULADAS",{"$f":"+D74","v":120.96},{"$nulls":7},{"$f":"+L74+H75","v":90.72000000000003},{"$nulls":3},{"$f":"+P74+L75","v":90.72000000000003},{"$nulls":3},{"$f":"T74+P75","v":90.72000000000003},{"$nulls":4},{"$f":"Y74+T75","v":90.72000000000003},{"$nulls":3},{"$f":"AC74+Y75","v":90.72000000000003},{"$nulls":3},{"$f":"AG74+AC75","v":90.72000000000003},{"$nulls":4},{"$f":"AL74+AG75","v":90.72000000000003},{"$nulls":3},{"$f":"+AP74+AL75","v":90.72000000000003},{"$nulls":4},{"$f":"AU74+AP75","v":90.72000000000003},{"$nulls":3},{"$f":"+AY74+AU75","v":90.72000000000003}]

{"sheet":"DISP_PLANTA","index":11,"n_rows":277,"n_cols":15,"rows_kept":277,"merged":[[7,2,7,13],[222,2,245,2],[246,2,276,2],[246,3,246,7],[247,3,247,7],[248,3,248,7],[249,3,249,7],[250,3,250,7],[251,3,251,7],[252,3,252,7],[253,3,253,7],[254,3,254,7],[255,3,255,7],[256,3,256,7],[257,3,257,7]]}
[null,"DISPONIBILIDAD PLANTA CONCENTRADORA 2024",{"$nulls":6},"MTBF",280,null,"MTTR",1.7]
[]
[null,null,"2012-01-01","2012-02-01","2012-03-01","2012-04-01","2012-05-01"]
[null,"MTBF",{"v":22.921034482758625,"d":"22.9"},{"v":29.868571428571425,"d":"29.9"},{"v":21.071290322580644,"d":"21.1"},{"v":28.742272727272734,"d":"28.7"},{"v":40.345882352941175,"d":"40.3"}]
[null,"MTTR",{"v":1.358620689655173,"d":"1.4"},{"v":0.7095238095238091,"d":"0.7"},{"v":1.4032258064516132,"d":"1.4"},{"v":1.6143939393939393,"d":"1.6"},{"v":0.5872549019607843,"d":"0.6"}]
[]
[]
[null,null,2024]
[]
[null,null,31,28,31,30,31,30,31,31,30,31,30,31]
[null,"HORAS PLANEADAS","2024-01-01","2024-02-01","2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01"]
[0.2,"TOTAL",{"$f":"+C10*24","v":744},{"$f":"+D10*24","v":672},744,720,744,720,744,744,720,744,720,744]
[0.2,{"$f":"+'HORAS PARADAS'!C7","v":"CHANCADO PRIMARIO"},{"$f":"+SUM('HORAS PARADAS'!D7:G7)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!H7:K7)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L7:P7)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q7:T7)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!U7:Y7)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!Z7:AC7)","v":8.400000000000002},{"$f":"+SUM('HORAS PARADAS'!AD7:AG7)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AH7:AL7)","v":10.08},{"$f":"+SUM('HORAS PARADAS'!AM7:AP7)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ7:AT7)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AU7:AY7)","v":10.080000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ7:BC7)","v":3.3600000000000003}]
[0.2,{"$f":"+'HORAS PARADAS'!C8","v":"CHANCADO SECUNDARIO"},{"$f":"+SUM('HORAS PARADAS'!D8:G8)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!H8:K8)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L8:P8)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q8:T8)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!U8:Y8)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!Z8:AC8)","v":8.400000000000002},{"$f":"+SUM('HORAS PARADAS'!AD8:AG8)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AH8:AL8)","v":10.08},{"$f":"+SUM('HORAS PARADAS'!AM8:AP8)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ8:AT8)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AU8:AY8)","v":10.080000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ8:BC8)","v":3.3600000000000003}]
[0.1,{"$f":"+'HORAS PARADAS'!C9","v":"CHANCADO TERCIARIO"},{"$f":"+SUM('HORAS PARADAS'!D9:G9)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!H9:K9)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L9:P9)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q9:T9)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!U9:Y9)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!Z9:AC9)","v":8.400000000000002},{"$f":"+SUM('HORAS PARADAS'!AD9:AG9)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AH9:AL9)","v":10.08},{"$f":"+SUM('HORAS PARADAS'!AM9:AP9)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ9:AT9)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AU9:AY9)","v":10.080000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ9:BC9)","v":3.3600000000000003}]
[0.05,{"$f":"+'HORAS PARADAS'!C10","v":"MOLIENDA"},{"$f":"+SUM('HORAS PARADAS'!D10:G10)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!H10:K10)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!L10:P10)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!Q10:T10)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!U10:Y10)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!Z10:AC10)","v":7.2},{"$f":"+SUM('HORAS PARADAS'!AD10:AG10)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!AH10:AL10)","v":8.639999999999999},{"$f":"+SUM('HORAS PARADAS'!AM10:AP10)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!AQ10:AT10)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!AU10:AY10)","v":8.64},{"$f":"+SUM('HORAS PARADAS'!AZ10:BC10)","v":2.88}]
[0.15,{"$f":"+'HORAS PARADAS'!C11","v":"PLANTA DE CAL"},{"$f":"+SUM('HORAS PARADAS'!D11:G11)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!H11:K11)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!L11:P11)","v":1.8000000000000003},{"$f":"+SUM('HORAS PARADAS'!Q11:T11)","v":3},{"$f":"+SUM('HORAS PARADAS'!U11:Y11)","v":3},{"$f":"+SUM('HORAS PARADAS'!Z11:AC11)","v":3},{"$f":"+SUM('HORAS PARADAS'!AD11:AG11)","v":3},{"$f":"+SUM('HORAS PARADAS'!AH11:AL11)","v":3.6000000000000005},{"$f":"+SUM('HORAS PARADAS'!AM11:AP11)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AQ11:AT11)","v":3},{"$f":"+SUM('HORAS PARADAS'!AU11:AY11)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AZ11:BC11)","v":1.2000000000000002}]
[0.2,{"$f":"+'HORAS PARADAS'!C12","v":"ABASTECIMIENTO DE AGUA"},{"$f":"+SUM('HORAS PARADAS'!D12:G12)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!H12:K12)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L12:P12)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q12:T12)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!U12:Y12)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!Z12:AC12)","v":8.400000000000002},{"$f":"+SUM('HORAS PARADAS'!AD12:AG12)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AH12:AL12)","v":10.08},{"$f":"+SUM('HORAS PARADAS'!AM12:AP12)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ12:AT12)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AU12:AY12)","v":10.080000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ12:BC12)","v":3.3600000000000003}]
[0.1,{"$f":"+'HORAS PARADAS'!C13","v":"REACTIVOS"},{"$f":"+SUM('HORAS PARADAS'!D13:G13)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!H13:K13)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!L13:P13)","v":1.8000000000000003},{"$f":"+SUM('HORAS PARADAS'!Q13:T13)","v":3},{"$f":"+SUM('HORAS PARADAS'!U13:Y13)","v":3},{"$f":"+SUM('HORAS PARADAS'!Z13:AC13)","v":3},{"$f":"+SUM('HORAS PARADAS'!AD13:AG13)","v":3},{"$f":"+SUM('HORAS PARADAS'!AH13:AL13)","v":3.6000000000000005},{"$f":"+SUM('HORAS PARADAS'!AM13:AP13)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AQ13:AT13)","v":3},{"$f":"+SUM('HORAS PARADAS'!AU13:AY13)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AZ13:BC13)","v":1.2000000000000002}]
[null,{"$f":"+'HORAS PARADAS'!C14","v":"FLOTACION Pb"},{"$f":"+SUM('HORAS PARADAS'!D14:G14)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!H14:K14)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L14:P14)","v":3.6000000000000005},{"$f":"+SUM('HORAS PARADAS'!Q14:T14)","v":6},{"$f":"+SUM('HORAS PARADAS'!U14:Y14)","v":6},{"$f":"+SUM('HORAS PARADAS'!Z14:AC14)","v":6},{"$f":"+SUM('HORAS PARADAS'!AD14:AG14)","v":6},{"$f":"+SUM('HORAS PARADAS'!AH14:AL14)","v":7.200000000000001},{"$f":"+SUM('HORAS PARADAS'!AM14:AP14)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ14:AT14)","v":6},{"$f":"+SUM('HORAS PARADAS'!AU14:AY14)","v":7.2},{"$f":"+SUM('HORAS PARADAS'!AZ14:BC14)","v":2.4000000000000004}]
[null,{"$f":"+'HORAS PARADAS'!C15","v":"FLOTACION Cu"},{"$f":"+SUM('HORAS PARADAS'!D15:G15)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!H15:K15)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L15:P15)","v":3.6000000000000005},{"$f":"+SUM('HORAS PARADAS'!Q15:T15)","v":6},{"$f":"+SUM('HORAS PARADAS'!U15:Y15)","v":6},{"$f":"+SUM('HORAS PARADAS'!Z15:AC15)","v":6},{"$f":"+SUM('HORAS PARADAS'!AD15:AG15)","v":6},{"$f":"+SUM('HORAS PARADAS'!AH15:AL15)","v":7.200000000000001},{"$f":"+SUM('HORAS PARADAS'!AM15:AP15)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ15:AT15)","v":6},{"$f":"+SUM('HORAS PARADAS'!AU15:AY15)","v":7.2},{"$f":"+SUM('HORAS PARADAS'!AZ15:BC15)","v":2.4000000000000004}]
[null,{"$f":"+'HORAS PARADAS'!C16","v":"FLOTACION Zn"},{"$f":"+SUM('HORAS PARADAS'!D16:G16)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!H16:K16)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L16:P16)","v":3.6000000000000005},{"$f":"+SUM('HORAS PARADAS'!Q16:T16)","v":6},{"$f":"+SUM('HORAS PARADAS'!U16:Y16)","v":6},{"$f":"+SUM('HORAS PARADAS'!Z16:AC16)","v":6},{"$f":"+SUM('HORAS PARADAS'!AD16:AG16)","v":6},{"$f":"+SUM('HORAS PARADAS'!AH16:AL16)","v":7.200000000000001},{"$f":"+SUM('HORAS PARADAS'!AM16:AP16)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ16:AT16)","v":6},{"$f":"+SUM('HORAS PARADAS'!AU16:AY16)","v":7.2},{"$f":"+SUM('HORAS PARADAS'!AZ16:BC16)","v":2.4000000000000004}]
[null,{"$f":"+'HORAS PARADAS'!C17","v":"FLOTACION Bulk"},{"$f":"+SUM('HORAS PARADAS'!D17:G17)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!H17:K17)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L17:P17)","v":3.6000000000000005},{"$f":"+SUM('HORAS PARADAS'!Q17:T17)","v":6},{"$f":"+SUM('HORAS PARADAS'!U17:Y17)","v":6},{"$f":"+SUM('HORAS PARADAS'!Z17:AC17)","v":6},{"$f":"+SUM('HORAS PARADAS'!AD17:AG17)","v":6},{"$f":"+SUM('HORAS PARADAS'!AH17:AL17)","v":7.200000000000001},{"$f":"+SUM('HORAS PARADAS'!AM17:AP17)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ17:AT17)","v":6},{"$f":"+SUM('HORAS PARADAS'!AU17:AY17)","v":7.2},{"$f":"+SUM('HORAS PARADAS'!AZ17:BC17)","v":2.4000000000000004}]
[null,{"$f":"+'HORAS PARADAS'!C18","v":"ESPESADORES"},{"$f":"+SUM('HORAS PARADAS'!D18:G18)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!H18:K18)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L18:P18)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q18:T18)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!U18:Y18)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!Z18:AC18)","v":8.400000000000002},{"$f":"+SUM('HORAS PARADAS'!AD18:AG18)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AH18:AL18)","v":10.08},{"$f":"+SUM('HORAS PARADAS'!AM18:AP18)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ18:AT18)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AU18:AY18)","v":10.080000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ18:BC18)","v":3.3600000000000003}]
[null,{"$f":"+'HORAS PARADAS'!C19","v":"FILTRADO Pb"},{"$f":"+SUM('HORAS PARADAS'!D19:G19)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!H19:K19)","v":3.84},{"$f":"+SUM('HORAS PARADAS'!L19:P19)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!Q19:T19)","v":4.8},{"$f":"+SUM('HORAS PARADAS'!U19:Y19)","v":4.8},{"$f":"+SUM('HORAS PARADAS'!Z19:AC19)","v":4.8},{"$f":"+SUM('HORAS PARADAS'!AD19:AG19)","v":4.8},{"$f":"+SUM('HORAS PARADAS'!AH19:AL19)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!AM19:AP19)","v":3.84},{"$f":"+SUM('HORAS PARADAS'!AQ19:AT19)","v":4.8},{"$f":"+SUM('HORAS PARADAS'!AU19:AY19)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!AZ19:BC19)","v":1.92}]
[null,{"$f":"+'HORAS PARADAS'!C20","v":"FILTRADO Cu"},{"$f":"+SUM('HORAS PARADAS'!D20:G20)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!H20:K20)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L20:P20)","v":3.6000000000000005},{"$f":"+SUM('HORAS PARADAS'!Q20:T20)","v":6},{"$f":"+SUM('HORAS PARADAS'!U20:Y20)","v":6},{"$f":"+SUM('HORAS PARADAS'!Z20:AC20)","v":6},{"$f":"+SUM('HORAS PARADAS'!AD20:AG20)","v":6},{"$f":"+SUM('HORAS PARADAS'!AH20:AL20)","v":7.200000000000001},{"$f":"+SUM('HORAS PARADAS'!AM20:AP20)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ20:AT20)","v":6},{"$f":"+SUM('HORAS PARADAS'!AU20:AY20)","v":7.2},{"$f":"+SUM('HORAS PARADAS'!AZ20:BC20)","v":2.4000000000000004}]
[null,{"$f":"+'HORAS PARADAS'!C21","v":"FILTRADO Zn"},{"$f":"+SUM('HORAS PARADAS'!D21:G21)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!H21:K21)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L21:P21)","v":3.6000000000000005},{"$f":"+SUM('HORAS PARADAS'!Q21:T21)","v":6},{"$f":"+SUM('HORAS PARADAS'!U21:Y21)","v":6},{"$f":"+SUM('HORAS PARADAS'!Z21:AC21)","v":6},{"$f":"+SUM('HORAS PARADAS'!AD21:AG21)","v":6},{"$f":"+SUM('HORAS PARADAS'!AH21:AL21)","v":7.200000000000001},{"$f":"+SUM('HORAS PARADAS'!AM21:AP21)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ21:AT21)","v":6},{"$f":"+SUM('HORAS PARADAS'!AU21:AY21)","v":7.2},{"$f":"+SUM('HORAS PARADAS'!AZ21:BC21)","v":2.4000000000000004}]
[null,{"$f":"+'HORAS PARADAS'!C22","v":"FILTRADO Bulk"},{"$f":"+SUM('HORAS PARADAS'!D22:G22)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!H22:K22)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L22:P22)","v":3.6000000000000005},{"$f":"+SUM('HORAS PARADAS'!Q22:T22)","v":6},{"$f":"+SUM('HORAS PARADAS'!U22:Y22)","v":6},{"$f":"+SUM('HORAS PARADAS'!Z22:AC22)","v":6},{"$f":"+SUM('HORAS PARADAS'!AD22:AG22)","v":6},{"$f":"+SUM('HORAS PARADAS'!AH22:AL22)","v":7.200000000000001},{"$f":"+SUM('HORAS PARADAS'!AM22:AP22)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AQ22:AT22)","v":6},{"$f":"+SUM('HORAS PARADAS'!AU22:AY22)","v":7.2},{"$f":"+SUM('HORAS PARADAS'!AZ22:BC22)","v":2.4000000000000004}]
[null,{"$f":"+'HORAS PARADAS'!C23","v":"PLANTA DE NEUTRALIZACION"},{"$f":"+SUM('HORAS PARADAS'!D23:G23)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!H23:K23)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!L23:P23)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!Q23:T23)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!U23:Y23)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!Z23:AC23)","v":7.2},{"$f":"+SUM('HORAS PARADAS'!AD23:AG23)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!AH23:AL23)","v":8.639999999999999},{"$f":"+SUM('HORAS PARADAS'!AM23:AP23)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!AQ23:AT23)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!AU23:AY23)","v":8.64},{"$f":"+SUM('HORAS PARADAS'!AZ23:BC23)","v":2.88}]
[null,{"$f":"+'HORAS PARADAS'!C24","v":"BOMBAS DE RELAVE"},{"$f":"+SUM('HORAS PARADAS'!D24:G24)","v":6.4799999999999995},{"$f":"+SUM('HORAS PARADAS'!H24:K24)","v":8.64},{"$f":"+SUM('HORAS PARADAS'!L24:P24)","v":6.48},{"$f":"+SUM('HORAS PARADAS'!Q24:T24)","v":10.799999999999999},{"$f":"+SUM('HORAS PARADAS'!U24:Y24)","v":10.799999999999999},{"$f":"+SUM('HORAS PARADAS'!Z24:AC24)","v":10.8},{"$f":"+SUM('HORAS PARADAS'!AD24:AG24)","v":10.799999999999999},{"$f":"+SUM('HORAS PARADAS'!AH24:AL24)","v":12.96},{"$f":"+SUM('HORAS PARADAS'!AM24:AP24)","v":8.64},{"$f":"+SUM('HORAS PARADAS'!AQ24:AT24)","v":10.799999999999999},{"$f":"+SUM('HORAS PARADAS'!AU24:AY24)","v":12.96},{"$f":"+SUM('HORAS PARADAS'!AZ24:BC24)","v":4.32}]
[null,"HORAS PARADA PREVENTIVO",{"$f":"+SUM('HORAS PARADAS'!D25:G25)","v":72.00000000000001},{"$f":"+SUM('HORAS PARADAS'!H25:K25)","v":95.99999999999999},{"$f":"+SUM('HORAS PARADAS'!L25:P25)","v":71.99999999999999},{"$f":"+SUM('HORAS PARADAS'!Q25:T25)","v":120.00000000000001},{"$f":"+SUM('HORAS PARADAS'!U25:Y25)","v":120.00000000000001},{"$f":"+SUM('HORAS PARADAS'!Z25:AC25)","v":120},{"$f":"+SUM('HORAS PARADAS'!AD25:AG25)","v":120.00000000000001},{"$f":"+SUM('HORAS PARADAS'!AH25:AL25)","v":143.99999999999997},{"$f":"+SUM('HORAS PARADAS'!AM25:AP25)","v":95.99999999999999},{"$f":"+SUM('HORAS PARADAS'!AQ25:AT25)","v":120.00000000000001},{"$f":"+SUM('HORAS PARADAS'!AU25:AY25)","v":144},{"$f":"+SUM('HORAS PARADAS'!AZ25:BC25)","v":47.99999999999999}]
[null,"HORAS TOTAL MEJORA"]
[null,"HORAS OPERACIÓN",{"$f":"(24*C10-C31-C32)","v":672},{"$f":"(24*D10-D31)","v":576},{"$f":"(24*E10-E31)","v":672},{"$f":"(24*F10-F31)","v":600},{"$f":"(24*G10-G31)","v":624},{"$f":"(24*H10-H31)","v":600},624,600,624,624,576,696]
[null,"HORAS REPARACION",{"$f":"IFERROR(+(C$33/$J$1)*$M$1,0)","v":{"v":4.08,"d":"4"}},{"$f":"IFERROR(+(D$33/$J$1)*$M$1,0)","v":{"v":3.497142857142857,"d":"3"}},{"v":4.08,"d":"4"},{"v":3.642857142857143,"d":"4"},{"v":3.7885714285714287,"d":"4"},{"v":3.642857142857143,"d":"4"},{"v":3.7885714285714287,"d":"4"},{"v":3.642857142857143,"d":"4"},{"v":3.7885714285714287,"d":"4"},{"v":3.7885714285714287,"d":"4"},{"v":3.497142857142857,"d":"3"},{"v":4.225714285714286,"d":"4"}]
[]
[0.07,{"$f":"+B13","v":"CHANCADO PRIMARIO"},{"$f":"+$A36*C$34","v":{"v":0.2856,"d":"0.3"}},{"$f":"+$A36*D$34","v":{"v":0.24480000000000002,"d":"0.2"}},{"v":0.2856,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.24480000000000002,"d":"0.2"},{"v":0.29580000000000006,"d":"0.3"}]
[0.07,{"$f":"+B14","v":"CHANCADO SECUNDARIO"},{"v":0.2856,"d":"0.3"},{"$f":"+$A37*D$34","v":{"v":0.24480000000000002,"d":"0.2"}},{"v":0.2856,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.24480000000000002,"d":"0.2"},{"v":0.29580000000000006,"d":"0.3"}]
[0.07,"CHANCADO TERCIARIO",{"v":0.2856,"d":"0.3"},{"v":0.24480000000000002,"d":"0.2"},{"v":0.2856,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.24480000000000002,"d":"0.2"},{"v":0.29580000000000006,"d":"0.3"}]
[0.06,"MOLIENDA",{"v":0.2448,"d":"0.2"},{"v":0.2098285714285714,"d":"0.2"},{"v":0.2448,"d":"0.2"},{"v":0.21857142857142856,"d":"0.2"},{"v":0.22731428571428572,"d":"0.2"},{"v":0.21857142857142856,"d":"0.2"},{"v":0.22731428571428572,"d":"0.2"},{"v":0.21857142857142856,"d":"0.2"},{"v":0.22731428571428572,"d":"0.2"},{"v":0.22731428571428572,"d":"0.2"},{"v":0.2098285714285714,"d":"0.2"},{"v":0.2535428571428571,"d":"0.3"}]
[0.025,"PLANTA DE CAL",{"v":0.10200000000000001,"d":"0.1"},{"v":0.08742857142857142,"d":"0.1"},{"v":0.10200000000000001,"d":"0.1"},{"v":0.09107142857142858,"d":"0.1"},{"v":0.09471428571428572,"d":"0.1"},{"v":0.09107142857142858,"d":"0.1"},{"v":0.09471428571428572,"d":"0.1"},{"v":0.09107142857142858,"d":"0.1"},{"v":0.09471428571428572,"d":"0.1"},{"v":0.09471428571428572,"d":"0.1"},{"v":0.08742857142857142,"d":"0.1"},{"v":0.10564285714285715,"d":"0.1"}]
[0.07,"ABASTECIMIENTO DE AGUA",{"v":0.2856,"d":"0.3"},{"$f":"+$A41*D$34","v":{"v":0.24480000000000002,"d":"0.2"}},{"v":0.2856,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.24480000000000002,"d":"0.2"},{"v":0.29580000000000006,"d":"0.3"}]
[0.025,"REACTIVOS",{"v":0.10200000000000001,"d":"0.1"},{"v":0.08742857142857142,"d":"0.1"},{"v":0.10200000000000001,"d":"0.1"},{"v":0.09107142857142858,"d":"0.1"},{"v":0.09471428571428572,"d":"0.1"},{"v":0.09107142857142858,"d":"0.1"},{"v":0.09471428571428572,"d":"0.1"},{"v":0.09107142857142858,"d":"0.1"},{"v":0.09471428571428572,"d":"0.1"},{"v":0.09471428571428572,"d":"0.1"},{"v":0.08742857142857142,"d":"0.1"},{"v":0.10564285714285715,"d":"0.1"}]
[0.05,"FLOTACION Pb",{"v":0.20400000000000001,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.2112857142857143,"d":"0.2"}]
[0.05,"FLOTACION Cu",{"v":0.20400000000000001,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.2112857142857143,"d":"0.2"}]
[0.05,"FLOTACION Zn",{"v":0.20400000000000001,"d":"0.2"},{"$f":"+$A45*D$34","v":{"v":0.17485714285714285,"d":"0.2"}},{"v":0.20400000000000001,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.2112857142857143,"d":"0.2"}]
[0.05,"FLOTACION Bulk",{"v":0.20400000000000001,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.2112857142857143,"d":"0.2"}]
[0.07,"ESPESADORES",{"v":0.2856,"d":"0.3"},{"v":0.24480000000000002,"d":"0.2"},{"v":0.2856,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.255,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.26520000000000005,"d":"0.3"},{"v":0.24480000000000002,"d":"0.2"},{"v":0.29580000000000006,"d":"0.3"}]
[0.04,"FILTRADO Pb",{"v":0.1632,"d":"0.2"},{"v":0.13988571428571428,"d":"0.1"},{"v":0.1632,"d":"0.2"},{"v":0.1457142857142857,"d":"0.1"},{"v":0.15154285714285715,"d":"0.2"},{"v":0.1457142857142857,"d":"0.1"},{"v":0.15154285714285715,"d":"0.2"},{"v":0.1457142857142857,"d":"0.1"},{"v":0.15154285714285715,"d":"0.2"},{"v":0.15154285714285715,"d":"0.2"},{"v":0.13988571428571428,"d":"0.1"},{"v":0.16902857142857144,"d":"0.2"}]
[0.05,"FILTRADO Cu",{"v":0.20400000000000001,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.2112857142857143,"d":"0.2"}]
[0.05,"FILTRADO Zn",{"v":0.20400000000000001,"d":"0.2"},{"$f":"+$A50*D$34","v":{"v":0.17485714285714285,"d":"0.2"}},{"v":0.20400000000000001,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.2112857142857143,"d":"0.2"}]
[0.05,"FILTRADO Bulk",{"v":0.20400000000000001,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18214285714285716,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.18942857142857145,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.2112857142857143,"d":"0.2"}]
[0.06,"PLANTA DE NEUTRALIZACION",{"v":0.2448,"d":"0.2"},{"v":0.2098285714285714,"d":"0.2"},{"v":0.2448,"d":"0.2"},{"v":0.21857142857142856,"d":"0.2"},{"v":0.22731428571428572,"d":"0.2"},{"v":0.21857142857142856,"d":"0.2"},{"v":0.22731428571428572,"d":"0.2"},{"v":0.21857142857142856,"d":"0.2"},{"v":0.22731428571428572,"d":"0.2"},{"v":0.22731428571428572,"d":"0.2"},{"v":0.2098285714285714,"d":"0.2"},{"v":0.2535428571428571,"d":"0.3"}]
[0.09,"BOMBAS DE RELAVE",{"v":0.36719999999999997,"d":"0.4"},{"v":0.3147428571428571,"d":"0.3"},{"v":0.36719999999999997,"d":"0.4"},{"v":0.32785714285714285,"d":"0.3"},{"v":0.3409714285714286,"d":"0.3"},{"v":0.32785714285714285,"d":"0.3"},{"v":0.3409714285714286,"d":"0.3"},{"v":0.32785714285714285,"d":"0.3"},{"v":0.3409714285714286,"d":"0.3"},{"v":0.3409714285714286,"d":"0.3"},{"v":0.3147428571428571,"d":"0.3"},{"v":0.3803142857142857,"d":"0.4"}]
[null,"HORAS PARADA CORRECTIVO",{"$f":"C36+C37+C38+C39+C40+C41+C42+IFERROR(1/(IFERROR(1/C43,0)+IFERROR(1/C44,0)+IFERROR(1/C45,0)+IFERROR(1/C46,0)),0)+C47+IFERROR(1/(IFERROR(1/C48,0)+IFERROR(1/C49,0)+IFERROR(1/C50,0)+IFERROR(1/C51,0)),0)+C52+C53","v":{"v":2.5878,"d":"2.59"}},{"$f":"D36+D37+D38+D39+D40+D41+D42+IFERROR(1/(IFERROR(1/D43,0)+IFERROR(1/D44,0)+IFERROR(1/D45,0)+IFERROR(1/D46,0)),0)+D47+IFERROR(1/(IFERROR(1/D48,0)+IFERROR(1/D49,0)+IFERROR(1/D50,0)+IFERROR(1/D51,0)),0)+D52+D53","v":{"v":2.218114285714286,"d":"2.22"}},{"v":2.5878,"d":"2.59"},{"v":2.310535714285714,"d":"2.31"},{"v":2.4029571428571432,"d":"2.40"},{"v":2.310535714285714,"d":"2.31"},{"v":2.4029571428571432,"d":"2.40"},{"v":2.310535714285714,"d":"2.31"},{"v":2.4029571428571432,"d":"2.40"},{"v":2.4029571428571432,"d":"2.40"},{"v":2.218114285714286,"d":"2.22"},{"v":2.680221428571429,"d":"2.68"}]
[null,null,{"$f":"+C10","v":31},{"$f":"+D10","v":28},31,30,31,30,31,31,30,31,30,31]
[null,"HORAS PROYECTADAS",{"$f":"+C11","v":"2024-01-01"},"2024-02-01","2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01"]
[0.2,"TOTAL",{"$f":"+C10*24","v":744},{"$f":"+D10*24","v":672},744,720,744,720,744,744,720,744,720,744]
[0.2,{"$f":"+B13","v":"CHANCADO PRIMARIO"},{"$f":"+SUM('HORAS PARADAS'!D31:G31)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H31:K31)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L31:P31)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q31:T31)","v":0},{"$f":"+SUM('HORAS PARADAS'!U31:Y31)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z31:AC31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD31:AG31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH31:AL31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM31:AP31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ31:AT31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU31:AY31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ31:BC31)","v":0}]
[0.2,"CHANCADO SECUNDARIO",{"$f":"+SUM('HORAS PARADAS'!D32:G32)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H32:K32)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L32:P32)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q32:T32)","v":0},{"$f":"+SUM('HORAS PARADAS'!U32:Y32)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z32:AC32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD32:AG32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH32:AL32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM32:AP32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ32:AT32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU32:AY32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ32:BC32)","v":0}]
[0.1,"CHANCADO TERCIARIO",{"$f":"+SUM('HORAS PARADAS'!D33:G33)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H33:K33)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L33:P33)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q33:T33)","v":0},{"$f":"+SUM('HORAS PARADAS'!U33:Y33)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z33:AC33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD33:AG33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH33:AL33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM33:AP33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ33:AT33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU33:AY33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ33:BC33)","v":0}]
[0.05,"MOLIENDA",{"$f":"+SUM('HORAS PARADAS'!D34:G34)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!H34:K34)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!L34:P34)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!Q34:T34)","v":0},{"$f":"+SUM('HORAS PARADAS'!U34:Y34)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z34:AC34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD34:AG34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH34:AL34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM34:AP34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ34:AT34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU34:AY34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ34:BC34)","v":0}]
[0.15,"PLANTA DE CAL",{"$f":"+SUM('HORAS PARADAS'!D35:G35)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!H35:K35)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!L35:P35)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!Q35:T35)","v":0},{"$f":"+SUM('HORAS PARADAS'!U35:Y35)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z35:AC35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD35:AG35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH35:AL35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM35:AP35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ35:AT35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU35:AY35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ35:BC35)","v":0}]
[0.2,"ABASTECIMIENTO DE AGUA",{"$f":"+SUM('HORAS PARADAS'!D36:G36)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H36:K36)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L36:P36)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q36:T36)","v":0},{"$f":"+SUM('HORAS PARADAS'!U36:Y36)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z36:AC36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD36:AG36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH36:AL36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM36:AP36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ36:AT36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU36:AY36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ36:BC36)","v":0}]
[0.1,"REACTIVOS",{"$f":"+SUM('HORAS PARADAS'!D37:G37)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!H37:K37)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!L37:P37)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!Q37:T37)","v":0},{"$f":"+SUM('HORAS PARADAS'!U37:Y37)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z37:AC37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD37:AG37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH37:AL37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM37:AP37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ37:AT37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU37:AY37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ37:BC37)","v":0}]
[null,"FLOTACION Pb",{"$f":"+SUM('HORAS PARADAS'!D38:G38)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!H38:K38)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L38:P38)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!Q38:T38)","v":0},{"$f":"+SUM('HORAS PARADAS'!U38:Y38)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z38:AC38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD38:AG38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH38:AL38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM38:AP38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ38:AT38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU38:AY38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ38:BC38)","v":0}]
[null,"FLOTACION Cu",{"$f":"+SUM('HORAS PARADAS'!D39:G39)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!H39:K39)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L39:P39)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!Q39:T39)","v":0},{"$f":"+SUM('HORAS PARADAS'!U39:Y39)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z39:AC39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD39:AG39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH39:AL39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM39:AP39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ39:AT39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU39:AY39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ39:BC39)","v":0}]
[null,"FLOTACION Zn",{"$f":"+SUM('HORAS PARADAS'!D40:G40)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!H40:K40)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L40:P40)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!Q40:T40)","v":0},{"$f":"+SUM('HORAS PARADAS'!U40:Y40)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z40:AC40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD40:AG40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH40:AL40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM40:AP40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ40:AT40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU40:AY40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ40:BC40)","v":0}]
[null,"FLOTACION Bulk",{"$f":"+SUM('HORAS PARADAS'!D41:G41)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!H41:K41)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L41:P41)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!Q41:T41)","v":0},{"$f":"+SUM('HORAS PARADAS'!U41:Y41)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z41:AC41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD41:AG41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH41:AL41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM41:AP41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ41:AT41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU41:AY41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ41:BC41)","v":0}]
[null,"ESPESADORES",{"$f":"+SUM('HORAS PARADAS'!D42:G42)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H42:K42)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L42:P42)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q42:T42)","v":0},{"$f":"+SUM('HORAS PARADAS'!U42:Y42)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z42:AC42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD42:AG42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH42:AL42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM42:AP42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ42:AT42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU42:AY42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ42:BC42)","v":0}]
[null,"FILTRADO Pb",{"$f":"+SUM('HORAS PARADAS'!D43:G43)","v":3.84},{"$f":"+SUM('HORAS PARADAS'!H43:K43)","v":3.84},{"$f":"+SUM('HORAS PARADAS'!L43:P43)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!Q43:T43)","v":0},{"$f":"+SUM('HORAS PARADAS'!U43:Y43)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z43:AC43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD43:AG43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH43:AL43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM43:AP43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ43:AT43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU43:AY43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ43:BC43)","v":0}]
[null,"FILTRADO Cu",{"$f":"+SUM('HORAS PARADAS'!D44:G44)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!H44:K44)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L44:P44)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!Q44:T44)","v":0},{"$f":"+SUM('HORAS PARADAS'!U44:Y44)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z44:AC44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD44:AG44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH44:AL44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM44:AP44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ44:AT44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU44:AY44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ44:BC44)","v":0}]
[null,"FILTRADO Zn",{"$f":"+SUM('HORAS PARADAS'!D45:G45)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!H45:K45)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L45:P45)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!Q45:T45)","v":0},{"$f":"+SUM('HORAS PARADAS'!U45:Y45)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z45:AC45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD45:AG45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH45:AL45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM45:AP45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ45:AT45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU45:AY45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ45:BC45)","v":0}]
[null,"FILTRADO Bulk",{"$f":"+SUM('HORAS PARADAS'!D46:G46)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!H46:K46)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!L46:P46)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!Q46:T46)","v":0},{"$f":"+SUM('HORAS PARADAS'!U46:Y46)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z46:AC46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD46:AG46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH46:AL46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM46:AP46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ46:AT46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU46:AY46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ46:BC46)","v":0}]
[null,"PLANTA DE NEUTRALIZACION",{"$f":"+SUM('HORAS PARADAS'!D47:G47)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!H47:K47)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!L47:P47)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!Q47:T47)","v":0},{"$f":"+SUM('HORAS PARADAS'!U47:Y47)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z47:AC47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD47:AG47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH47:AL47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM47:AP47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ47:AT47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU47:AY47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ47:BC47)","v":0}]
[null,"BOMBAS DE RELAVE",{"$f":"+SUM('HORAS PARADAS'!D48:G48)","v":8.64},{"$f":"+SUM('HORAS PARADAS'!H48:K48)","v":8.64},{"$f":"+SUM('HORAS PARADAS'!L48:P48)","v":6.4799999999999995},{"$f":"+SUM('HORAS PARADAS'!Q48:T48)","v":0},{"$f":"+SUM('HORAS PARADAS'!U48:Y48)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z48:AC48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD48:AG48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH48:AL48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM48:AP48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ48:AT48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU48:AY48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ48:BC48)","v":0}]
[null,"HORAS PARADA PREVENTIVO",{"$f":"+SUM('HORAS PARADAS'!D49:G49)","v":95.99999999999999},{"$f":"+SUM('HORAS PARADAS'!H49:K49)","v":95.99999999999999},{"$f":"+SUM('HORAS PARADAS'!L49:P49)","v":72.00000000000001},{"$f":"+SUM('HORAS PARADAS'!Q49:T49)","v":0},{"$f":"+SUM('HORAS PARADAS'!U49:Y49)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z49:AC49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD49:AG49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH49:AL49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM49:AP49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ49:AT49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU49:AY49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ49:BC49)","v":0}]
[null,"HORAS TOTAL MEJORA"]
[null,"HORAS OPERACIÓN",{"$f":"(24*C10-C76-C77)","v":648},{"$f":"(24*D10-D76-D77)","v":576},672,720,744,720,744,744,720,744,720,744]
[null,"HORAS REPARACION",{"$f":"IFERROR(+(C$78/$J$1)*$M$1,0)","v":{"v":3.9342857142857146,"d":"4"}},{"$f":"IFERROR(+(D$78/$J$1)*$M$1,0)","v":{"v":3.497142857142857,"d":"3"}},{"v":4.08,"d":"4"},{"v":4.371428571428572,"d":"4"},{"v":4.517142857142857,"d":"5"},{"v":4.371428571428572,"d":"4"},{"v":4.517142857142857,"d":"5"},{"v":4.517142857142857,"d":"5"},{"v":4.371428571428572,"d":"4"},{"v":4.517142857142857,"d":"5"},{"v":4.371428571428572,"d":"4"},{"v":4.517142857142857,"d":"5"}]
[]
[{"$f":"+A36","v":0.07},{"$f":"+B58","v":"CHANCADO PRIMARIO"},{"$f":"+$A81*C$79","v":{"v":0.27540000000000003,"d":"0.3"}},{"$f":"+$A81*D$79","v":{"v":0.24480000000000002,"d":"0.2"}},{"v":0.2856,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"}]
[{"$f":"+A37","v":0.07},{"$f":"+B59","v":"CHANCADO SECUNDARIO"},{"$f":"+$A82*C$79","v":{"v":0.27540000000000003,"d":"0.3"}},{"v":0.24480000000000002,"d":"0.2"},{"v":0.2856,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"}]
[0.07,"CHANCADO TERCIARIO",{"v":0.27540000000000003,"d":"0.3"},{"v":0.24480000000000002,"d":"0.2"},{"v":0.2856,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"}]
[0.06,"MOLIENDA",{"v":0.23605714285714285,"d":"0.2"},{"v":0.2098285714285714,"d":"0.2"},{"v":0.2448,"d":"0.2"},{"v":0.2622857142857143,"d":"0.3"},{"v":0.2710285714285714,"d":"0.3"},{"v":0.2622857142857143,"d":"0.3"},{"v":0.2710285714285714,"d":"0.3"},{"v":0.2710285714285714,"d":"0.3"},{"v":0.2622857142857143,"d":"0.3"},{"v":0.2710285714285714,"d":"0.3"},{"v":0.2622857142857143,"d":"0.3"},{"v":0.2710285714285714,"d":"0.3"}]
[0.025,"PLANTA DE CAL",{"v":0.09835714285714287,"d":"0.1"},{"v":0.08742857142857142,"d":"0.1"},{"v":0.10200000000000001,"d":"0.1"},{"v":0.1092857142857143,"d":"0.1"},{"v":0.11292857142857143,"d":"0.1"},{"v":0.1092857142857143,"d":"0.1"},{"v":0.11292857142857143,"d":"0.1"},{"v":0.11292857142857143,"d":"0.1"},{"v":0.1092857142857143,"d":"0.1"},{"v":0.11292857142857143,"d":"0.1"},{"v":0.1092857142857143,"d":"0.1"},{"v":0.11292857142857143,"d":"0.1"}]
[0.07,"ABASTECIMIENTO DE AGUA",{"v":0.27540000000000003,"d":"0.3"},{"v":0.24480000000000002,"d":"0.2"},{"v":0.2856,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"}]
[0.025,"REACTIVOS",{"v":0.09835714285714287,"d":"0.1"},{"v":0.08742857142857142,"d":"0.1"},{"v":0.10200000000000001,"d":"0.1"},{"v":0.1092857142857143,"d":"0.1"},{"v":0.11292857142857143,"d":"0.1"},{"v":0.1092857142857143,"d":"0.1"},{"v":0.11292857142857143,"d":"0.1"},{"v":0.11292857142857143,"d":"0.1"},{"v":0.1092857142857143,"d":"0.1"},{"v":0.11292857142857143,"d":"0.1"},{"v":0.1092857142857143,"d":"0.1"},{"v":0.11292857142857143,"d":"0.1"}]
[0.05,"FLOTACION Pb",{"v":0.19671428571428573,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"}]
[0.05,"FLOTACION Cu",{"v":0.19671428571428573,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"}]
[0.05,"FLOTACION Zn",{"v":0.19671428571428573,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"}]
[0.05,"FLOTACION Bulk",{"v":0.19671428571428573,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"}]
[0.07,"ESPESADORES",{"v":0.27540000000000003,"d":"0.3"},{"v":0.24480000000000002,"d":"0.2"},{"v":0.2856,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"},{"v":0.30600000000000005,"d":"0.3"},{"v":0.31620000000000004,"d":"0.3"}]
[0.04,"FILTRADO Pb",{"v":0.15737142857142858,"d":"0.2"},{"v":0.13988571428571428,"d":"0.1"},{"v":0.1632,"d":"0.2"},{"v":0.17485714285714288,"d":"0.2"},{"v":0.18068571428571428,"d":"0.2"},{"v":0.17485714285714288,"d":"0.2"},{"v":0.18068571428571428,"d":"0.2"},{"v":0.18068571428571428,"d":"0.2"},{"v":0.17485714285714288,"d":"0.2"},{"v":0.18068571428571428,"d":"0.2"},{"v":0.17485714285714288,"d":"0.2"},{"v":0.18068571428571428,"d":"0.2"}]
[0.05,"FILTRADO Cu",{"v":0.19671428571428573,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"}]
[0.05,"FILTRADO Zn",{"v":0.19671428571428573,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"}]
[0.05,"FILTRADO Bulk",{"v":0.19671428571428573,"d":"0.2"},{"v":0.17485714285714285,"d":"0.2"},{"v":0.20400000000000001,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"},{"v":0.2185714285714286,"d":"0.2"},{"v":0.22585714285714287,"d":"0.2"}]
[0.06,"PLANTA DE NEUTRALIZACION",{"v":0.23605714285714285,"d":"0.2"},{"v":0.2098285714285714,"d":"0.2"},{"v":0.2448,"d":"0.2"},{"v":0.2622857142857143,"d":"0.3"},{"v":0.2710285714285714,"d":"0.3"},{"v":0.2622857142857143,"d":"0.3"},{"v":0.2710285714285714,"d":"0.3"},{"v":0.2710285714285714,"d":"0.3"},{"v":0.2622857142857143,"d":"0.3"},{"v":0.2710285714285714,"d":"0.3"},{"v":0.2622857142857143,"d":"0.3"},{"v":0.2710285714285714,"d":"0.3"}]
[0.09,"BOMBAS DE RELAVE",{"v":0.3540857142857143,"d":"0.4"},{"v":0.3147428571428571,"d":"0.3"},{"v":0.36719999999999997,"d":"0.4"},{"v":0.39342857142857146,"d":"0.4"},{"v":0.4065428571428571,"d":"0.4"},{"v":0.39342857142857146,"d":"0.4"},{"v":0.4065428571428571,"d":"0.4"},{"v":0.4065428571428571,"d":"0.4"},{"v":0.39342857142857146,"d":"0.4"},{"v":0.4065428571428571,"d":"0.4"},{"v":0.39342857142857146,"d":"0.4"},{"v":0.4065428571428571,"d":"0.4"}]
[null,"HORAS PARADA CORRECTIVO",{"$f":"C81+C82+C83+C84+C85+C86+C87+IFERROR(1/(IFERROR(1/C88,0)+IFERROR(1/C89,0)+IFERROR(1/C90,0)+IFERROR(1/C91,0)),0)+C92+IFERROR(1/(IFERROR(1/C93,0)+IFERROR(1/C94,0)+IFERROR(1/C95,0)+IFERROR(1/C96,0)),0)+C97+C98","v":{"v":2.4953785714285712,"d":"2.50"}},{"$f":"D81+D82+D83+D84+D85+D86+D87+IFERROR(1/(IFERROR(1/D88,0)+IFERROR(1/D89,0)+IFERROR(1/D90,0)+IFERROR(1/D91,0)),0)+D92+IFERROR(1/(IFERROR(1/D93,0)+IFERROR(1/D94,0)+IFERROR(1/D95,0)+IFERROR(1/D96,0)),0)+D97+D98","v":{"v":2.218114285714286,"d":"2.22"}},{"v":2.5878,"d":"2.59"},{"v":2.7726428571428574,"d":"2.77"},{"v":2.865064285714286,"d":"2.87"},{"v":2.7726428571428574,"d":"2.77"},{"v":2.865064285714286,"d":"2.87"},{"v":2.865064285714286,"d":"2.87"},{"v":2.7726428571428574,"d":"2.77"},{"v":2.865064285714286,"d":"2.87"},{"v":2.7726428571428574,"d":"2.77"},{"v":2.865064285714286,"d":"2.87"}]
[]
[null,"HORAS REALES",{"$f":"+C56","v":"2024-01-01"},"2024-02-01","2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01"]
[0.2,"TOTAL",{"$f":"+C55*24","v":744},{"$f":"+D55*24","v":672},744,720,744,720,744,744,720,744,720,744]
[null,{"$f":"+B58","v":"CHANCADO PRIMARIO"},{"$f":"+SUM('HORAS PARADAS'!D55:G55)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H55:K55)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L55:P55)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q55:T55)","v":0},{"$f":"+SUM('HORAS PARADAS'!U55:Y55)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z55:AC55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD55:AG55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH55:AL55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM55:AP55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ55:AT55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU55:AY55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ55:BC55)","v":0}]
[0.2,"CHANCADO SECUNDARIO",{"$f":"+SUM('HORAS PARADAS'!D56:G56)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H56:K56)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L56:P56)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q56:T56)","v":0},{"$f":"+SUM('HORAS PARADAS'!U56:Y56)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z56:AC56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD56:AG56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH56:AL56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM56:AP56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ56:AT56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU56:AY56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ56:BC56)","v":0}]
[0.2,"CHANCADO TERCIARIO",{"$f":"+SUM('HORAS PARADAS'!D57:G57)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H57:K57)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L57:P57)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q57:T57)","v":0},{"$f":"+SUM('HORAS PARADAS'!U57:Y57)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z57:AC57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD57:AG57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH57:AL57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM57:AP57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ57:AT57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU57:AY57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ57:BC57)","v":0}]
[0.1,"MOLIENDA",{"$f":"+SUM('HORAS PARADAS'!D58:G58)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H58:K58)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L58:P58)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q58:T58)","v":0},{"$f":"+SUM('HORAS PARADAS'!U58:Y58)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z58:AC58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD58:AG58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH58:AL58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM58:AP58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ58:AT58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU58:AY58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ58:BC58)","v":0}]
[0.05,"PLANTA DE CAL",{"$f":"+SUM('HORAS PARADAS'!D59:G59)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H59:K59)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L59:P59)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q59:T59)","v":0},{"$f":"+SUM('HORAS PARADAS'!U59:Y59)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z59:AC59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD59:AG59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH59:AL59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM59:AP59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ59:AT59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU59:AY59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ59:BC59)","v":0}]
[0.15,"ABASTECIMIENTO DE AGUA",{"$f":"+SUM('HORAS PARADAS'!D60:G60)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H60:K60)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L60:P60)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q60:T60)","v":0},{"$f":"+SUM('HORAS PARADAS'!U60:Y60)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z60:AC60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD60:AG60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH60:AL60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM60:AP60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ60:AT60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU60:AY60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ60:BC60)","v":0}]
[0.2,"REACTIVOS",{"$f":"+SUM('HORAS PARADAS'!D61:G61)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H61:K61)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L61:P61)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q61:T61)","v":0},{"$f":"+SUM('HORAS PARADAS'!U61:Y61)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z61:AC61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD61:AG61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH61:AL61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM61:AP61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ61:AT61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU61:AY61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ61:BC61)","v":0}]
[0.1,"FLOTACION Pb",{"$f":"+SUM('HORAS PARADAS'!D62:G62)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H62:K62)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L62:P62)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q62:T62)","v":0},{"$f":"+SUM('HORAS PARADAS'!U62:Y62)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z62:AC62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD62:AG62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH62:AL62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM62:AP62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ62:AT62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU62:AY62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ62:BC62)","v":0}]
[null,"FLOTACION Cu",{"$f":"+SUM('HORAS PARADAS'!D63:G63)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H63:K63)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L63:P63)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q63:T63)","v":0},{"$f":"+SUM('HORAS PARADAS'!U63:Y63)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z63:AC63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD63:AG63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH63:AL63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM63:AP63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ63:AT63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU63:AY63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ63:BC63)","v":0}]
[null,"FLOTACION Zn",{"$f":"+SUM('HORAS PARADAS'!D64:G64)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H64:K64)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L64:P64)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q64:T64)","v":0},{"$f":"+SUM('HORAS PARADAS'!U64:Y64)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z64:AC64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD64:AG64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH64:AL64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM64:AP64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ64:AT64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU64:AY64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ64:BC64)","v":0}]
[null,"FLOTACION Bulk",{"$f":"+SUM('HORAS PARADAS'!D65:G65)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H65:K65)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L65:P65)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q65:T65)","v":0},{"$f":"+SUM('HORAS PARADAS'!U65:Y65)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z65:AC65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD65:AG65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH65:AL65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM65:AP65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ65:AT65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU65:AY65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ65:BC65)","v":0}]
[null,"ESPESADORES",{"$f":"+SUM('HORAS PARADAS'!D66:G66)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H66:K66)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L66:P66)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q66:T66)","v":0},{"$f":"+SUM('HORAS PARADAS'!U66:Y66)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z66:AC66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD66:AG66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH66:AL66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM66:AP66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ66:AT66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU66:AY66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ66:BC66)","v":0}]
[null,"FILTRADO Pb",{"$f":"+SUM('HORAS PARADAS'!D67:G67)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H67:K67)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L67:P67)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q67:T67)","v":0},{"$f":"+SUM('HORAS PARADAS'!U67:Y67)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z67:AC67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD67:AG67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH67:AL67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM67:AP67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ67:AT67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU67:AY67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ67:BC67)","v":0}]
[null,"FILTRADO Cu",{"$f":"+SUM('HORAS PARADAS'!D68:G68)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H68:K68)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L68:P68)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q68:T68)","v":0},{"$f":"+SUM('HORAS PARADAS'!U68:Y68)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z68:AC68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD68:AG68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH68:AL68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM68:AP68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ68:AT68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU68:AY68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ68:BC68)","v":0}]
[null,"FILTRADO Zn",{"$f":"+SUM('HORAS PARADAS'!D69:G69)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H69:K69)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L69:P69)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q69:T69)","v":0},{"$f":"+SUM('HORAS PARADAS'!U69:Y69)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z69:AC69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD69:AG69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH69:AL69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM69:AP69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ69:AT69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU69:AY69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ69:BC69)","v":0}]
[null,"FILTRADO Bulk",{"$f":"+SUM('HORAS PARADAS'!D70:G70)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H70:K70)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L70:P70)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q70:T70)","v":0},{"$f":"+SUM('HORAS PARADAS'!U70:Y70)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z70:AC70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD70:AG70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH70:AL70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM70:AP70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ70:AT70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU70:AY70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ70:BC70)","v":0}]
[null,"PLANTA DE NEUTRALIZACION",{"$f":"+SUM('HORAS PARADAS'!D71:G71)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H71:K71)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L71:P71)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q71:T71)","v":0},{"$f":"+SUM('HORAS PARADAS'!U71:Y71)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z71:AC71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD71:AG71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH71:AL71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM71:AP71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ71:AT71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU71:AY71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ71:BC71)","v":0}]
[null,"BOMBAS DE RELAVE",{"$f":"+SUM('HORAS PARADAS'!D72:G72)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!H72:K72)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!L72:P72)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!Q72:T72)","v":0},{"$f":"+SUM('HORAS PARADAS'!U72:Y72)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z72:AC72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD72:AG72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH72:AL72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM72:AP72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ72:AT72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU72:AY72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ72:BC72)","v":0}]
[null,"HORAS PARADA PREVENTIVO",{"$f":"+SUM('HORAS PARADAS'!D73:G73)","v":120.96},{"$f":"+SUM('HORAS PARADAS'!H73:K73)","v":120.96},{"$f":"+SUM('HORAS PARADAS'!L73:P73)","v":90.72000000000003},{"$f":"+SUM('HORAS PARADAS'!Q73:T73)","v":0},{"$f":"+SUM('HORAS PARADAS'!U73:Y73)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z73:AC73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD73:AG73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH73:AL73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM73:AP73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ73:AT73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU73:AY73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ73:BC73)","v":0}]
[null,"HORAS TOTAL MEJORA"]
[null,"HORAS OPERACIÓN",{"$f":"(24*C10-C121-C122)","v":{"v":623.04,"d":"623"}},{"$f":"(24*D10-D121-D122)","v":{"v":551.04,"d":"551"}},{"v":653.28,"d":"653"},720,744,720,744,744,720,744,720,744]
[null,"HORAS REPARACION",{"$f":"+C144","v":{"v":57.91287878787878,"d":"58"}},{"$f":"+D144","v":{"v":21.243589743589745,"d":"21"}},0,0,0,0,0,0,0,0,0,0]
[]
[{"$f":"+A35","v":0},{"$f":"+B103","v":"CHANCADO PRIMARIO"},{"v":2,"d":"2.0"}]
[{"$f":"+A36","v":0.07},"CHANCADO SECUNDARIO",{"v":6,"d":"6.0"},{"v":7,"d":"7.0"}]
[{"$f":"+A37","v":0.07},"CHANCADO TERCIARIO",{"v":15,"d":"15.0"},{"v":3,"d":"3.0"}]
[0.07,"MOLIENDA",{"v":12,"d":"12.0"},{"v":2,"d":"2.0"}]
[0.06,"PLANTA DE CAL"]
[0.025,"ABASTECIMIENTO DE AGUA",{"v":13,"d":"13.0"}]
[0.07,"REACTIVOS",{"v":5,"d":"5.0"}]
[0.025,"FLOTACION Pb",{"v":3,"d":"3.0"}]
[0.05,"FLOTACION Cu"]
[0.05,"FLOTACION Zn",{"v":9,"d":"9.0"},{"v":5,"d":"5.0"}]
[0.05,"FLOTACION Bulk"]
[0.05,"ESPESADORES",{"v":2,"d":"2.0"}]
[0.07,"FILTRADO Pb",{"v":5,"d":"5.0"},{"v":4,"d":"4.0"}]
[0.04,"FILTRADO Cu",{"v":1,"d":"1.0"}]
[0.05,"FILTRADO Zn",{"v":1,"d":"1.0"}]
[0.05,"FILTRADO Bulk"]
[0.05,"PLANTA DE NEUTRALIZACION",{"v":6,"d":"6.0"},{"v":6,"d":"6.0"}]
[0.06,"BOMBAS DE RELAVE",{"v":24,"d":"24.0"},{"v":13,"d":"13.0"}]
[0.09,"HORAS PARADA CORRECTIVO",{"$f":"C126+C127+C128+C129+C130+C131+C132+IFERROR(1/(IFERROR(1/C133,0)+IFERROR(1/C134,0)+IFERROR(1/C135,0)+IFERROR(1/C136,0)),0)+C137+IFERROR(1/(IFERROR(1/C138,0)+IFERROR(1/C139,0)+IFERROR(1/C140,0)+IFERROR(1/C141,0)),0)+IFERROR(1/C142,0)+IFERROR(1/C143,0)","v":{"v":57.91287878787878,"d":"57.91"}},{"$f":"D126+D127+D128+D129+D130+D131+D132+IFERROR(1/(IFERROR(1/D133,0)+IFERROR(1/D134,0)+IFERROR(1/D135,0)+IFERROR(1/D136,0)),0)+D137+IFERROR(1/(IFERROR(1/D138,0)+IFERROR(1/D139,0)+IFERROR(1/D140,0)+IFERROR(1/D141,0)),0)+IFERROR(1/D142,0)+IFERROR(1/D143,0)","v":{"v":21.243589743589745,"d":"21.24"}},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"$f":"L126+L127+L128+L129+L130+L131+L132+IFERROR(1/(IFERROR(1/L133,0)+IFERROR(1/L134,0)+IFERROR(1/L135,0)+IFERROR(1/L136,0)),0)+L137+IFERROR(1/(IFERROR(1/L138,0)+IFERROR(1/L139,0)+IFERROR(1/L140,0)+IFERROR(1/L141,0)),0)+IFERROR(1/L142,0)+IFERROR(1/L143,0)","v":{"v":0,"d":"0.00"}},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"}]
[]
[null,"HORAS CONTR",{"$f":"+C101","v":"2024-01-01"},"2024-02-01","2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01"]
[0.2,"TOTAL",{"$f":"+C102","v":744},{"$f":"+D102","v":672},744,720,744,720,744,744,720,744,720,744]
[null,{"$f":"+B103","v":"CHANCADO PRIMARIO"},19.759999999999998,13.440000000000001,17.92,8.96,16.380000000000003,11.760000000000002,11.760000000000002,28.560000000000002,18.480000000000004,20.160000000000004,11.760000000000002,16.800000000000004]
[0.2,"CHANCADO SECUNDARIO",19.759999999999998,13.440000000000001,17.92,8.96,16.380000000000003,11.760000000000002,11.760000000000002,28.560000000000002,18.480000000000004,20.160000000000004,11.760000000000002,16.800000000000004]
[0.2,"CHANCADO TERCIARIO",19.759999999999998,13.440000000000001,17.92,8.96,16.380000000000003,11.760000000000002,11.760000000000002,28.560000000000002,18.480000000000004,20.160000000000004,11.760000000000002,16.800000000000004]
[0.1,"MOLIENDA",10.08,11.52,15.360000000000001,7.68,14.04,10.08,10.08,24.479999999999997,15.84,17.28,10.079999999999998,14.4]
[0.05,"PLANTA DE CAL",4.2,4.8,6.4,3.2,5.85,4.2,4.2,10.2,6.6000000000000005,7.200000000000001,4.2,6]
[0.15,"ABASTECIMIENTO DE AGUA",11.760000000000002,13.440000000000001,17.92,8.96,16.380000000000003,11.760000000000002,11.760000000000002,28.560000000000002,18.480000000000004,20.160000000000004,11.760000000000002,16.800000000000004]
[0.2,"REACTIVOS",4.2,4.8,6.4,3.2,5.85,4.2,4.2,10.2,6.6000000000000005,7.200000000000001,4.2,6]
[0.1,"FLOTACION Pb",8.4,9.6,12.8,6.4,11.7,8.4,8.4,20.4,13.200000000000001,14.400000000000002,8.4,12]
[null,"FLOTACION Cu",8.4,9.6,12.8,6.4,11.7,8.4,8.4,20.4,13.200000000000001,14.400000000000002,8.4,12]
[null,"FLOTACION Zn",8.4,9.6,12.8,6.4,11.7,8.4,8.4,20.4,13.200000000000001,14.400000000000002,8.4,12]
[null,"FLOTACION Bulk",8.4,9.6,12.8,6.4,11.7,8.4,8.4,20.4,13.200000000000001,14.400000000000002,8.4,12]
[null,"ESPESADORES",11.760000000000002,13.440000000000001,17.92,8.96,16.380000000000003,11.760000000000002,11.760000000000002,28.560000000000002,18.480000000000004,20.160000000000004,11.760000000000002,16.800000000000004]
[null,"FILTRADO Pb",6.72,7.68,10.24,5.12,9.36,6.72,6.72,16.32,10.559999999999999,11.52,6.72,9.6]
[null,"FILTRADO Cu",8.4,9.6,12.8,6.4,11.7,8.4,8.4,20.4,13.200000000000001,14.400000000000002,8.4,12]
[null,"FILTRADO Zn",8.4,9.6,12.8,6.4,11.7,8.4,8.4,20.4,13.200000000000001,14.400000000000002,8.4,12]
[null,"FILTRADO Bulk",8.4,9.6,12.8,6.4,11.7,8.4,8.4,20.4,13.200000000000001,14.400000000000002,8.4,12]
[null,"PLANTA DE NEUTRALIZACION",10.08,11.52,15.360000000000001,7.68,14.04,10.08,10.08,24.479999999999997,15.84,17.28,10.079999999999998,14.4]
[null,"BOMBAS DE RELAVE",15.120000000000001,17.279999999999998,23.04,11.52,21.06,15.120000000000001,15.120000000000001,36.72,23.76,25.92,15.12,21.599999999999998]
[null,"HORAS PARADA PREVENTIVO",{"$f":"SUM(C148:C165)","v":{"v":192.00000000000006,"d":"192.0"}},{"$f":"SUM(D148:D165)","v":{"v":191.99999999999997,"d":"192.0"}},{"v":256.0000000000001,"d":"256.0"},{"v":128.00000000000006,"d":"128.0"},{"v":233.99999999999997,"d":"234.0"},{"v":168.00000000000006,"d":"168.0"},{"v":168.00000000000006,"d":"168.0"},{"v":408,"d":"408.0"},{"v":264,"d":"264.0"},{"v":288.00000000000006,"d":"288.0"},{"v":168.00000000000006,"d":"168.0"},{"v":240.00000000000003,"d":"240.0"}]
[null,"HORAS TOTAL MEJORA"]
[null,"HORAS OPERACIÓN",{"$f":"(24*C55-C166-C167)","v":552},{"$f":"(24*D55-D166-D167)","v":480},{"v":487.9999999999999,"d":"488"},592,510,552,576,336,456,{"v":455.99999999999994,"d":"456"},552,504]
[null,"HORAS REPARACION",{"$f":"+C189","v":{"v":21.71666666666667,"d":"22"}},{"$f":"+D189","v":{"v":10.090909090909092,"d":"10"}},0,0,0,0,0,0,0,0,0,0]
[]
[{"$f":"+A80","v":0},{"$f":"+B148","v":"CHANCADO PRIMARIO"}]
[{"$f":"+A81","v":0.07},"CHANCADO SECUNDARIO",{"v":4,"d":"4.0"},{"v":4,"d":"4.0"}]
[{"$f":"+A82","v":0.07},"CHANCADO TERCIARIO",null,{"v":3,"d":"3.0"}]
[0.07,"MOLIENDA",{"v":2,"d":"2.0"}]
[0.06,"PLANTA DE CAL"]
[0.025,"ABASTECIMIENTO DE AGUA",{"v":13,"d":"13.0"}]
[0.07,"REACTIVOS"]
[0.025,"FLOTACION Pb"]
[0.05,"FLOTACION Cu"]
[0.05,"FLOTACION Zn",null,{"v":3,"d":"3.0"}]
[0.05,"FLOTACION Bulk"]
[0.05,"ESPESADORES",{"v":2,"d":"2.0"}]
[0.07,"FILTRADO Pb",{"v":2,"d":"2.0"}]
[0.04,"FILTRADO Cu"]
[0.05,"FILTRADO Zn",{"v":1,"d":"1.0"}]
[0.05,"FILTRADO Bulk"]
[0.05,"PLANTA DE NEUTRALIZACION"]
[0.06,"BOMBAS DE RELAVE",{"v":20,"d":"20.0"},{"v":11,"d":"11.0"}]
[0.09,"HORAS CONTR CORRECTIVO",{"$f":"C171+C172+C173+C174+C175+C176+C177+IFERROR(1/(IFERROR(1/C178,0)+IFERROR(1/C179,0)+IFERROR(1/C180,0)+IFERROR(1/C181,0)),0)+C182+IFERROR(1/(IFERROR(1/C183,0)+IFERROR(1/C184,0)+IFERROR(1/C185,0)+IFERROR(1/C186,0)),0)+IFERROR(1/C187,0)+IFERROR(1/C188,0)","v":{"v":21.71666666666667,"d":"21.72"}},{"$f":"D171+D172+D173+D174+D175+D176+D177+IFERROR(1/(IFERROR(1/D178,0)+IFERROR(1/D179,0)+IFERROR(1/D180,0)+IFERROR(1/D181,0)),0)+D182+IFERROR(1/(IFERROR(1/D183,0)+IFERROR(1/D184,0)+IFERROR(1/D185,0)+IFERROR(1/D186,0)),0)+IFERROR(1/D187,0)+IFERROR(1/D188,0)","v":{"v":10.090909090909092,"d":"10.09"}},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"}]
[]
[null,"DISPONIBILIDAD PLANTA","2024-01-01","2024-02-01","2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01","Promedio"]
[null,"DF Budget",{"$f":"((24*C10)-C31-C32-C54)/(24*C10)","v":{"v":0.8997475806451612,"d":"90.0%"}},{"$f":"((24*D10)-D31-D32-D54)/(24*D10)","v":{"v":0.8538420918367348,"d":"85.4%"}},{"$f":"((24*E10)-E31-E32-E54)/(24*E10)","v":{"v":0.8997475806451612,"d":"90.0%"}},{"$f":"((24*F10)-F31-F32-F54)/(24*F10)","v":{"v":0.8301242559523809,"d":"83.0%"}},{"$f":"((24*G10)-G31-(G32)-G54)/(24*G10)","v":{"v":0.835479896313364,"d":"83.5%"}},{"$f":"((24*H10)-H31-(H32)-H54)/(24*H10)","v":{"v":0.8301242559523809,"d":"83.0%"}},{"$f":"((24*I10)-I31-I32-I54)/(24*I10)","v":{"v":0.835479896313364,"d":"83.5%"}},{"v":0.8033460541474654,"d":"80.3%"},{"v":0.8633292261904761,"d":"86.3%"},{"v":0.835479896313364,"d":"83.5%"},{"v":0.7969192857142857,"d":"79.7%"},{"v":0.9318814228110598,"d":"93.2%"},{"$f":"AVERAGE(C192:L192)","v":{"v":0.8486700734309853,"d":"84.9%"}}]
[null,"DF Forecast",{"$f":"((24*C10)-C76-C77-C99)/(24*C10)","v":{"v":0.8676137384792627,"d":"86.8%"}},{"v":0.8538420918367348,"d":"85.4%"},{"v":0.8997475806451612,"d":"90.0%"},{"v":0.9961491071428572,"d":"99.6%"},{"v":0.9961491071428571,"d":"99.6%"},{"v":0.9961491071428572,"d":"99.6%"},{"v":0.9961491071428571,"d":"99.6%"},{"v":0.9961491071428571,"d":"99.6%"},{"v":0.9961491071428572,"d":"99.6%"},{"v":0.9961491071428571,"d":"99.6%"},{"v":0.9961491071428572,"d":"99.6%"},{"v":0.9961491071428571,"d":"99.6%"},{"$f":"AVERAGE(C193:L193)","v":{"v":0.9594247160961158,"d":"95.9%"}}]
[null,"DF Real",{"$f":"((24*C10)-(C121+C122+C144))/(24*C10)","v":{"v":0.7595794639947866,"d":"76.0%"}},{"$f":"IF(D144=0,\"-\",((24*D10)-D121-D122-D144)/(24*D10))","v":{"v":0.7883875152625153,"d":"78.8%"}},{"$f":"IF(E144=0,\"-\",((24*E10)-E121-E122-E144)/(24*E10))","v":"-"},"-","-","-","-","-","-","-","-","-",{"$f":"AVERAGE(C194:L194)","v":{"v":0.7739834896286509,"d":"77.4%"}}]
[null,"DF Real - CONTR",{"$f":"((24*C10)-(C166+C167+C189))/(24*C10)","v":{"v":0.7127464157706093,"d":"71.3%"}},{"$f":"IF(D189=0,\"-\",((24*D10)-D166-D167-D189)/(24*D10))","v":{"v":0.6992694805194806,"d":"69.9%"}},{"$f":"IF(E189=0,\"-\",((24*E10)-E166-E167-E189)/(24*E10))","v":"-"},"-","-","-","-","-","-","-","-","-",{"$f":"AVERAGE(C195:L195)","v":{"v":0.706007948145045,"d":"70.6%"}}]
{"$rows_empty":27}
[null,"PRINCIPALES ACTIVIDADES","ENERO","BOMBA VOGT Nº2 FILTRO PRENSA",{"$nulls":4},"Falla en el sistema de bombeo (atoro de la bomba)"]
[{"$nulls":3},"BOMBA RIO TORRES Nº1",{"$nulls":4},"Falla en la linea de distribucion de carga (fuga de carga por agujero)"]
[{"$nulls":3},"MUESTREADOR DE RELAVE METSO",{"$nulls":4},"Falla en el sistema electrico (quemadura de motor)"]
[{"$nulls":3},"CELDA WENCO ZN SCAVENGER N° 6",{"$nulls":4},"Falla en el sistema electrico (rotura de estructura de motor)"]
[{"$nulls":3},"ZARANDA DE ALTA FRECUENCIA / SAF",{"$nulls":4},"Falla en el sistema electrico (rotura de estructura de motor)"]
[{"$nulls":3},"CELDA DR 500 #02",{"$nulls":4},"CELDA DR 500 #02; Falla en el sistema de agitacion(dispersor)"]
[{"$nulls":3},"MOLINO #01",{"$nulls":4},"MOLINO #01; falla en el sistema de transmision(chumacera de contraeje)"]
[{"$nulls":3},"BOMBA MARS #01",{"$nulls":4},"BOMBA MARS #01; falla en el sistema de transmision(caja de transmsionh)"]
[{"$nulls":3},"VALVULA NEUMATICA DESCARGA DE CALACON ALIMENTO A POZA DE MARS # 01",{"$nulls":4},"VALVULA NEUMATICA DESCARGA DE CALACON ALIMENTO A POZA DE MARS # 01; Falla en el sistema de bombeo(valvula)"]
[{"$nulls":3},"CEDAZO # 01",{"$nulls":4},"CEDAZO # 01; Falla en el sistema de transmision(tambor)"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":4},"FILTRO PRENSA; Falla en el sistema electronico"]
[{"$nulls":3},"MOLINO FULLER ",{"$nulls":4},"MOLINO FULLER ; Falla en el sistema de transmision(reductor)"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº136",{"$nulls":4},"BOMBA DOSIFICADORA Nº136; Falla en el sistema de distribucion(manga)"]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":4},"CEDAZO 02 ; Falla en el sistema de la zaranda(panel)"]
[{"$nulls":3},"BOMBA DE LUBRICACION #01 DE MOLINO 8X11",{"$nulls":4},"BOMBA DE LUBRICACION #01 DE MOLINO 8X11; Falla en el sistema de transmision(acoplamiento)"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº122",{"$nulls":4},"BOMBA DOSIFICADORA Nº122; Falla en el sistema de distribucion(manga)"]
[{"$nulls":3},"ESPESADOR DE ZINC",{"$nulls":4},"Falla en la linea de descarga del cono  del espesador"]
[{"$nulls":3},"FILTRO CC 30",{"$nulls":4},"Falla en  sistema de de transmison de la rastra"]
[{"$nulls":3},"COMPRESORA ST1509",{"$nulls":4},"Falla en el circuito de aire de la compresora(valvula de alivio) "]
[{"$nulls":3},"BOMBA DE LODOS 3 Y 4",{"$nulls":4},"Falla en el sistema de bombeo. "]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":4},"Falla en el sistema de transmision"]
[{"$nulls":3},"BOMBA DOSIFICADORA FLOTACION",{"$nulls":4},"Falla en el sistema de bombeo "]
[{"$nulls":3},"DETECTOR DE METALES  FAJA 5A",{"$nulls":4},"Falla en el funcionamiento de control del equipo"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":4},"Falla en el sistema de regulacion de la valvula diafragma"]
[null,null,"FEBRERO","CELDA DENVER SUB A-24 Nº2",{"$nulls":4},"Falla en la linea de electrico (rotor)"]
[{"$nulls":3},"SOPLADOR INGERSOLL RAND",{"$nulls":4},"Falla en sistema de alimentacion de aire"]
[{"$nulls":3},"BOMBA VERTICAL 02 DE RETORNO CURRIER ",{"$nulls":4},"Fallla en el sistema de bombeo"]
[{"$nulls":3},"CEDAZO #02",{"$nulls":4},"Falla en el sistema de transmision"]
[{"$nulls":3},"BOMBA 02 DE MOLINO 8 X 11",{"$nulls":4},"Fallla en el sistema de bombeo"]
[{"$nulls":3},"BOMBA NOVA 02",{"$nulls":4},"Falla en el sistema de bombeo"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":4},"Falla en el sistema electronico"]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":4},"Falla en el sistema de transmision"]
[{"$nulls":3},"CHANCADORA TERCIARIA ",{"$nulls":4},"Falla en el sistema de transmision"]
[{"$nulls":3},"FAJA 07 DE CHANCADO ",{"$nulls":4},"Falla en el sistema de transmision"]
[{"$nulls":3},"CLARIFICADOR N° 3",{"$nulls":4},"Falla en el sistema electrico"]
[{"$nulls":3},"CEDAZO #01",{"$nulls":4},"Falla en el sistema de transmision"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":4},"Falla en el mecanismo(tambor)"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":4},"Falla en el motor electrico(templador)"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":4},"Falla en el sistema de control del sensor(final de carrera)"]
[{"$nulls":3},"BOMBAS NOVA 4",{"$nulls":4},"Falla en el sendor de nivel(actuador de boya)"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":4},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"BOMBA # 01 DE CELDA SK 240",{"$nulls":4},"Falla en el sistema de bombeo(impulsor)"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":4},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"FAJA N° 7",{"$nulls":4},"Falla en el motoreductor"]
[{"$nulls":3},"BOMBA 77 A",{"$nulls":4},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"CELDA SP-18 ",{"$nulls":4},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"FAJA 5D DE CHANCADO",{"$nulls":4},"Falla en el empalme de la banda transportadora"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":4},"Falla en el sistema electronico"]
[{"$nulls":3},"FAJA TRANSPORTADORA DE ALIMENTO AL MOLINO 8X11",{"$nulls":4},"Falla en el sistema de acarreo de mineral (banda transportadora)"]
[{"$nulls":3},"BOMBA MARS 04",{"$nulls":4},"Falla en el sistema estructural (base de bomba)"]
[{"$nulls":3},"BOMBA 1.5 COURIER CONCENTRADO DE PLOMO",{"$nulls":4},"Falla en la linea de tuberias de descarga"]
[{"$nulls":3},"BOMBA HIDROSTAL EF05 Nº1",{"$nulls":4},"Falla en el sistema de bombeo"]
[{"$nulls":3},"FAJA 5C DE CHANCADO",{"$nulls":4},"Falla en el sistema de transmision(cadena de transmision)"]
[{"$nulls":3},"BOMBA MARS 02",{"$nulls":4},"Falla en la linea de tuberias de descarga (valvula de descarga)"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":4},"Falla en el sistema de zarandeo (malla)"]

{"sheet":"MTTR","index":12,"n_rows":143,"n_cols":15,"rows_kept":143,"merged":[[7,2,7,13],[88,2,111,2],[112,2,142,2],[112,3,112,7],[113,3,113,7],[114,3,114,7],[115,3,115,7],[116,3,116,7],[117,3,117,7],[118,3,118,7],[119,3,119,7],[120,3,120,7],[121,3,121,7],[122,3,122,7],[123,3,123,7]]}
[null,"MTTR PLANTA CONCENTRADORA 2024",{"$nulls":6},"MTBF",{"$f":"+DISP_PLANTA!J1","v":280},null,"MTTR",{"$f":"+DISP_PLANTA!M1","v":1.7}]
[]
[null,null,"2012-01-01","2012-02-01","2012-03-01","2012-04-01","2012-05-01"]
[null,"MTBF",{"v":22.921034482758625,"d":"22.9"},{"v":29.868571428571425,"d":"29.9"},{"v":21.071290322580644,"d":"21.1"},{"v":28.742272727272734,"d":"28.7"},{"v":40.345882352941175,"d":"40.3"}]
[null,"MTTR",{"v":1.358620689655173,"d":"1.4"},{"v":0.7095238095238091,"d":"0.7"},{"v":1.4032258064516132,"d":"1.4"},{"v":1.6143939393939393,"d":"1.6"},{"v":0.5872549019607843,"d":"0.6"}]
[]
[]
[null,null,2024]
[]
[null,null,31,29,31,30,31,30,31,31,30,31,30,31]
[null,"MTTR","2024-01-01","2024-02-01","2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01"]
[0.2,"PLANEADO",{"$f":"+$M$1","v":1.7},{"$f":"+$M$1","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7]
[0.2,"PROYECTADO",{"$f":"+$M$1","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7]
[0.2,"REALIZADO",{"$f":"C34","v":{"v":4.107142857142857,"d":"4.1"}},{"$f":"D34","v":{"v":2.7142857142857144,"d":"2.7"}},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7]
[]
[0.07,"CHANCADO PRIMARIO",{"v":2,"d":"2.0"}]
[0.07,"CHANCADO SECUNDARIO",1.8,{"v":2.2,"d":"2"}]
[0.07,"CHANCADO TERCIARIO",14.7,{"v":1.5,"d":"2"}]
[0.06,"MOLIENDA",{"v":3,"d":"3.0"},{"v":1.5,"d":"2"}]
[0.025,"PLANTA DE CAL"]
[0.07,"ABASTECIMIENTO DE AGUA",12.5]
[0.025,"REACTIVOS",2.5]
[0.05,"FLOTACION Pb",2.5]
[0.05,"FLOTACION Cu"]
[0.05,"FLOTACION Zn",{"v":3,"d":"3.0"},{"v":2.5,"d":"3"}]
[0.05,"FLOTACION Bulk"]
[0.07,"ESPESADORES",{"v":2,"d":"2.0"}]
[0.04,"FILTRADO Pb",2.5,4]
[0.05,"FILTRADO Cu",{"v":1,"d":"1.0"}]
[0.05,"FILTRADO Zn",{"v":1,"d":"1.0"}]
[0.05,"FILTRADO Bulk"]
[0.06,"PLANTA DE NEUTRALIZACION",{"v":3,"d":"3.0"},3]
[0.09,"BOMBAS DE RELAVE",{"v":6,"d":"6.0"},{"v":4.3,"d":"4"}]
[null,"MTTR TOTAL",{"$f":"IF(SUM(C16:C33)=0,C13,AVERAGE(C16:C33))","v":{"v":4.107142857142857,"d":"4.1"}},{"v":2.7142857142857144,"d":"2.7"},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7]
[null,null,{"$f":"+C10","v":31},29,31,30,31,30,31,31,30,31,30,31]
[0.07,"CHANCADO PRIMARIO"]
[0.07,"CHANCADO SECUNDARIO",1.8,2]
[0.07,"CHANCADO TERCIARIO",null,{"v":1.5,"d":"2"}]
[0.06,"MOLIENDA",{"v":2,"d":"2.0"}]
[0.025,"PLANTA DE CAL"]
[0.07,"ABASTECIMIENTO DE AGUA",12.5]
[0.025,"REACTIVOS"]
[0.05,"FLOTACION Pb"]
[0.05,"FLOTACION Cu"]
[0.05,"FLOTACION Zn",null,3]
[0.05,"FLOTACION Bulk"]
[0.07,"ESPESADORES",{"v":2,"d":"2.0"}]
[0.04,"FILTRADO Pb",{"v":2,"d":"2.0"}]
[0.05,"FILTRADO Cu"]
[0.05,"FILTRADO Zn",{"v":1,"d":"1.0"}]
[0.05,"FILTRADO Bulk"]
[0.06,"PLANTA DE NEUTRALIZACION"]
[0.09,"BOMBAS DE RELAVE",6.7,{"v":5.5,"d":"6"}]
[null,"MTTR TOTAL",{"$f":"IF(SUM(C36:C53)=0,C14,AVERAGE(C36:C53))","v":{"v":4,"d":"4.0"}},{"$f":"IF(SUM(D36:D53)=0,D14,AVERAGE(D36:D53))","v":{"v":3,"d":"3.0"}},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7]
[null,null,{"$f":"+C30","v":1},0,0,0,0,0,0,0,0,0,0,0]
[null,"DISPONIBILIDAD PLANTA","2024-01-01","2024-02-01","2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01","Promedio"]
[null,"DF Budget (Producción)",{"v":0.943,"d":"94.3%"},{"v":0.948,"d":"94.8%"},{"v":0.943,"d":"94.3%"},{"v":0.966,"d":"96.6%"},{"v":0.56,"d":"56.0%"},{"v":0.56,"d":"56.0%"},{"v":0.943,"d":"94.3%"},{"v":0.9670000000000001,"d":"96.7%"},{"v":0.9420000000000001,"d":"94.2%"},{"v":0.9540000000000001,"d":"95.4%"},{"v":0.95,"d":"95.0%"},{"v":0.879,"d":"87.9%"}]
[null,"MTTR Budget",{"$f":"IF(C12=0,\"-\",C12)","v":1.7},{"$f":"IF(D12=0,\"-\",D12)","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,{"$f":"AVERAGE(C58:N58)","v":{"v":1.6999999999999995,"d":"2"}}]
[null,"MTTR Forecast",{"$f":"IF(C13=0,\"-\",C13)","v":1.7},{"$f":"IF(D13=0,\"-\",D13)","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,{"$f":"AVERAGE(C59:N59)","v":{"v":1.6999999999999995,"d":"2"}}]
[null,"MTTR Real",{"v":4.107142857142857,"d":"4.1"},{"v":4.107142857142857,"d":"4.1"},{"$nulls":10},{"$f":"AVERAGE(C60:E60)","v":{"v":4.107142857142857,"d":"4"}}]
[null,"MTTR Real - CONTR.",{"v":4,"d":"4.0"},{"v":4,"d":"4.0"},{"$nulls":10},{"$f":"AVERAGE(C61:N61)","v":4}]
{"$rows_empty":27}
[null,"PRINCIPALES ACTIVIDADES","ENERO","BOMBA VOGT Nº2 FILTRO PRENSA",{"$nulls":4}," Fuga de carga por agujero de tuberia de descarga"]
[{"$nulls":3},"BOMBA RIO TORRES Nº1",{"$nulls":4}," Fuga de carga por agujero de tuberia de descarga"]
[{"$nulls":3},"MUESTREADOR DE RELAVE METSO",{"$nulls":4}," Quemadura de motor"]
[{"$nulls":3},"CELDA WENCO ZN SCAVENGER N° 6",{"$nulls":4}," Rotura de estructura de motor por juego axial"]
[{"$nulls":3},"ZARANDA DE ALTA FRECUENCIA / SAF",{"$nulls":4},"Rotura de los portarodajes del motor"]
[{"$nulls":3},"CELDA DR 500 #02",{"$nulls":4},"Soltura de dispersor por corrosion de pernos de fijacion"]
[{"$nulls":3},"MOLINO #01",{"$nulls":4},"Soltura de pernos de chumacera del contraeje por vibracion excesiva"]
[{"$nulls":3},"BOMBA MARS #01",{"$nulls":4},"Fuga de aceite por la caja de transmision por falta de ajuste en el montaje"]
[{"$nulls":3},"VALVULA NEUMATICA DESCARGA DE CALACON ALIMENTO A POZA DE MARS # 01",{"$nulls":4},"Fuga de carga por brida de la linea de la bomba vertical"]
[{"$nulls":3},"CEDAZO # 01",{"$nulls":4},"Fuga de aceite en el tambor por excesiva vibracion "]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":4},"Falsa señal de final de carrera por descalibracion"]
[{"$nulls":3},"MOLINO FULLER ",{"$nulls":4},"Sonido elevado del reductor por desgaste de piñon"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº136",{"$nulls":4},"Fisura de manga por rosamiento de componente"]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":4},"Rotura de panel por ingreso de material extraño"]
[{"$nulls":3},"BOMBA DE LUBRICACION #01 DE MOLINO 8X11",{"$nulls":4},"Rotura de acoplamiento omega por fatiga"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº122",{"$nulls":4},"Fisura de manga por rosamiento de componente"]
[{"$nulls":3},"ESPESADOR DE ZINC",{"$nulls":4},"Derrame de carga por fisura de manga de la valvula de descarga"]
[{"$nulls":3},"FILTRO CC 30",{"$nulls":4},"Vibracion excesiva por soltura de pernos de la chumacera de la rastra"]
[{"$nulls":3},"COMPRESORA ST1509",{"$nulls":4},"Parametro elevados por falta de señal a la valvula de alivio"]
[{"$nulls":3},"BOMBA DE LODOS 3 Y 4",{"$nulls":4},"Perdida de presion por ingreso de material extraño en la camara de bombeo"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":4},"Quemado de correas de transmision por desgaste de polea"]
[{"$nulls":3},"BOMBA DOSIFICADORA FLOTACION",{"$nulls":4},"Derrame de carga por fisura de manga"]
[{"$nulls":3},"DETECTOR DE METALES  FAJA 5A",{"$nulls":4},"Perdida de eficiencia por quemado de varistor"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":4},"Perdida de eficiencia por rotura de resorte de control de diafragma"]
[null,null,"FEBRERO","CELDA DENVER SUB A-24 Nº2",{"$nulls":4},"Recalentamiento de motor electrico por la presencia de pernos rotos"]
[{"$nulls":3},"SOPLADOR INGERSOLL RAND",{"$nulls":4},"Recalentamiento de soplador por obstruccion del filtro de aire"]
[{"$nulls":3},"BOMBA VERTICAL 02 DE RETORNO CURRIER ",{"$nulls":4},"Perdida de presion de bombeo por arenamiento"]
[{"$nulls":3},"CEDAZO #02",{"$nulls":4},"Rotura de fajas por desalineamiento"]
[{"$nulls":3},"BOMBA 02 DE MOLINO 8 X 11",{"$nulls":4},"Perdida de presion de bombeo por arenamiento"]
[{"$nulls":3},"BOMBA NOVA 02",{"$nulls":4},"Perdida de presion de bombeo por soltura  pernos de acoplamiento de rotor"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":4},"Alerta en el modulo de control del equipo"]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":4},"Rotura de fajas por desalineamiento"]
[{"$nulls":3},"CHANCADORA TERCIARIA ",{"$nulls":4},"Rotura de fajas por ingreso de material extraño"]
[{"$nulls":3},"FAJA 07 DE CHANCADO ",{"$nulls":4},"Soltura de cadena de transmision por desgaste"]
[{"$nulls":3},"CLARIFICADOR N° 3",{"$nulls":4},"Recalentamiento del motor por trabamiento de rodamientos del motor"]
[{"$nulls":3},"CEDAZO #01",{"$nulls":4},"Soltura de fajas por destemplado "]
[{"$nulls":3},"CEDAZO 02",{"$nulls":4},"Se amarro los rodamiento del tambor por mala reparacion"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":4},"Rotura del templador por sobreesfuerzo en el sistema de transmision(tambor)"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":4},"Perdida de señal de eficiencia en final de carrera por descalibracion de sensor"]
[{"$nulls":3},"BOMBAS NOVA 4",{"$nulls":4},"Perdida de señal en la activacion del actuador de la boya, por cumplimiento de vida util"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":4},"Quemado de correas por ingreso de inchancable(restos de jebe)"]
[{"$nulls":3},"BOMBA # 01 DE CELDA SK 240",{"$nulls":4},"Perdida de presion de bombeo por arenamiento  en la linea de alimentacion"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":4},"Quemado de correas por ingreso de inchancable(restos de jebe)"]
[{"$nulls":3},"FAJA N° 7",{"$nulls":4},"Sonido en el motoreductor por presencia de desgaste de rodamientos"]
[{"$nulls":3},"BOMBA 77 A",{"$nulls":4},"Quemado de correas por desalineamiento(polea conducida con desgaste)"]
[{"$nulls":3},"CELDA SP-18 ",{"$nulls":4},"Rotura de correa de transmision por fatiga(01 correa)"]
[{"$nulls":3},"FAJA 5D DE CHANCADO",{"$nulls":4},"Soltura de empalme de la banda por ingreso de material extraño(carga abrasiva)"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":4},"Cables de control en mal estado por ambiente inadecuado"]
[{"$nulls":3},"FAJA TRANSPORTADORA DE ALIMENTO AL MOLINO 8X11",{"$nulls":4},"Angulo de raspador en contacto con la banda transportadora (genero cortes pqueños)"]
[{"$nulls":3},"BOMBA MARS 04",{"$nulls":4},"Presencia de pernos rotos de media luna de la botella de mezcla"]
[{"$nulls":3},"BOMBA 1.5 COURIER CONCENTRADO DE PLOMO",{"$nulls":4},"Presencia de fisuras en la tuberia de descarga"]
[{"$nulls":3},"BOMBA HIDROSTAL EF05 Nº1",{"$nulls":4},"Fuga de agua por sellos mecanicos de la bomba"]
[{"$nulls":3},"FAJA 5C DE CHANCADO",{"$nulls":4},"Cadena de transmision RS 100 trabada"]
[{"$nulls":3},"BOMBA MARS 02",{"$nulls":4},"Perdida de eficiencia de la valvula de descarga (presenta oxidacion excesiva)"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":4},"Mallas con agujeros producto del trabajo"]

{"sheet":"MTBF","index":13,"n_rows":143,"n_cols":15,"rows_kept":143,"merged":[[7,2,7,13],[88,2,111,2],[112,2,142,2],[112,3,112,7],[113,3,113,7],[114,3,114,7],[115,3,115,7],[116,3,116,7],[117,3,117,7],[118,3,118,7],[119,3,119,7],[120,3,120,7],[121,3,121,7],[122,3,122,7],[123,3,123,7]]}
[null,"MTBF PLANTA CONCENTRADORA 2024",{"$nulls":6},"MTBF",{"$f":"+DISP_PLANTA!J1","v":280},null,"MTTR",{"$f":"+DISP_PLANTA!M1","v":1.7}]
[]
[null,null,"2012-01-01","2012-02-01","2012-03-01","2012-04-01","2012-05-01"]
[null,"MTBF",{"v":22.921034482758625,"d":"22.9"},{"v":29.868571428571425,"d":"29.9"},{"v":21.071290322580644,"d":"21.1"},{"v":28.742272727272734,"d":"28.7"},{"v":40.345882352941175,"d":"40.3"}]
[null,"MTTR",{"v":1.358620689655173,"d":"1.4"},{"v":0.7095238095238091,"d":"0.7"},{"v":1.4032258064516132,"d":"1.4"},{"v":1.6143939393939393,"d":"1.6"},{"v":0.5872549019607843,"d":"0.6"}]
[]
[]
[null,null,2024]
[]
[null,null,31,29,31,30,31,30,31,31,30,31,30,31]
[null,"MTBF","2024-01-01","2024-02-01","2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01"]
[0.2,"PLANEADO",{"$f":"+$J$1","v":280},{"$f":"+$J$1","v":280},280,280,280,280,280,280,280,280,280,280]
[0.2,"PROYECTADO",{"$f":"+$J$1","v":280},280,{"$f":"+$J$1","v":280},280,280,280,280,280,280,280,280,280]
[0.2,"REALIZADO",{"$f":"C34","v":{"v":501.42857142857144,"d":"501"}},{"$f":"D34","v":{"v":42.857142857142854,"d":"43"}},280,280,280,280,280,280,280,280,280,280]
[]
[0.07,"CHANCADO PRIMARIO",{"v":648,"d":"648.0"}]
[0.07,"CHANCADO SECUNDARIO",{"v":216,"d":"216.0"},{"v":24,"d":"24.0"}]
[0.07,"CHANCADO TERCIARIO",{"v":648,"d":"648.0"},{"v":36,"d":"36.0"}]
[0.06,"MOLIENDA",{"v":162,"d":"162.0"},{"v":72,"d":"72.0"}]
[0.025,"PLANTA DE CAL"]
[0.07,"ABASTECIMIENTO DE AGUA",{"v":648,"d":"648.0"}]
[0.025,"REACTIVOS",{"v":324,"d":"324.0"}]
[0.05,"FLOTACION Pb",{"v":648,"d":"648.0"}]
[0.05,"FLOTACION Cu"]
[0.05,"FLOTACION Zn",{"v":648,"d":"648.0"},{"v":36,"d":"36.0"}]
[0.05,"FLOTACION Bulk"]
[0.07,"ESPESADORES",{"v":648,"d":"648.0"}]
[0.04,"FILTRADO Pb",{"v":648,"d":"648.0"},{"v":72,"d":"72.0"}]
[0.05,"FILTRADO Cu",{"v":648,"d":"648.0"}]
[0.05,"FILTRADO Zn",{"v":648,"d":"648.0"}]
[0.05,"FILTRADO Bulk"]
[0.06,"PLANTA DE NEUTRALIZACION",{"v":324,"d":"324.0"},{"v":36,"d":"36.0"}]
[0.09,"BOMBAS DE RELAVE",{"v":162,"d":"162.0"},{"v":24,"d":"24.0"}]
[null,"MTBF TOTAL",{"$f":"IF(SUM(C16:C33)=0,C13,AVERAGE(C16:C33))","v":{"v":501.42857142857144,"d":"501.4"}},{"v":42.857142857142854,"d":"42.9"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"}]
[null,null,{"$f":"+C10","v":31},29,31,30,31,30,31,31,30,31,30,31]
[0.07,"CHANCADO PRIMARIO"]
[0.07,"CHANCADO SECUNDARIO",{"v":324,"d":"324.0"},{"v":36,"d":"36.0"}]
[0.07,"CHANCADO TERCIARIO",null,{"v":36,"d":"36.0"}]
[0.06,"MOLIENDA",{"v":648,"d":"648.0"}]
[0.025,"PLANTA DE CAL"]
[0.07,"ABASTECIMIENTO DE AGUA",{"v":648,"d":"648.0"}]
[0.025,"REACTIVOS"]
[0.05,"FLOTACION Pb"]
[0.05,"FLOTACION Cu"]
[0.05,"FLOTACION Zn",null,{"v":72,"d":"72.0"}]
[0.05,"FLOTACION Bulk"]
[0.07,"ESPESADORES",{"v":648,"d":"648.0"}]
[0.04,"FILTRADO Pb",{"v":648,"d":"648.0"}]
[0.05,"FILTRADO Cu"]
[0.05,"FILTRADO Zn",{"v":648,"d":"648.0"}]
[0.05,"FILTRADO Bulk"]
[0.06,"PLANTA DE NEUTRALIZACION"]
[0.09,"BOMBAS DE RELAVE",{"v":216,"d":"216.0"},{"v":36,"d":"36.0"}]
[null,"MTBF CONTRACTUAL",{"$f":"IF(SUM(C36:C53)=0,C14,AVERAGE(C36:C53))","v":{"v":540,"d":"540.0"}},{"$f":"IF(SUM(D36:D53)=0,D14,AVERAGE(D36:D53))","v":{"v":45,"d":"45.0"}},{"$f":"IF(SUM(E36:E53)=0,E14,AVERAGE(E36:E53))","v":{"v":280,"d":"280.0"}},{"$f":"IF(SUM(F36:F53)=0,F14,AVERAGE(F36:F53))","v":{"v":280,"d":"280.0"}},{"$f":"IF(SUM(G36:G53)=0,G14,AVERAGE(G36:G53))","v":{"v":280,"d":"280.0"}},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"}]
[null,null,{"$f":"+C30","v":648},0,0,0,0,0,0,0,0,0,0,0]
[null,{"$f":"+B1","v":"MTBF PLANTA CONCENTRADORA 2024"},"2024-01-01","2024-02-01","2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2023-11-01","2023-12-01","Promedio"]
[null,"DF Budget (Producción)",{"v":0.943,"d":"94.3%"},{"v":0.948,"d":"94.8%"},{"v":0.943,"d":"94.3%"},{"v":0.966,"d":"96.6%"},{"v":0.56,"d":"56.0%"},{"v":0.56,"d":"56.0%"},{"v":0.943,"d":"94.3%"},{"v":0.9670000000000001,"d":"96.7%"},{"v":0.9420000000000001,"d":"94.2%"},{"v":0.9540000000000001,"d":"95.4%"},{"v":0.95,"d":"95.0%"},{"v":0.879,"d":"87.9%"}]
[null,"MTBF Budget",{"$f":"IF(C12=0,\"-\",C12)","v":{"v":280,"d":"280.0"}},{"$f":"IF(D12=0,\"-\",D12)","v":{"v":280,"d":"280.0"}},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"$f":"AVERAGE(C58:J58)","v":280}]
[null,"MTBF Forecast",{"$f":"IF(C13=0,\"-\",C13)","v":{"v":280,"d":"280.0"}},{"$f":"IF(D13=0,\"-\",D13)","v":{"v":280,"d":"280.0"}},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"v":280,"d":"280.0"},{"$f":"AVERAGE(C59:J59)","v":280}]
[null,"MTBF Real",{"v":501.42857142857144,"d":"501.4"},{"v":42.857142857142854,"d":"42.9"},{"$nulls":8},{"$f":"IF(M14=0,\"-\",M14)","v":{"v":280,"d":"280.0"}},{"v":280,"d":"280.0"},{"$f":"AVERAGE(C60:J60)","v":{"v":272.14285714285717,"d":"272"}}]
[null,"MTBF Real - CONTR",{"v":540,"d":"540.0"},{"v":45,"d":"45.0"},{"$nulls":8},{"$f":"+M54","v":{"v":280,"d":"280.0"}},{"v":280,"d":"280.0"},{"$f":"AVERAGE(C61:J61)","v":{"v":292.5,"d":"293"}}]
{"$rows_empty":27}
[null,"PRINCIPALES ACTIVIDADES","ENERO","BOMBA VOGT Nº2 FILTRO PRENSA",{"$nulls":4},"Limpieza de carga de la bomba VOGT e inspeccion del estado del impulsor"]
[{"$nulls":3},"BOMBA RIO TORRES Nº1",{"$nulls":4},"Desembridado de válvula de cuchilla de 8\" para drenaje de agua de las quenas y reparacion de agujeros de tuberia"]
[{"$nulls":3},"MUESTREADOR DE RELAVE METSO",{"$nulls":4},"Cambio de cadena y alineamiento de motor"]
[{"$nulls":3},"CELDA WENCO ZN SCAVENGER N° 6",{"$nulls":4},"Reparacion de estructura de motor"]
[{"$nulls":3},"ZARANDA DE ALTA FRECUENCIA / SAF",{"$nulls":4},"Reparacion de estructura de motor"]
[{"$nulls":3},"CELDA DR 500 #02",{"$nulls":4},"Cambio de pernos de fijacion del dispersor"]
[{"$nulls":3},"MOLINO #01",{"$nulls":4},"Ajuste de pernos de chumacera del contraeje"]
[{"$nulls":3},"BOMBA MARS #01",{"$nulls":4},"Ajuste de pernos de fijacion de la caja de transmision"]
[{"$nulls":3},"VALVULA NEUMATICA DESCARGA DE CALACON ALIMENTO A POZA DE MARS # 01",{"$nulls":4},"Reparacion de la  brida de  la linea de descarga de la bomba vertical"]
[{"$nulls":3},"CEDAZO # 01",{"$nulls":4},"Ajuste de los pernos del tambor "]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":4},"Calibracion y seguimiento del final de carrera"]
[{"$nulls":3},"MOLINO FULLER ",{"$nulls":4},"Cambio de aceite del reductor y medicion de desgaste del piñon"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº136",{"$nulls":4},"Cambio de manga "]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":4},"Cambiuo de panel y piunes de sujecion"]
[{"$nulls":3},"BOMBA DE LUBRICACION #01 DE MOLINO 8X11",{"$nulls":4},"Cambio de acoplamiento y alineamiento del sistema de transmision"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº122",{"$nulls":4},"Cambio de manga "]
[{"$nulls":3},"ESPESADOR DE ZINC",{"$nulls":4},"Se cambio manga de la valvula de descarga"]
[{"$nulls":3},"FILTRO CC 30",{"$nulls":4},"Se ajusto  pernos de la chumacera de la rastra y se alineo el sistema de transmision"]
[{"$nulls":3},"COMPRESORA ST1509",{"$nulls":4},"Se realizo mantenimiento de la  valvula de alivio"]
[{"$nulls":3},"BOMBA DE LODOS 3 Y 4",{"$nulls":4},"Se reviso y retiromaterial extraño en la camara de bombeo"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":4},"Se cambio correas y las poleas  del sistema de  transmision"]
[{"$nulls":3},"BOMBA DOSIFICADORA FLOTACION",{"$nulls":4},"Se cambio manga y glicerina"]
[{"$nulls":3},"DETECTOR DE METALES  FAJA 5A",{"$nulls":4},"Se realizo el cambio del varistor y regulacion de parametros"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":4},"Se cambio resorte de control de diafragma"]
[null,null,"FEBRERO","CELDA DENVER SUB A-24 Nº2",{"$nulls":4},"Se realiza cambio de pernos y seguimiento del funcionamiento"]
[{"$nulls":3},"SOPLADOR INGERSOLL RAND",{"$nulls":4},"Se realiza cambio de filtro de aire, nivelacion de aceite y seguimiento del funcionamiento"]
[{"$nulls":3},"BOMBA VERTICAL 02 DE RETORNO CURRIER ",{"$nulls":4},"Se realizo desarenamiento de la linea de bombeo"]
[{"$nulls":3},"CEDAZO #02",{"$nulls":4},"Se cambio las fajas de trasmision"]
[{"$nulls":3},"BOMBA 02 DE MOLINO 8 X 11",{"$nulls":4},"Se realizo desarenamiento de sistema de bombeo"]
[{"$nulls":3},"BOMBA NOVA 02",{"$nulls":4},"Se ajusto los  pernos de acoplamiento de rotor"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":4},"Equipo fuera de servicio"]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":4},"Se cambio las fajas de trasmision"]
[{"$nulls":3},"CHANCADORA TERCIARIA ",{"$nulls":4},"Se cambio las fajas  de transmision"]
[{"$nulls":3},"FAJA 07 DE CHANCADO ",{"$nulls":4},"Se cambio y templo la cadena de transmision "]
[{"$nulls":3},"CLARIFICADOR N° 3",{"$nulls":4},"Se cambio el motor electrico y se alineo las poleas"]
[{"$nulls":3},"CEDAZO #01",{"$nulls":4},"Se realizo el templado de las fajas de transmision"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":4},"Se reinstalo el  tambor por falla del tambor reparado"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":4},"Se cambio motor electrico stand by y se alineo las poleas y templado de correas"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":4},"Se calibro el sensor de final de carrera ."]
[{"$nulls":3},"BOMBAS NOVA 4",{"$nulls":4},"Se realizo el mantenimiento del  actuador de la boya,"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":4},"Se cambio, se alineo y templo las correas de transmision"]
[{"$nulls":3},"BOMBA # 01 DE CELDA SK 240",{"$nulls":4},"Se cambio el impulsor y se desareno la linea de alimentaion"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":4},"Se cambio, se alineo y templo las correas de transmision"]
[{"$nulls":3},"FAJA N° 7",{"$nulls":4},"Se cambio el motoreductor y se templo la cadena del sistema de transmision"]
[{"$nulls":3},"BOMBA 77 A",{"$nulls":4},"Se cambio, se alineo y templo las correas de transmision"]
[{"$nulls":3},"CELDA SP-18 ",{"$nulls":4},"Se cambio, se alineo y templo las correas de transmision"]
[{"$nulls":3},"FAJA 5D DE CHANCADO",{"$nulls":4},"Se realizo el pegado del empalme sueltop de la banda transportadora"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":4},"Se realizó la Inspección por el proveedor dejando operativo el equipo( cables de control en mal estado y suelto), se dejo seteado la presion a 120 psi y la temperatura a 170  ºF, con al observacion de realizar la reparacion de la valvula espiral(se dejo anulado)."]
[{"$nulls":3},"FAJA TRANSPORTADORA DE ALIMENTO AL MOLINO 8X11",{"$nulls":4},"Se retiro el angulo, se verifico los cortes y se resano banda"]
[{"$nulls":3},"BOMBA MARS 04",{"$nulls":4},"Cambio de pernos de media luna de la botella de mezcla"]
[{"$nulls":3},"BOMBA 1.5 COURIER CONCENTRADO DE PLOMO",{"$nulls":4},"Resane de fisuras en la tuberia de descarga"]
[{"$nulls":3},"BOMBA HIDROSTAL EF05 Nº1",{"$nulls":4},"Cambio de sellos mecanicos de la bomba"]
[{"$nulls":3},"FAJA 5C DE CHANCADO",{"$nulls":4},"Cambio de cadena de transmision RS 100"]
[{"$nulls":3},"BOMBA MARS 02",{"$nulls":4},"Cambio de valvula de descarga"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":4},"Reparacion de mallas"]

{"sheet":"GRAF HORAS PLC","index":14,"n_rows":29,"n_cols":28,"rows_kept":29,"merged":[[0,1,0,27],[2,1,2,13],[2,15,2,27],[24,1,24,13],[24,15,24,27]]}
[null,"HORAS PLANTA 2024"]
[]
[null,"HORAS PREVENTIVO",{"$nulls":13},"HORAS ACUMULADAS PREVENTIVO"]
[null,"MES","2024-01-01","2024-02-01","2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01",null,"MES",{"$f":"+C4","v":"2024-01-01"},{"$f":"+D4","v":"2024-02-01"},"2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01"]
[null,"Budget",{"$f":"+DISP_PLANTA!C31","v":{"v":72.00000000000001,"d":"72"}},{"$f":"+DISP_PLANTA!D31","v":{"v":95.99999999999999,"d":"96"}},{"$nulls":11},"Budget",{"$f":"+SUM($C$5:C$5)","v":{"v":72.00000000000001,"d":"72"}},{"$f":"+SUM($C$5:D$5)","v":168}]
[null,"Forecast",{"$f":"+DISP_PLANTA!C76","v":{"v":95.99999999999999,"d":"96"}},{"$f":"+DISP_PLANTA!D76","v":{"v":95.99999999999999,"d":"96"}},{"$nulls":11},"Forecast",{"$f":"+SUM($C$6:C$6)","v":{"v":95.99999999999999,"d":"96"}},{"$f":"+SUM($C$6:D$6)","v":{"v":191.99999999999997,"d":"192"}}]
[null,"Real",{"$f":"+DISP_PLANTA!C33","v":{"v":672,"d":"672.0"}},{"$f":"+DISP_PLANTA!D33","v":{"v":576,"d":"576.0"}},{"$nulls":10},{"$f":"+DISP_PLANTA!O121","v":{"v":0,"d":"0.0"}},"Real",{"$f":"+SUM($C$7:C$7)","v":{"v":672,"d":"672.0"}},{"$f":"+SUM($C$7:D$7)","v":{"v":1248,"d":"1248.0"}}]
[null,"Hr Paradas",{"$nulls":13},"Hr Paradas",{"$f":"SUM($C$8:C$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:D$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:E$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:F$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:G$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:H$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:I$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:J$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:K$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:L$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:M$8)","v":{"v":0,"d":"0.0"}},{"$f":"SUM($C$8:N$8)","v":{"v":0,"d":"0.0"}}]
{"$rows_empty":16}
[null,"HORAS CORRECTIVO",{"$nulls":13},"HORAS ACUMULADAS CORRECTIVO"]
[null,"MES",{"$f":"+C4","v":"2024-01-01"},{"$f":"+D4","v":"2024-02-01"},"2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01",null,"MES",{"$f":"+C4","v":"2024-01-01"},{"$f":"+D4","v":"2024-02-01"},"2024-03-01","2024-04-01","2024-05-01","2024-06-01","2024-07-01","2024-08-01","2024-09-01","2024-10-01","2024-11-01","2024-12-01"]
[null,"Budget",{"$f":"+DISP_PLANTA!C54","v":{"v":2.5878,"d":"3"}},{"$f":"+DISP_PLANTA!D54","v":{"v":2.218114285714286,"d":"2"}},{"$nulls":11},"Budget",{"$f":"SUM($C$27:C$27)","v":{"v":2.5878,"d":"3"}},{"$f":"SUM($C$27:D$27)","v":{"v":4.805914285714286,"d":"5"}}]
[null,"Forecast",{"$f":"+DISP_PLANTA!C99","v":{"v":2.4953785714285712,"d":"2"}},{"$f":"+DISP_PLANTA!D99","v":{"v":2.218114285714286,"d":"2"}},{"$nulls":11},"Forecast",{"$f":"+SUM($C$28:C$28)","v":{"v":2.4953785714285712,"d":"2"}},{"$f":"+SUM($C$28:D$28)","v":{"v":4.713492857142857,"d":"5"}}]
[null,"Real",{"$f":"+DISP_PLANTA!C144","v":{"v":57.91287878787878,"d":"57.9"}},{"$f":"+DISP_PLANTA!D144","v":{"v":21.243589743589745,"d":"21.2"}},{"$nulls":11},"Real",{"$f":"SUM($C$29:C$29)","v":{"v":57.91287878787878,"d":"57.9"}},{"$f":"SUM($C$29:D$29)","v":{"v":79.15646853146853,"d":"79.2"}},{"$f":"SUM($C$29:E$29)","v":{"v":79.15646853146853,"d":"79.2"}},{"$f":"SUM($C$29:F$29)","v":{"v":79.15646853146853,"d":"79.2"}},{"$f":"SUM($C$29:G$29)","v":{"v":79.15646853146853,"d":"79.2"}},{"$f":"SUM($C$29:H$29)","v":{"v":79.15646853146853,"d":"79.2"}},{"$f":"SUM($C$29:I$29)","v":{"v":79.15646853146853,"d":"79.2"}},{"$f":"SUM($C$29:J$29)","v":{"v":79.15646853146853,"d":"79.2"}},{"$f":"SUM($C$29:K$29)","v":{"v":79.15646853146853,"d":"79.2"}},{"$f":"SUM($C$29:L$29)","v":{"v":79.15646853146853,"d":"79.2"}},{"$f":"SUM($C$29:M$29)","v":{"v":79.15646853146853,"d":"79.2"}},{"$f":"SUM($C$29:N$29)","v":{"v":79.15646853146853,"d":"79.2"}}]

{"sheet":"DISP_PLANTA_SEM","index":15,"n_rows":328,"n_cols":57,"rows_kept":328,"merged":[[7,2,7,13],[223,2,227,2],[223,3,223,7],[223,8,223,13],[224,3,224,7],[224,8,224,13],[225,3,225,7],[225,8,225,13],[226,3,226,7],[226,8,226,13],[227,3,227,7],[227,8,227,13],[228,2,230,2],[228,3,228,7],[228,8,228,13],[229,3,229,7],[229,8,229,13],[230,3,230,7],[230,8,230,13],[231,2,241,2],[231,3,231,7],[231,8,231,13],[232,3,232,7],[232,8,232,13],[233,3,233,7],[233,8,233,13],[234,3,234,7],[234,8,234,13],[235,3,235,7],[235,8,235,13],[236,3,236,7],[236,8,236,13],[237,3,237,7],[237,8,237,13],[238,3,238,7],[238,8,238,13],[239,3,239,7],[239,8,239,13],[240,3,240,7],[240,8,240,13],[241,3,241,7],[241,8,241,13],[242,2,249,2],[242,3,242,7],[243,3,243,7],[244,3,244,7],[245,3,245,7],[246,3,246,7],[247,3,247,7],[248,3,248,7],[249,3,249,7],[250,2,251,2],[250,3,250,7],[251,3,251,7],[252,2,261,2],[252,3,252,7],[253,3,253,7],[254,3,254,7],[255,3,255,7],[256,3,256,7],[257,3,257,7],[258,3,258,7],[259,3,259,7],[260,3,260,7],[261,3,261,7],[262,2,273,2],[274,2,280,2],[281,2,288,2],[289,2,298,2],[299,2,307,2],[308,2,319,2],[320,2,327,2]]}
[null,"DISPONIBILIDAD PLANTA CONCENTRADORA 2024",{"$nulls":6},"MTBF",65,null,"MTTR",1.7]
[]
[null,null,"2012-01-01","2012-02-01","2012-03-01","2012-04-01","2012-05-01"]
[null,"MTBF",{"v":22.921034482758625,"d":"22.9"},{"v":29.868571428571425,"d":"29.9"},{"v":21.071290322580644,"d":"21.1"},{"v":28.742272727272734,"d":"28.7"},{"v":40.345882352941175,"d":"40.3"}]
[null,"MTTR",{"v":1.358620689655173,"d":"1.4"},{"v":0.7095238095238091,"d":"0.7"},{"v":1.4032258064516132,"d":"1.4"},{"v":1.6143939393939393,"d":"1.6"},{"v":0.5872549019607843,"d":"0.6"}]
[]
[]
[null,null,2024]
[]
[null,null,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7]
[null,"HORAS PLANEADAS","SEM01","SEM02","SEM03","SEM04","SEM05","SEM06","SEM07","SEM08","SEM09","SEM10","SEM11","SEM12","SEM13","SEM14","SEM15","SEM16","SEM17","SEM18","SEM19","SEM20","SEM21","SEM22","SEM23","SEM24","SEM25","SEM26","SEM27","SEM28","SEM29","SEM30","SEM31","SEM32","SEM33","SEM34","SEM35","SEM36","SEM37","SEM38","SEM39","SEM40","SEM41","SEM42","SEM43","SEM44","SEM45","SEM46","SEM47","SEM48","SEM49","SEM50","SEM51","SEM52"]
[0.2,"TOTAL",{"$f":"+C10*24","v":168},{"$f":"+D10*24","v":168},168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168]
[0.2,{"$f":"+'HORAS PARADAS'!C7","v":"CHANCADO PRIMARIO"},{"$f":"+SUM('HORAS PARADAS'!D7)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!E7)","v":0},{"$f":"+SUM('HORAS PARADAS'!F7)","v":0},{"$f":"+SUM('HORAS PARADAS'!G7)","v":0},{"$f":"+SUM('HORAS PARADAS'!H7)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I7)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J7)","v":0},{"$f":"+SUM('HORAS PARADAS'!K7)","v":0},{"$f":"+SUM('HORAS PARADAS'!L7)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!M7)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!N7)","v":0},{"$f":"+SUM('HORAS PARADAS'!O7)","v":0},{"$f":"+SUM('HORAS PARADAS'!P7)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q7)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!R7)","v":0},{"$f":"+SUM('HORAS PARADAS'!S7)","v":0},{"$f":"+SUM('HORAS PARADAS'!T7)","v":0},{"$f":"+SUM('HORAS PARADAS'!U7)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!V7)","v":0},{"$f":"+SUM('HORAS PARADAS'!W7)","v":0},{"$f":"+SUM('HORAS PARADAS'!X7)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y7)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z7)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!AA7)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!AB7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD7)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AE7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH7)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!AI7)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL7)","v":1.6800000000000002},10.080000000000002,10.080000000000002,{"$f":"+SUM('HORAS PARADAS'!AO7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ7)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AR7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU7)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!AV7)","v":3.3600000000000003},11.760000000000002,{"$f":"+SUM('HORAS PARADAS'!AX7)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY7)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ7)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!BA7)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB7)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC7)","v":0}]
[0.2,{"$f":"+'HORAS PARADAS'!C8","v":"CHANCADO SECUNDARIO"},{"$f":"+SUM('HORAS PARADAS'!D8)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!E8)","v":0},{"$f":"+SUM('HORAS PARADAS'!F8)","v":0},{"$f":"+SUM('HORAS PARADAS'!G8)","v":0},{"$f":"+SUM('HORAS PARADAS'!H8)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I8)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J8)","v":0},{"$f":"+SUM('HORAS PARADAS'!K8)","v":0},{"$f":"+SUM('HORAS PARADAS'!L8)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!M8)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!N8)","v":0},{"$f":"+SUM('HORAS PARADAS'!O8)","v":0},{"$f":"+SUM('HORAS PARADAS'!P8)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q8)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!R8)","v":0},{"$f":"+SUM('HORAS PARADAS'!S8)","v":0},{"$f":"+SUM('HORAS PARADAS'!T8)","v":0},{"$f":"+SUM('HORAS PARADAS'!U8)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!V8)","v":0},{"$f":"+SUM('HORAS PARADAS'!W8)","v":0},{"$f":"+SUM('HORAS PARADAS'!X8)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y8)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z8)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!AA8)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!AB8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD8)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AE8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH8)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!AI8)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL8)","v":1.6800000000000002},10.080000000000002,10.080000000000002,{"$f":"+SUM('HORAS PARADAS'!AO8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ8)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AR8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU8)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!AV8)","v":3.3600000000000003},11.760000000000002,{"$f":"+SUM('HORAS PARADAS'!AX8)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY8)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ8)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!BA8)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB8)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC8)","v":0}]
[0.1,{"$f":"+'HORAS PARADAS'!C9","v":"CHANCADO TERCIARIO"},{"$f":"+SUM('HORAS PARADAS'!D9)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!E9)","v":0},{"$f":"+SUM('HORAS PARADAS'!F9)","v":0},{"$f":"+SUM('HORAS PARADAS'!G9)","v":0},{"$f":"+SUM('HORAS PARADAS'!H9)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I9)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J9)","v":0},{"$f":"+SUM('HORAS PARADAS'!K9)","v":0},{"$f":"+SUM('HORAS PARADAS'!L9)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!M9)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!N9)","v":0},{"$f":"+SUM('HORAS PARADAS'!O9)","v":0},{"$f":"+SUM('HORAS PARADAS'!P9)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q9)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!R9)","v":0},{"$f":"+SUM('HORAS PARADAS'!S9)","v":0},{"$f":"+SUM('HORAS PARADAS'!T9)","v":0},{"$f":"+SUM('HORAS PARADAS'!U9)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!V9)","v":0},{"$f":"+SUM('HORAS PARADAS'!W9)","v":0},{"$f":"+SUM('HORAS PARADAS'!X9)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y9)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z9)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!AA9)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!AB9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD9)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AE9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH9)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!AI9)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL9)","v":1.6800000000000002},10.080000000000002,10.080000000000002,{"$f":"+SUM('HORAS PARADAS'!AO9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ9)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AR9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU9)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!AV9)","v":3.3600000000000003},11.760000000000002,{"$f":"+SUM('HORAS PARADAS'!AX9)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY9)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ9)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!BA9)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB9)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC9)","v":0}]
[0.05,{"$f":"+'HORAS PARADAS'!C10","v":"MOLIENDA"},{"$f":"+SUM('HORAS PARADAS'!D10)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!E10)","v":0},{"$f":"+SUM('HORAS PARADAS'!F10)","v":0},{"$f":"+SUM('HORAS PARADAS'!G10)","v":0},{"$f":"+SUM('HORAS PARADAS'!H10)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!I10)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!J10)","v":0},{"$f":"+SUM('HORAS PARADAS'!K10)","v":0},{"$f":"+SUM('HORAS PARADAS'!L10)","v":1.44},{"$f":"+SUM('HORAS PARADAS'!M10)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!N10)","v":0},{"$f":"+SUM('HORAS PARADAS'!O10)","v":0},{"$f":"+SUM('HORAS PARADAS'!P10)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q10)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!R10)","v":0},{"$f":"+SUM('HORAS PARADAS'!S10)","v":0},{"$f":"+SUM('HORAS PARADAS'!T10)","v":0},{"$f":"+SUM('HORAS PARADAS'!U10)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!V10)","v":0},{"$f":"+SUM('HORAS PARADAS'!W10)","v":0},{"$f":"+SUM('HORAS PARADAS'!X10)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y10)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z10)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!AA10)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!AB10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD10)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!AE10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH10)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!AI10)","v":1.44},{"$f":"+SUM('HORAS PARADAS'!AJ10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL10)","v":1.44},8.64,8.64,{"$f":"+SUM('HORAS PARADAS'!AO10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ10)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!AR10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU10)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!AV10)","v":2.88},10.08,{"$f":"+SUM('HORAS PARADAS'!AX10)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY10)","v":1.44},{"$f":"+SUM('HORAS PARADAS'!AZ10)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!BA10)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB10)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC10)","v":0}]
[0.15,{"$f":"+'HORAS PARADAS'!C11","v":"PLANTA DE CAL"},{"$f":"+SUM('HORAS PARADAS'!D11)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!E11)","v":0},{"$f":"+SUM('HORAS PARADAS'!F11)","v":0},{"$f":"+SUM('HORAS PARADAS'!G11)","v":0},{"$f":"+SUM('HORAS PARADAS'!H11)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!I11)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!J11)","v":0},{"$f":"+SUM('HORAS PARADAS'!K11)","v":0},{"$f":"+SUM('HORAS PARADAS'!L11)","v":0.6000000000000001},{"$f":"+SUM('HORAS PARADAS'!M11)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!N11)","v":0},{"$f":"+SUM('HORAS PARADAS'!O11)","v":0},{"$f":"+SUM('HORAS PARADAS'!P11)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q11)","v":3},{"$f":"+SUM('HORAS PARADAS'!R11)","v":0},{"$f":"+SUM('HORAS PARADAS'!S11)","v":0},{"$f":"+SUM('HORAS PARADAS'!T11)","v":0},{"$f":"+SUM('HORAS PARADAS'!U11)","v":3},{"$f":"+SUM('HORAS PARADAS'!V11)","v":0},{"$f":"+SUM('HORAS PARADAS'!W11)","v":0},{"$f":"+SUM('HORAS PARADAS'!X11)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y11)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z11)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AA11)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!AB11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD11)","v":3},{"$f":"+SUM('HORAS PARADAS'!AE11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH11)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AI11)","v":0.6000000000000001},{"$f":"+SUM('HORAS PARADAS'!AJ11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL11)","v":0.6000000000000001},3.6,3.6,{"$f":"+SUM('HORAS PARADAS'!AO11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ11)","v":3},{"$f":"+SUM('HORAS PARADAS'!AR11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU11)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!AV11)","v":1.2000000000000002},4.2,{"$f":"+SUM('HORAS PARADAS'!AX11)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY11)","v":0.6000000000000001},{"$f":"+SUM('HORAS PARADAS'!AZ11)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!BA11)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB11)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC11)","v":0}]
[0.2,{"$f":"+'HORAS PARADAS'!C12","v":"ABASTECIMIENTO DE AGUA"},{"$f":"+SUM('HORAS PARADAS'!D12)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!E12)","v":0},{"$f":"+SUM('HORAS PARADAS'!F12)","v":0},{"$f":"+SUM('HORAS PARADAS'!G12)","v":0},{"$f":"+SUM('HORAS PARADAS'!H12)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I12)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J12)","v":0},{"$f":"+SUM('HORAS PARADAS'!K12)","v":0},{"$f":"+SUM('HORAS PARADAS'!L12)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!M12)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!N12)","v":0},{"$f":"+SUM('HORAS PARADAS'!O12)","v":0},{"$f":"+SUM('HORAS PARADAS'!P12)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q12)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!R12)","v":0},{"$f":"+SUM('HORAS PARADAS'!S12)","v":0},{"$f":"+SUM('HORAS PARADAS'!T12)","v":0},{"$f":"+SUM('HORAS PARADAS'!U12)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!V12)","v":0},{"$f":"+SUM('HORAS PARADAS'!W12)","v":0},{"$f":"+SUM('HORAS PARADAS'!X12)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y12)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z12)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!AA12)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!AB12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD12)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AE12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH12)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!AI12)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL12)","v":1.6800000000000002},10.080000000000002,10.080000000000002,{"$f":"+SUM('HORAS PARADAS'!AO12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ12)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AR12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU12)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!AV12)","v":3.3600000000000003},11.760000000000002,{"$f":"+SUM('HORAS PARADAS'!AX12)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY12)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ12)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!BA12)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB12)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC12)","v":0}]
[0.1,{"$f":"+'HORAS PARADAS'!C13","v":"REACTIVOS"},{"$f":"+SUM('HORAS PARADAS'!D13)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!E13)","v":0},{"$f":"+SUM('HORAS PARADAS'!F13)","v":0},{"$f":"+SUM('HORAS PARADAS'!G13)","v":0},{"$f":"+SUM('HORAS PARADAS'!H13)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!I13)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!J13)","v":0},{"$f":"+SUM('HORAS PARADAS'!K13)","v":0},{"$f":"+SUM('HORAS PARADAS'!L13)","v":0.6000000000000001},{"$f":"+SUM('HORAS PARADAS'!M13)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!N13)","v":0},{"$f":"+SUM('HORAS PARADAS'!O13)","v":0},{"$f":"+SUM('HORAS PARADAS'!P13)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q13)","v":3},{"$f":"+SUM('HORAS PARADAS'!R13)","v":0},{"$f":"+SUM('HORAS PARADAS'!S13)","v":0},{"$f":"+SUM('HORAS PARADAS'!T13)","v":0},{"$f":"+SUM('HORAS PARADAS'!U13)","v":3},{"$f":"+SUM('HORAS PARADAS'!V13)","v":0},{"$f":"+SUM('HORAS PARADAS'!W13)","v":0},{"$f":"+SUM('HORAS PARADAS'!X13)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y13)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z13)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AA13)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!AB13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD13)","v":3},{"$f":"+SUM('HORAS PARADAS'!AE13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH13)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AI13)","v":0.6000000000000001},{"$f":"+SUM('HORAS PARADAS'!AJ13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL13)","v":0.6000000000000001},3.6,3.6,{"$f":"+SUM('HORAS PARADAS'!AO13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ13)","v":3},{"$f":"+SUM('HORAS PARADAS'!AR13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU13)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!AV13)","v":1.2000000000000002},4.2,{"$f":"+SUM('HORAS PARADAS'!AX13)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY13)","v":0.6000000000000001},{"$f":"+SUM('HORAS PARADAS'!AZ13)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!BA13)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB13)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC13)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C14","v":"FLOTACION Pb"},{"$f":"+SUM('HORAS PARADAS'!D14)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!E14)","v":0},{"$f":"+SUM('HORAS PARADAS'!F14)","v":0},{"$f":"+SUM('HORAS PARADAS'!G14)","v":0},{"$f":"+SUM('HORAS PARADAS'!H14)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I14)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J14)","v":0},{"$f":"+SUM('HORAS PARADAS'!K14)","v":0},{"$f":"+SUM('HORAS PARADAS'!L14)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!M14)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!N14)","v":0},{"$f":"+SUM('HORAS PARADAS'!O14)","v":0},{"$f":"+SUM('HORAS PARADAS'!P14)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q14)","v":6},{"$f":"+SUM('HORAS PARADAS'!R14)","v":0},{"$f":"+SUM('HORAS PARADAS'!S14)","v":0},{"$f":"+SUM('HORAS PARADAS'!T14)","v":0},{"$f":"+SUM('HORAS PARADAS'!U14)","v":6},{"$f":"+SUM('HORAS PARADAS'!V14)","v":0},{"$f":"+SUM('HORAS PARADAS'!W14)","v":0},{"$f":"+SUM('HORAS PARADAS'!X14)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y14)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z14)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AA14)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AB14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD14)","v":6},{"$f":"+SUM('HORAS PARADAS'!AE14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH14)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AI14)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL14)","v":1.2000000000000002},7.2,7.2,{"$f":"+SUM('HORAS PARADAS'!AO14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ14)","v":6},{"$f":"+SUM('HORAS PARADAS'!AR14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU14)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AV14)","v":2.4000000000000004},8.4,{"$f":"+SUM('HORAS PARADAS'!AX14)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY14)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ14)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!BA14)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB14)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC14)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C15","v":"FLOTACION Cu"},{"$f":"+SUM('HORAS PARADAS'!D15)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!E15)","v":0},{"$f":"+SUM('HORAS PARADAS'!F15)","v":0},{"$f":"+SUM('HORAS PARADAS'!G15)","v":0},{"$f":"+SUM('HORAS PARADAS'!H15)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I15)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J15)","v":0},{"$f":"+SUM('HORAS PARADAS'!K15)","v":0},{"$f":"+SUM('HORAS PARADAS'!L15)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!M15)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!N15)","v":0},{"$f":"+SUM('HORAS PARADAS'!O15)","v":0},{"$f":"+SUM('HORAS PARADAS'!P15)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q15)","v":6},{"$f":"+SUM('HORAS PARADAS'!R15)","v":0},{"$f":"+SUM('HORAS PARADAS'!S15)","v":0},{"$f":"+SUM('HORAS PARADAS'!T15)","v":0},{"$f":"+SUM('HORAS PARADAS'!U15)","v":6},{"$f":"+SUM('HORAS PARADAS'!V15)","v":0},{"$f":"+SUM('HORAS PARADAS'!W15)","v":0},{"$f":"+SUM('HORAS PARADAS'!X15)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y15)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z15)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AA15)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AB15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD15)","v":6},{"$f":"+SUM('HORAS PARADAS'!AE15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH15)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AI15)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL15)","v":1.2000000000000002},7.2,7.2,{"$f":"+SUM('HORAS PARADAS'!AO15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ15)","v":6},{"$f":"+SUM('HORAS PARADAS'!AR15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU15)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AV15)","v":2.4000000000000004},8.4,{"$f":"+SUM('HORAS PARADAS'!AX15)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY15)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ15)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!BA15)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB15)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC15)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C16","v":"FLOTACION Zn"},{"$f":"+SUM('HORAS PARADAS'!D16)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!E16)","v":0},{"$f":"+SUM('HORAS PARADAS'!F16)","v":0},{"$f":"+SUM('HORAS PARADAS'!G16)","v":0},{"$f":"+SUM('HORAS PARADAS'!H16)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I16)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J16)","v":0},{"$f":"+SUM('HORAS PARADAS'!K16)","v":0},{"$f":"+SUM('HORAS PARADAS'!L16)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!M16)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!N16)","v":0},{"$f":"+SUM('HORAS PARADAS'!O16)","v":0},{"$f":"+SUM('HORAS PARADAS'!P16)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q16)","v":6},{"$f":"+SUM('HORAS PARADAS'!R16)","v":0},{"$f":"+SUM('HORAS PARADAS'!S16)","v":0},{"$f":"+SUM('HORAS PARADAS'!T16)","v":0},{"$f":"+SUM('HORAS PARADAS'!U16)","v":6},{"$f":"+SUM('HORAS PARADAS'!V16)","v":0},{"$f":"+SUM('HORAS PARADAS'!W16)","v":0},{"$f":"+SUM('HORAS PARADAS'!X16)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y16)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z16)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AA16)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AB16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD16)","v":6},{"$f":"+SUM('HORAS PARADAS'!AE16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH16)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AI16)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL16)","v":1.2000000000000002},7.2,7.2,{"$f":"+SUM('HORAS PARADAS'!AO16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ16)","v":6},{"$f":"+SUM('HORAS PARADAS'!AR16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU16)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AV16)","v":2.4000000000000004},8.4,{"$f":"+SUM('HORAS PARADAS'!AX16)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY16)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ16)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!BA16)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB16)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC16)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C17","v":"FLOTACION Bulk"},{"$f":"+SUM('HORAS PARADAS'!D17)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!E17)","v":0},{"$f":"+SUM('HORAS PARADAS'!F17)","v":0},{"$f":"+SUM('HORAS PARADAS'!G17)","v":0},{"$f":"+SUM('HORAS PARADAS'!H17)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I17)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J17)","v":0},{"$f":"+SUM('HORAS PARADAS'!K17)","v":0},{"$f":"+SUM('HORAS PARADAS'!L17)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!M17)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!N17)","v":0},{"$f":"+SUM('HORAS PARADAS'!O17)","v":0},{"$f":"+SUM('HORAS PARADAS'!P17)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q17)","v":6},{"$f":"+SUM('HORAS PARADAS'!R17)","v":0},{"$f":"+SUM('HORAS PARADAS'!S17)","v":0},{"$f":"+SUM('HORAS PARADAS'!T17)","v":0},{"$f":"+SUM('HORAS PARADAS'!U17)","v":6},{"$f":"+SUM('HORAS PARADAS'!V17)","v":0},{"$f":"+SUM('HORAS PARADAS'!W17)","v":0},{"$f":"+SUM('HORAS PARADAS'!X17)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y17)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z17)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AA17)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AB17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD17)","v":6},{"$f":"+SUM('HORAS PARADAS'!AE17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH17)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AI17)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL17)","v":1.2000000000000002},7.2,7.2,{"$f":"+SUM('HORAS PARADAS'!AO17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ17)","v":6},{"$f":"+SUM('HORAS PARADAS'!AR17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU17)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AV17)","v":2.4000000000000004},8.4,{"$f":"+SUM('HORAS PARADAS'!AX17)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY17)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ17)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!BA17)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB17)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC17)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C18","v":"ESPESADORES"},{"$f":"+SUM('HORAS PARADAS'!D18)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!E18)","v":0},{"$f":"+SUM('HORAS PARADAS'!F18)","v":0},{"$f":"+SUM('HORAS PARADAS'!G18)","v":0},{"$f":"+SUM('HORAS PARADAS'!H18)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I18)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J18)","v":0},{"$f":"+SUM('HORAS PARADAS'!K18)","v":0},{"$f":"+SUM('HORAS PARADAS'!L18)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!M18)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!N18)","v":0},{"$f":"+SUM('HORAS PARADAS'!O18)","v":0},{"$f":"+SUM('HORAS PARADAS'!P18)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q18)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!R18)","v":0},{"$f":"+SUM('HORAS PARADAS'!S18)","v":0},{"$f":"+SUM('HORAS PARADAS'!T18)","v":0},{"$f":"+SUM('HORAS PARADAS'!U18)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!V18)","v":0},{"$f":"+SUM('HORAS PARADAS'!W18)","v":0},{"$f":"+SUM('HORAS PARADAS'!X18)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y18)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z18)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!AA18)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!AB18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD18)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AE18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH18)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!AI18)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL18)","v":1.6800000000000002},10.080000000000002,10.080000000000002,{"$f":"+SUM('HORAS PARADAS'!AO18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ18)","v":8.4},{"$f":"+SUM('HORAS PARADAS'!AR18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU18)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!AV18)","v":3.3600000000000003},11.760000000000002,{"$f":"+SUM('HORAS PARADAS'!AX18)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY18)","v":1.6800000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ18)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!BA18)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB18)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC18)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C19","v":"FILTRADO Pb"},{"$f":"+SUM('HORAS PARADAS'!D19)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!E19)","v":0},{"$f":"+SUM('HORAS PARADAS'!F19)","v":0},{"$f":"+SUM('HORAS PARADAS'!G19)","v":0},{"$f":"+SUM('HORAS PARADAS'!H19)","v":1.92},{"$f":"+SUM('HORAS PARADAS'!I19)","v":1.92},{"$f":"+SUM('HORAS PARADAS'!J19)","v":0},{"$f":"+SUM('HORAS PARADAS'!K19)","v":0},{"$f":"+SUM('HORAS PARADAS'!L19)","v":0.96},{"$f":"+SUM('HORAS PARADAS'!M19)","v":1.92},{"$f":"+SUM('HORAS PARADAS'!N19)","v":0},{"$f":"+SUM('HORAS PARADAS'!O19)","v":0},{"$f":"+SUM('HORAS PARADAS'!P19)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q19)","v":4.8},{"$f":"+SUM('HORAS PARADAS'!R19)","v":0},{"$f":"+SUM('HORAS PARADAS'!S19)","v":0},{"$f":"+SUM('HORAS PARADAS'!T19)","v":0},{"$f":"+SUM('HORAS PARADAS'!U19)","v":4.8},{"$f":"+SUM('HORAS PARADAS'!V19)","v":0},{"$f":"+SUM('HORAS PARADAS'!W19)","v":0},{"$f":"+SUM('HORAS PARADAS'!X19)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y19)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z19)","v":1.92},{"$f":"+SUM('HORAS PARADAS'!AA19)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!AB19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD19)","v":4.8},{"$f":"+SUM('HORAS PARADAS'!AE19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH19)","v":3.84},{"$f":"+SUM('HORAS PARADAS'!AI19)","v":0.96},{"$f":"+SUM('HORAS PARADAS'!AJ19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL19)","v":0.96},5.76,5.76,{"$f":"+SUM('HORAS PARADAS'!AO19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ19)","v":4.8},{"$f":"+SUM('HORAS PARADAS'!AR19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU19)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!AV19)","v":1.92},6.72,{"$f":"+SUM('HORAS PARADAS'!AX19)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY19)","v":0.96},{"$f":"+SUM('HORAS PARADAS'!AZ19)","v":1.92},{"$f":"+SUM('HORAS PARADAS'!BA19)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB19)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC19)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C20","v":"FILTRADO Cu"},{"$f":"+SUM('HORAS PARADAS'!D20)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!E20)","v":0},{"$f":"+SUM('HORAS PARADAS'!F20)","v":0},{"$f":"+SUM('HORAS PARADAS'!G20)","v":0},{"$f":"+SUM('HORAS PARADAS'!H20)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I20)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J20)","v":0},{"$f":"+SUM('HORAS PARADAS'!K20)","v":0},{"$f":"+SUM('HORAS PARADAS'!L20)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!M20)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!N20)","v":0},{"$f":"+SUM('HORAS PARADAS'!O20)","v":0},{"$f":"+SUM('HORAS PARADAS'!P20)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q20)","v":6},{"$f":"+SUM('HORAS PARADAS'!R20)","v":0},{"$f":"+SUM('HORAS PARADAS'!S20)","v":0},{"$f":"+SUM('HORAS PARADAS'!T20)","v":0},{"$f":"+SUM('HORAS PARADAS'!U20)","v":6},{"$f":"+SUM('HORAS PARADAS'!V20)","v":0},{"$f":"+SUM('HORAS PARADAS'!W20)","v":0},{"$f":"+SUM('HORAS PARADAS'!X20)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y20)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z20)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AA20)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AB20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD20)","v":6},{"$f":"+SUM('HORAS PARADAS'!AE20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH20)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AI20)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL20)","v":1.2000000000000002},7.2,7.2,{"$f":"+SUM('HORAS PARADAS'!AO20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ20)","v":6},{"$f":"+SUM('HORAS PARADAS'!AR20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU20)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AV20)","v":2.4000000000000004},8.4,{"$f":"+SUM('HORAS PARADAS'!AX20)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY20)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ20)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!BA20)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB20)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC20)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C21","v":"FILTRADO Zn"},{"$f":"+SUM('HORAS PARADAS'!D21)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!E21)","v":0},{"$f":"+SUM('HORAS PARADAS'!F21)","v":0},{"$f":"+SUM('HORAS PARADAS'!G21)","v":0},{"$f":"+SUM('HORAS PARADAS'!H21)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I21)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J21)","v":0},{"$f":"+SUM('HORAS PARADAS'!K21)","v":0},{"$f":"+SUM('HORAS PARADAS'!L21)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!M21)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!N21)","v":0},{"$f":"+SUM('HORAS PARADAS'!O21)","v":0},{"$f":"+SUM('HORAS PARADAS'!P21)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q21)","v":6},{"$f":"+SUM('HORAS PARADAS'!R21)","v":0},{"$f":"+SUM('HORAS PARADAS'!S21)","v":0},{"$f":"+SUM('HORAS PARADAS'!T21)","v":0},{"$f":"+SUM('HORAS PARADAS'!U21)","v":6},{"$f":"+SUM('HORAS PARADAS'!V21)","v":0},{"$f":"+SUM('HORAS PARADAS'!W21)","v":0},{"$f":"+SUM('HORAS PARADAS'!X21)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y21)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z21)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AA21)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AB21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD21)","v":6},{"$f":"+SUM('HORAS PARADAS'!AE21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH21)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AI21)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL21)","v":1.2000000000000002},7.2,7.2,{"$f":"+SUM('HORAS PARADAS'!AO21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ21)","v":6},{"$f":"+SUM('HORAS PARADAS'!AR21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU21)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AV21)","v":2.4000000000000004},8.4,{"$f":"+SUM('HORAS PARADAS'!AX21)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY21)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ21)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!BA21)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB21)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC21)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C22","v":"FILTRADO Bulk"},{"$f":"+SUM('HORAS PARADAS'!D22)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!E22)","v":0},{"$f":"+SUM('HORAS PARADAS'!F22)","v":0},{"$f":"+SUM('HORAS PARADAS'!G22)","v":0},{"$f":"+SUM('HORAS PARADAS'!H22)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I22)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J22)","v":0},{"$f":"+SUM('HORAS PARADAS'!K22)","v":0},{"$f":"+SUM('HORAS PARADAS'!L22)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!M22)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!N22)","v":0},{"$f":"+SUM('HORAS PARADAS'!O22)","v":0},{"$f":"+SUM('HORAS PARADAS'!P22)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q22)","v":6},{"$f":"+SUM('HORAS PARADAS'!R22)","v":0},{"$f":"+SUM('HORAS PARADAS'!S22)","v":0},{"$f":"+SUM('HORAS PARADAS'!T22)","v":0},{"$f":"+SUM('HORAS PARADAS'!U22)","v":6},{"$f":"+SUM('HORAS PARADAS'!V22)","v":0},{"$f":"+SUM('HORAS PARADAS'!W22)","v":0},{"$f":"+SUM('HORAS PARADAS'!X22)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y22)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z22)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!AA22)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AB22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD22)","v":6},{"$f":"+SUM('HORAS PARADAS'!AE22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH22)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!AI22)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AJ22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL22)","v":1.2000000000000002},7.2,7.2,{"$f":"+SUM('HORAS PARADAS'!AO22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ22)","v":6},{"$f":"+SUM('HORAS PARADAS'!AR22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU22)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!AV22)","v":2.4000000000000004},8.4,{"$f":"+SUM('HORAS PARADAS'!AX22)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY22)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!AZ22)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!BA22)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB22)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC22)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C23","v":"PLANTA DE NEUTRALIZACION"},{"$f":"+SUM('HORAS PARADAS'!D23)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!E23)","v":0},{"$f":"+SUM('HORAS PARADAS'!F23)","v":0},{"$f":"+SUM('HORAS PARADAS'!G23)","v":0},{"$f":"+SUM('HORAS PARADAS'!H23)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!I23)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!J23)","v":0},{"$f":"+SUM('HORAS PARADAS'!K23)","v":0},{"$f":"+SUM('HORAS PARADAS'!L23)","v":1.44},{"$f":"+SUM('HORAS PARADAS'!M23)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!N23)","v":0},{"$f":"+SUM('HORAS PARADAS'!O23)","v":0},{"$f":"+SUM('HORAS PARADAS'!P23)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q23)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!R23)","v":0},{"$f":"+SUM('HORAS PARADAS'!S23)","v":0},{"$f":"+SUM('HORAS PARADAS'!T23)","v":0},{"$f":"+SUM('HORAS PARADAS'!U23)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!V23)","v":0},{"$f":"+SUM('HORAS PARADAS'!W23)","v":0},{"$f":"+SUM('HORAS PARADAS'!X23)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y23)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z23)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!AA23)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!AB23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD23)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!AE23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH23)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!AI23)","v":1.44},{"$f":"+SUM('HORAS PARADAS'!AJ23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL23)","v":1.44},8.64,8.64,{"$f":"+SUM('HORAS PARADAS'!AO23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ23)","v":7.199999999999999},{"$f":"+SUM('HORAS PARADAS'!AR23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU23)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!AV23)","v":2.88},10.08,{"$f":"+SUM('HORAS PARADAS'!AX23)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY23)","v":1.44},{"$f":"+SUM('HORAS PARADAS'!AZ23)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!BA23)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB23)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC23)","v":0}]
[null,{"$f":"+'HORAS PARADAS'!C24","v":"BOMBAS DE RELAVE"},{"$f":"+SUM('HORAS PARADAS'!D24)","v":6.4799999999999995},{"$f":"+SUM('HORAS PARADAS'!E24)","v":0},{"$f":"+SUM('HORAS PARADAS'!F24)","v":0},{"$f":"+SUM('HORAS PARADAS'!G24)","v":0},{"$f":"+SUM('HORAS PARADAS'!H24)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!I24)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!J24)","v":0},{"$f":"+SUM('HORAS PARADAS'!K24)","v":0},{"$f":"+SUM('HORAS PARADAS'!L24)","v":2.16},{"$f":"+SUM('HORAS PARADAS'!M24)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!N24)","v":0},{"$f":"+SUM('HORAS PARADAS'!O24)","v":0},{"$f":"+SUM('HORAS PARADAS'!P24)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q24)","v":10.799999999999999},{"$f":"+SUM('HORAS PARADAS'!R24)","v":0},{"$f":"+SUM('HORAS PARADAS'!S24)","v":0},{"$f":"+SUM('HORAS PARADAS'!T24)","v":0},{"$f":"+SUM('HORAS PARADAS'!U24)","v":10.799999999999999},{"$f":"+SUM('HORAS PARADAS'!V24)","v":0},{"$f":"+SUM('HORAS PARADAS'!W24)","v":0},{"$f":"+SUM('HORAS PARADAS'!X24)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y24)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z24)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!AA24)","v":6.4799999999999995},{"$f":"+SUM('HORAS PARADAS'!AB24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD24)","v":10.799999999999999},{"$f":"+SUM('HORAS PARADAS'!AE24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH24)","v":8.64},{"$f":"+SUM('HORAS PARADAS'!AI24)","v":2.16},{"$f":"+SUM('HORAS PARADAS'!AJ24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL24)","v":2.16},12.959999999999999,12.959999999999999,{"$f":"+SUM('HORAS PARADAS'!AO24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ24)","v":10.799999999999999},{"$f":"+SUM('HORAS PARADAS'!AR24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU24)","v":6.4799999999999995},{"$f":"+SUM('HORAS PARADAS'!AV24)","v":4.32},15.12,{"$f":"+SUM('HORAS PARADAS'!AX24)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY24)","v":2.16},{"$f":"+SUM('HORAS PARADAS'!AZ24)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!BA24)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB24)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC24)","v":0}]
[null,"HORAS PARADA PREVENTIVO",{"$f":"+SUM('HORAS PARADAS'!D25)","v":72.00000000000001},{"$f":"+SUM('HORAS PARADAS'!E25)","v":0},{"$f":"+SUM('HORAS PARADAS'!F25)","v":0},{"$f":"+SUM('HORAS PARADAS'!G25)","v":0},{"$f":"+SUM('HORAS PARADAS'!H25)","v":47.99999999999999},{"$f":"+SUM('HORAS PARADAS'!I25)","v":47.99999999999999},{"$f":"+SUM('HORAS PARADAS'!J25)","v":0},{"$f":"+SUM('HORAS PARADAS'!K25)","v":0},{"$f":"+SUM('HORAS PARADAS'!L25)","v":23.999999999999996},{"$f":"+SUM('HORAS PARADAS'!M25)","v":47.99999999999999},{"$f":"+SUM('HORAS PARADAS'!N25)","v":0},{"$f":"+SUM('HORAS PARADAS'!O25)","v":0},{"$f":"+SUM('HORAS PARADAS'!P25)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q25)","v":120.00000000000001},{"$f":"+SUM('HORAS PARADAS'!R25)","v":0},{"$f":"+SUM('HORAS PARADAS'!S25)","v":0},{"$f":"+SUM('HORAS PARADAS'!T25)","v":0},{"$f":"+SUM('HORAS PARADAS'!U25)","v":120.00000000000001},{"$f":"+SUM('HORAS PARADAS'!V25)","v":0},{"$f":"+SUM('HORAS PARADAS'!W25)","v":0},{"$f":"+SUM('HORAS PARADAS'!X25)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y25)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z25)","v":47.99999999999999},{"$f":"+SUM('HORAS PARADAS'!AA25)","v":72.00000000000001},{"$f":"+SUM('HORAS PARADAS'!AB25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD25)","v":120.00000000000001},{"$f":"+SUM('HORAS PARADAS'!AE25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH25)","v":95.99999999999999},{"$f":"+SUM('HORAS PARADAS'!AI25)","v":23.999999999999996},{"$f":"+SUM('HORAS PARADAS'!AJ25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL25)","v":23.999999999999996},{"$f":"+SUM('HORAS PARADAS'!AM25)","v":95.99999999999999},{"$f":"+SUM('HORAS PARADAS'!AN25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ25)","v":120.00000000000001},{"$f":"+SUM('HORAS PARADAS'!AR25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU25)","v":72.00000000000001},{"$f":"+SUM('HORAS PARADAS'!AV25)","v":47.99999999999999},{"$f":"+SUM('HORAS PARADAS'!AW25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX25)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY25)","v":23.999999999999996},{"$f":"+SUM('HORAS PARADAS'!AZ25)","v":47.99999999999999},{"$f":"+SUM('HORAS PARADAS'!BA25)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB25)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC25)","v":0}]
[null,"HORAS TOTAL MEJORA"]
[null,"HORAS OPERACIÓN",{"$f":"(24*C10-C31-C32)","v":{"v":95.99999999999999,"d":"96"}},{"$f":"(24*D10-D31)","v":168},{"$f":"(24*E10-E31)","v":168},{"$f":"(24*F10-F31)","v":168},120,120,168,168,144,120,168,168,168,{"v":47.999999999999986,"d":"48"},168,168,168,{"$f":"(24*T10-T31)","v":{"v":47.999999999999986,"d":"48"}},168,168,168,168,120,{"v":95.99999999999999,"d":"96"},168,168,{"v":47.999999999999986,"d":"48"},168,168,168,{"v":72.00000000000001,"d":"72"},144,168,168,144,{"v":72.00000000000001,"d":"72"},168,168,168,{"v":47.999999999999986,"d":"48"},{"$f":"(24*AQ10-AQ31)","v":168},168,168,{"v":95.99999999999999,"d":"96"},120,168,168,144,120,168,168,168]
[null,"HORAS REPARACION",{"$f":"IFERROR(+(C$33/$J$1)*$M$1,0)","v":{"v":2.5107692307692306,"d":"3"}},{"$f":"IFERROR(+(D$33/$J$1)*$M$1,0)","v":{"v":4.393846153846154,"d":"4"}},{"$f":"IFERROR(+(E$33/$J$1)*$M$1,0)","v":{"v":4.393846153846154,"d":"4"}},{"v":4.393846153846154,"d":"4"},{"v":3.1384615384615384,"d":"3"},{"v":3.1384615384615384,"d":"3"},{"v":4.393846153846154,"d":"4"},{"$f":"IFERROR(+(J$33/$J$1)*$M$1,0)","v":{"v":4.393846153846154,"d":"4"}},{"v":3.766153846153846,"d":"4"},{"v":3.1384615384615384,"d":"3"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":1.255384615384615,"d":"1"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":1.255384615384615,"d":"1"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":3.1384615384615384,"d":"3"},{"v":2.5107692307692306,"d":"3"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":1.255384615384615,"d":"1"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":1.8830769230769235,"d":"2"},{"v":3.766153846153846,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":3.766153846153846,"d":"4"},{"v":1.8830769230769235,"d":"2"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":1.255384615384615,"d":"1"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":2.5107692307692306,"d":"3"},{"v":3.1384615384615384,"d":"3"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":3.766153846153846,"d":"4"},{"v":3.1384615384615384,"d":"3"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"}]
[]
[0.07,{"$f":"+B13","v":"CHANCADO PRIMARIO"},{"$f":"+$A36*C$34","v":{"v":0.17575384615384615,"d":"0.2"}},{"$f":"+$A36*D$34","v":{"v":0.3075692307692308,"d":"0.3"}},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"$f":"+$A36*T$34","v":{"v":0.08787692307692306,"d":"0.1"}},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.13181538461538467,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.043938461538461496,"d":"0.0"},{"v":0.043938461538461496,"d":"0.0"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"}]
[0.07,{"$f":"+B14","v":"CHANCADO SECUNDARIO"},{"v":0.17575384615384615,"d":"0.2"},{"$f":"+$A37*D$34","v":{"v":0.3075692307692308,"d":"0.3"}},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.13181538461538467,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.043938461538461496,"d":"0.0"},{"v":0.043938461538461496,"d":"0.0"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"}]
[0.07,"CHANCADO TERCIARIO",{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.13181538461538467,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.043938461538461496,"d":"0.0"},{"v":0.043938461538461496,"d":"0.0"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"}]
[0.06,"MOLIENDA",{"v":0.15064615384615385,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.22596923076923076,"d":"0.2"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.07532307692307691,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.07532307692307691,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.15064615384615385,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.07532307692307691,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.1129846153846154,"d":"0.1"},{"v":0.22596923076923076,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.22596923076923076,"d":"0.2"},{"v":0.03766153846153842,"d":"0.0"},{"v":0.03766153846153842,"d":"0.0"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.07532307692307691,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.15064615384615385,"d":"0.2"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.22596923076923076,"d":"0.2"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"}]
[0.025,"PLANTA DE CAL",{"v":0.06276923076923077,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.09415384615384616,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"$f":"+$A40*O$34","v":{"v":0.10984615384615387,"d":"0.1"}},{"v":0.03138461538461538,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.03138461538461538,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.06276923076923077,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.03138461538461538,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.04707692307692309,"d":"0.0"},{"v":0.09415384615384616,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.09415384615384616,"d":"0.1"},{"v":0.015692307692307676,"d":"0.0"},{"v":0.015692307692307676,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.03138461538461538,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.06276923076923077,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.09415384615384616,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"}]
[0.07,"ABASTECIMIENTO DE AGUA",{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.13181538461538467,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.043938461538461496,"d":"0.0"},{"v":0.043938461538461496,"d":"0.0"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"}]
[0.025,"REACTIVOS",{"v":0.06276923076923077,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.09415384615384616,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.03138461538461538,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.03138461538461538,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.06276923076923077,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.03138461538461538,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.04707692307692309,"d":"0.0"},{"v":0.09415384615384616,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.09415384615384616,"d":"0.1"},{"v":0.015692307692307676,"d":"0.0"},{"v":0.015692307692307676,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.03138461538461538,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.06276923076923077,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.09415384615384616,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"}]
[0.05,"FLOTACION Pb",{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.09415384615384619,"d":"0.1"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.05,"FLOTACION Cu",{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.09415384615384619,"d":"0.1"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.05,"FLOTACION Zn",{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.09415384615384619,"d":"0.1"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.05,"FLOTACION Bulk",{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"$f":"+$A46*AD$34","v":{"v":0.21969230769230774,"d":"0.2"}},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.09415384615384619,"d":"0.1"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.07,"ESPESADORES",{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.13181538461538467,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.043938461538461496,"d":"0.0"},{"v":0.043938461538461496,"d":"0.0"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.08787692307692306,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"}]
[0.04,"FILTRADO Pb",{"v":0.10043076923076923,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.15064615384615385,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.050215384615384606,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.050215384615384606,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.10043076923076923,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.050215384615384606,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.07532307692307694,"d":"0.1"},{"v":0.15064615384615385,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.15064615384615385,"d":"0.2"},{"v":0.02510769230769228,"d":"0.0"},{"v":0.02510769230769228,"d":"0.0"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.050215384615384606,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.10043076923076923,"d":"0.1"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.15064615384615385,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"}]
[0.05,"FILTRADO Cu",{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.09415384615384619,"d":"0.1"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.05,"FILTRADO Zn",{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.09415384615384619,"d":"0.1"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.05,"FILTRADO Bulk",{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.09415384615384619,"d":"0.1"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.03138461538461535,"d":"0.0"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.06276923076923076,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.18830769230769231,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.06,"PLANTA DE NEUTRALIZACION",{"v":0.15064615384615385,"d":"0.2"},{"$f":"+$A52*D$34","v":{"v":0.2636307692307693,"d":"0.3"}},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.22596923076923076,"d":"0.2"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.07532307692307691,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.07532307692307691,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.15064615384615385,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.07532307692307691,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.1129846153846154,"d":"0.1"},{"v":0.22596923076923076,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.22596923076923076,"d":"0.2"},{"v":0.03766153846153842,"d":"0.0"},{"v":0.03766153846153842,"d":"0.0"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.07532307692307691,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.15064615384615385,"d":"0.2"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"$f":"+$A52*AW$34","v":{"v":0.2636307692307693,"d":"0.3"}},{"v":0.22596923076923076,"d":"0.2"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"}]
[0.09,"BOMBAS DE RELAVE",{"v":0.22596923076923076,"d":"0.2"},{"$f":"+$A53*D$34","v":{"v":0.3954461538461539,"d":"0.4"}},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.28246153846153843,"d":"0.3"},{"v":0.28246153846153843,"d":"0.3"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.33895384615384616,"d":"0.3"},{"v":0.28246153846153843,"d":"0.3"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.11298461538461535,"d":"0.1"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.11298461538461535,"d":"0.1"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.28246153846153843,"d":"0.3"},{"v":0.22596923076923076,"d":"0.2"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.11298461538461535,"d":"0.1"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.1694769230769231,"d":"0.2"},{"v":0.33895384615384616,"d":"0.3"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.33895384615384616,"d":"0.3"},{"v":0.056492307692307626,"d":"0.1"},{"v":0.056492307692307626,"d":"0.1"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.11298461538461535,"d":"0.1"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.22596923076923076,"d":"0.2"},{"v":0.28246153846153843,"d":"0.3"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.33895384615384616,"d":"0.3"},{"v":0.28246153846153843,"d":"0.3"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"}]
[null,"HORAS PARADA CORRECTIVO",{"$f":"C36+C37+C38+C39+C40+C41+C42+IFERROR(1/(IFERROR(1/C43,0)+IFERROR(1/C44,0)+IFERROR(1/C45,0)+IFERROR(1/C46,0)),0)+C47+IFERROR(1/(IFERROR(1/C48,0)+IFERROR(1/C49,0)+IFERROR(1/C50,0)+IFERROR(1/C51,0)),0)+C52+C53","v":{"v":1.5924923076923077,"d":"1.59"}},{"$f":"D36+D37+D38+D39+D40+D41+D42+IFERROR(1/(IFERROR(1/D43,0)+IFERROR(1/D44,0)+IFERROR(1/D45,0)+IFERROR(1/D46,0)),0)+D47+IFERROR(1/(IFERROR(1/D48,0)+IFERROR(1/D49,0)+IFERROR(1/D50,0)+IFERROR(1/D51,0)),0)+D52+D53","v":{"v":2.786861538461539,"d":"2.79"}},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":1.9906153846153845,"d":"1.99"},{"v":1.9906153846153845,"d":"1.99"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.388738461538462,"d":"2.39"},{"v":1.9906153846153845,"d":"1.99"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":0.7962461538461537,"d":"0.80"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":0.7962461538461537,"d":"0.80"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":1.9906153846153845,"d":"1.99"},{"v":1.5924923076923077,"d":"1.59"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":0.7962461538461537,"d":"0.80"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":1.1943692307692313,"d":"1.19"},{"v":2.388738461538462,"d":"2.39"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.388738461538462,"d":"2.39"},{"v":0.39812307692307647,"d":"0.40"},{"v":0.39812307692307647,"d":"0.40"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":0.7962461538461537,"d":"0.80"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":1.5924923076923077,"d":"1.59"},{"v":1.9906153846153845,"d":"1.99"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.388738461538462,"d":"2.39"},{"v":1.9906153846153845,"d":"1.99"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"}]
[null,null,{"$f":"+C10","v":7},{"$f":"+D10","v":7},{"$f":"+E10","v":7},7,7,7,7,7,7,7,7,{"$f":"+N10","v":7},{"$f":"+O10","v":7},7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7,7]
[null,"HORAS PROYECTADAS",{"$f":"+C11","v":"SEM01"},"SEM02","SEM03","SEM04","SEM05","SEM06","SEM07","SEM08","SEM09","SEM10","SEM11","SEM12","SEM13","SEM14","SEM15","SEM16","SEM17","SEM18","SEM19","SEM20","SEM21","SEM22","SEM23","SEM24","SEM25","SEM26","SEM27","SEM28","SEM29","SEM30","SEM31","SEM32","SEM33","SEM34","SEM35","SEM36","SEM37","SEM38","SEM39","SEM40","SEM41","SEM42","SEM43","SEM44","SEM45","SEM46","SEM47","SEM48","SEM49","SEM50","SEM51","SEM52"]
[0.2,"TOTAL",{"$f":"+C10*24","v":168},{"$f":"+D10*24","v":168},168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168]
[0.2,{"$f":"+B13","v":"CHANCADO PRIMARIO"},{"$f":"+SUM('HORAS PARADAS'!D31)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E31)","v":0},{"$f":"+SUM('HORAS PARADAS'!F31)","v":0},{"$f":"+SUM('HORAS PARADAS'!G31)","v":0},{"$f":"+SUM('HORAS PARADAS'!H31)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I31)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J31)","v":0},{"$f":"+SUM('HORAS PARADAS'!K31)","v":0},{"$f":"+SUM('HORAS PARADAS'!L31)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M31)","v":0},{"$f":"+SUM('HORAS PARADAS'!N31)","v":0},{"$f":"+SUM('HORAS PARADAS'!O31)","v":0},{"$f":"+SUM('HORAS PARADAS'!P31)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q31)","v":0},{"$f":"+SUM('HORAS PARADAS'!R31)","v":0},{"$f":"+SUM('HORAS PARADAS'!S31)","v":0},{"$f":"+SUM('HORAS PARADAS'!T31)","v":0},{"$f":"+SUM('HORAS PARADAS'!U31)","v":0},{"$f":"+SUM('HORAS PARADAS'!V31)","v":0},{"$f":"+SUM('HORAS PARADAS'!W31)","v":0},{"$f":"+SUM('HORAS PARADAS'!X31)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y31)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY31)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ31)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA31)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB31)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC31)","v":0}]
[0.2,"CHANCADO SECUNDARIO",{"$f":"+SUM('HORAS PARADAS'!D32)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E32)","v":0},{"$f":"+SUM('HORAS PARADAS'!F32)","v":0},{"$f":"+SUM('HORAS PARADAS'!G32)","v":0},{"$f":"+SUM('HORAS PARADAS'!H32)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I32)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J32)","v":0},{"$f":"+SUM('HORAS PARADAS'!K32)","v":0},{"$f":"+SUM('HORAS PARADAS'!L32)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M32)","v":0},{"$f":"+SUM('HORAS PARADAS'!N32)","v":0},{"$f":"+SUM('HORAS PARADAS'!O32)","v":0},{"$f":"+SUM('HORAS PARADAS'!P32)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q32)","v":0},{"$f":"+SUM('HORAS PARADAS'!R32)","v":0},{"$f":"+SUM('HORAS PARADAS'!S32)","v":0},{"$f":"+SUM('HORAS PARADAS'!T32)","v":0},{"$f":"+SUM('HORAS PARADAS'!U32)","v":0},{"$f":"+SUM('HORAS PARADAS'!V32)","v":0},{"$f":"+SUM('HORAS PARADAS'!W32)","v":0},{"$f":"+SUM('HORAS PARADAS'!X32)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y32)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY32)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ32)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA32)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB32)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC32)","v":0}]
[0.1,"CHANCADO TERCIARIO",{"$f":"+SUM('HORAS PARADAS'!D33)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E33)","v":0},{"$f":"+SUM('HORAS PARADAS'!F33)","v":0},{"$f":"+SUM('HORAS PARADAS'!G33)","v":0},{"$f":"+SUM('HORAS PARADAS'!H33)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I33)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J33)","v":0},{"$f":"+SUM('HORAS PARADAS'!K33)","v":0},{"$f":"+SUM('HORAS PARADAS'!L33)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M33)","v":0},{"$f":"+SUM('HORAS PARADAS'!N33)","v":0},{"$f":"+SUM('HORAS PARADAS'!O33)","v":0},{"$f":"+SUM('HORAS PARADAS'!P33)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q33)","v":0},{"$f":"+SUM('HORAS PARADAS'!R33)","v":0},{"$f":"+SUM('HORAS PARADAS'!S33)","v":0},{"$f":"+SUM('HORAS PARADAS'!T33)","v":0},{"$f":"+SUM('HORAS PARADAS'!U33)","v":0},{"$f":"+SUM('HORAS PARADAS'!V33)","v":0},{"$f":"+SUM('HORAS PARADAS'!W33)","v":0},{"$f":"+SUM('HORAS PARADAS'!X33)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y33)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY33)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ33)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA33)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB33)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC33)","v":0}]
[0.05,"MOLIENDA",{"$f":"+SUM('HORAS PARADAS'!D34)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!E34)","v":0},{"$f":"+SUM('HORAS PARADAS'!F34)","v":0},{"$f":"+SUM('HORAS PARADAS'!G34)","v":0},{"$f":"+SUM('HORAS PARADAS'!H34)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!I34)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!J34)","v":0},{"$f":"+SUM('HORAS PARADAS'!K34)","v":0},{"$f":"+SUM('HORAS PARADAS'!L34)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!M34)","v":0},{"$f":"+SUM('HORAS PARADAS'!N34)","v":0},{"$f":"+SUM('HORAS PARADAS'!O34)","v":0},{"$f":"+SUM('HORAS PARADAS'!P34)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q34)","v":0},{"$f":"+SUM('HORAS PARADAS'!R34)","v":0},{"$f":"+SUM('HORAS PARADAS'!S34)","v":0},{"$f":"+SUM('HORAS PARADAS'!T34)","v":0},{"$f":"+SUM('HORAS PARADAS'!U34)","v":0},{"$f":"+SUM('HORAS PARADAS'!V34)","v":0},{"$f":"+SUM('HORAS PARADAS'!W34)","v":0},{"$f":"+SUM('HORAS PARADAS'!X34)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y34)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY34)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ34)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA34)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB34)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC34)","v":0}]
[0.15,"PLANTA DE CAL",{"$f":"+SUM('HORAS PARADAS'!D35)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!E35)","v":0},{"$f":"+SUM('HORAS PARADAS'!F35)","v":0},{"$f":"+SUM('HORAS PARADAS'!G35)","v":0},{"$f":"+SUM('HORAS PARADAS'!H35)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!I35)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!J35)","v":0},{"$f":"+SUM('HORAS PARADAS'!K35)","v":0},{"$f":"+SUM('HORAS PARADAS'!L35)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!M35)","v":0},{"$f":"+SUM('HORAS PARADAS'!N35)","v":0},{"$f":"+SUM('HORAS PARADAS'!O35)","v":0},{"$f":"+SUM('HORAS PARADAS'!P35)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q35)","v":0},{"$f":"+SUM('HORAS PARADAS'!R35)","v":0},{"$f":"+SUM('HORAS PARADAS'!S35)","v":0},{"$f":"+SUM('HORAS PARADAS'!T35)","v":0},{"$f":"+SUM('HORAS PARADAS'!U35)","v":0},{"$f":"+SUM('HORAS PARADAS'!V35)","v":0},{"$f":"+SUM('HORAS PARADAS'!W35)","v":0},{"$f":"+SUM('HORAS PARADAS'!X35)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y35)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY35)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ35)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA35)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB35)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC35)","v":0}]
[0.2,"ABASTECIMIENTO DE AGUA",{"$f":"+SUM('HORAS PARADAS'!D36)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E36)","v":0},{"$f":"+SUM('HORAS PARADAS'!F36)","v":0},{"$f":"+SUM('HORAS PARADAS'!G36)","v":0},{"$f":"+SUM('HORAS PARADAS'!H36)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I36)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J36)","v":0},{"$f":"+SUM('HORAS PARADAS'!K36)","v":0},{"$f":"+SUM('HORAS PARADAS'!L36)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M36)","v":0},{"$f":"+SUM('HORAS PARADAS'!N36)","v":0},{"$f":"+SUM('HORAS PARADAS'!O36)","v":0},{"$f":"+SUM('HORAS PARADAS'!P36)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q36)","v":0},{"$f":"+SUM('HORAS PARADAS'!R36)","v":0},{"$f":"+SUM('HORAS PARADAS'!S36)","v":0},{"$f":"+SUM('HORAS PARADAS'!T36)","v":0},{"$f":"+SUM('HORAS PARADAS'!U36)","v":0},{"$f":"+SUM('HORAS PARADAS'!V36)","v":0},{"$f":"+SUM('HORAS PARADAS'!W36)","v":0},{"$f":"+SUM('HORAS PARADAS'!X36)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y36)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY36)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ36)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA36)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB36)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC36)","v":0}]
[0.1,"REACTIVOS",{"$f":"+SUM('HORAS PARADAS'!D37)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!E37)","v":0},{"$f":"+SUM('HORAS PARADAS'!F37)","v":0},{"$f":"+SUM('HORAS PARADAS'!G37)","v":0},{"$f":"+SUM('HORAS PARADAS'!H37)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!I37)","v":1.2000000000000002},{"$f":"+SUM('HORAS PARADAS'!J37)","v":0},{"$f":"+SUM('HORAS PARADAS'!K37)","v":0},{"$f":"+SUM('HORAS PARADAS'!L37)","v":1.8},{"$f":"+SUM('HORAS PARADAS'!M37)","v":0},{"$f":"+SUM('HORAS PARADAS'!N37)","v":0},{"$f":"+SUM('HORAS PARADAS'!O37)","v":0},{"$f":"+SUM('HORAS PARADAS'!P37)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q37)","v":0},{"$f":"+SUM('HORAS PARADAS'!R37)","v":0},{"$f":"+SUM('HORAS PARADAS'!S37)","v":0},{"$f":"+SUM('HORAS PARADAS'!T37)","v":0},{"$f":"+SUM('HORAS PARADAS'!U37)","v":0},{"$f":"+SUM('HORAS PARADAS'!V37)","v":0},{"$f":"+SUM('HORAS PARADAS'!W37)","v":0},{"$f":"+SUM('HORAS PARADAS'!X37)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y37)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY37)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ37)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA37)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB37)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC37)","v":0}]
[null,"FLOTACION Pb",{"$f":"+SUM('HORAS PARADAS'!D38)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!E38)","v":0},{"$f":"+SUM('HORAS PARADAS'!F38)","v":0},{"$f":"+SUM('HORAS PARADAS'!G38)","v":0},{"$f":"+SUM('HORAS PARADAS'!H38)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I38)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J38)","v":0},{"$f":"+SUM('HORAS PARADAS'!K38)","v":0},{"$f":"+SUM('HORAS PARADAS'!L38)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!M38)","v":0},{"$f":"+SUM('HORAS PARADAS'!N38)","v":0},{"$f":"+SUM('HORAS PARADAS'!O38)","v":0},{"$f":"+SUM('HORAS PARADAS'!P38)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q38)","v":0},{"$f":"+SUM('HORAS PARADAS'!R38)","v":0},{"$f":"+SUM('HORAS PARADAS'!S38)","v":0},{"$f":"+SUM('HORAS PARADAS'!T38)","v":0},{"$f":"+SUM('HORAS PARADAS'!U38)","v":0},{"$f":"+SUM('HORAS PARADAS'!V38)","v":0},{"$f":"+SUM('HORAS PARADAS'!W38)","v":0},{"$f":"+SUM('HORAS PARADAS'!X38)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y38)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY38)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ38)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA38)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB38)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC38)","v":0}]
[null,"FLOTACION Cu",{"$f":"+SUM('HORAS PARADAS'!D39)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!E39)","v":0},{"$f":"+SUM('HORAS PARADAS'!F39)","v":0},{"$f":"+SUM('HORAS PARADAS'!G39)","v":0},{"$f":"+SUM('HORAS PARADAS'!H39)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I39)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J39)","v":0},{"$f":"+SUM('HORAS PARADAS'!K39)","v":0},{"$f":"+SUM('HORAS PARADAS'!L39)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!M39)","v":0},{"$f":"+SUM('HORAS PARADAS'!N39)","v":0},{"$f":"+SUM('HORAS PARADAS'!O39)","v":0},{"$f":"+SUM('HORAS PARADAS'!P39)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q39)","v":0},{"$f":"+SUM('HORAS PARADAS'!R39)","v":0},{"$f":"+SUM('HORAS PARADAS'!S39)","v":0},{"$f":"+SUM('HORAS PARADAS'!T39)","v":0},{"$f":"+SUM('HORAS PARADAS'!U39)","v":0},{"$f":"+SUM('HORAS PARADAS'!V39)","v":0},{"$f":"+SUM('HORAS PARADAS'!W39)","v":0},{"$f":"+SUM('HORAS PARADAS'!X39)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y39)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY39)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ39)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA39)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB39)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC39)","v":0}]
[null,"FLOTACION Zn",{"$f":"+SUM('HORAS PARADAS'!D40)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!E40)","v":0},{"$f":"+SUM('HORAS PARADAS'!F40)","v":0},{"$f":"+SUM('HORAS PARADAS'!G40)","v":0},{"$f":"+SUM('HORAS PARADAS'!H40)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I40)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J40)","v":0},{"$f":"+SUM('HORAS PARADAS'!K40)","v":0},{"$f":"+SUM('HORAS PARADAS'!L40)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!M40)","v":0},{"$f":"+SUM('HORAS PARADAS'!N40)","v":0},{"$f":"+SUM('HORAS PARADAS'!O40)","v":0},{"$f":"+SUM('HORAS PARADAS'!P40)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q40)","v":0},{"$f":"+SUM('HORAS PARADAS'!R40)","v":0},{"$f":"+SUM('HORAS PARADAS'!S40)","v":0},{"$f":"+SUM('HORAS PARADAS'!T40)","v":0},{"$f":"+SUM('HORAS PARADAS'!U40)","v":0},{"$f":"+SUM('HORAS PARADAS'!V40)","v":0},{"$f":"+SUM('HORAS PARADAS'!W40)","v":0},{"$f":"+SUM('HORAS PARADAS'!X40)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y40)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY40)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ40)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA40)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB40)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC40)","v":0}]
[null,"FLOTACION Bulk",{"$f":"+SUM('HORAS PARADAS'!D41)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!E41)","v":0},{"$f":"+SUM('HORAS PARADAS'!F41)","v":0},{"$f":"+SUM('HORAS PARADAS'!G41)","v":0},{"$f":"+SUM('HORAS PARADAS'!H41)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I41)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J41)","v":0},{"$f":"+SUM('HORAS PARADAS'!K41)","v":0},{"$f":"+SUM('HORAS PARADAS'!L41)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!M41)","v":0},{"$f":"+SUM('HORAS PARADAS'!N41)","v":0},{"$f":"+SUM('HORAS PARADAS'!O41)","v":0},{"$f":"+SUM('HORAS PARADAS'!P41)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q41)","v":0},{"$f":"+SUM('HORAS PARADAS'!R41)","v":0},{"$f":"+SUM('HORAS PARADAS'!S41)","v":0},{"$f":"+SUM('HORAS PARADAS'!T41)","v":0},{"$f":"+SUM('HORAS PARADAS'!U41)","v":0},{"$f":"+SUM('HORAS PARADAS'!V41)","v":0},{"$f":"+SUM('HORAS PARADAS'!W41)","v":0},{"$f":"+SUM('HORAS PARADAS'!X41)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y41)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY41)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ41)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA41)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB41)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC41)","v":0}]
[null,"ESPESADORES",{"$f":"+SUM('HORAS PARADAS'!D42)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E42)","v":0},{"$f":"+SUM('HORAS PARADAS'!F42)","v":0},{"$f":"+SUM('HORAS PARADAS'!G42)","v":0},{"$f":"+SUM('HORAS PARADAS'!H42)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I42)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J42)","v":0},{"$f":"+SUM('HORAS PARADAS'!K42)","v":0},{"$f":"+SUM('HORAS PARADAS'!L42)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M42)","v":0},{"$f":"+SUM('HORAS PARADAS'!N42)","v":0},{"$f":"+SUM('HORAS PARADAS'!O42)","v":0},{"$f":"+SUM('HORAS PARADAS'!P42)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q42)","v":0},{"$f":"+SUM('HORAS PARADAS'!R42)","v":0},{"$f":"+SUM('HORAS PARADAS'!S42)","v":0},{"$f":"+SUM('HORAS PARADAS'!T42)","v":0},{"$f":"+SUM('HORAS PARADAS'!U42)","v":0},{"$f":"+SUM('HORAS PARADAS'!V42)","v":0},{"$f":"+SUM('HORAS PARADAS'!W42)","v":0},{"$f":"+SUM('HORAS PARADAS'!X42)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y42)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY42)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ42)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA42)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB42)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC42)","v":0}]
[null,"FILTRADO Pb",{"$f":"+SUM('HORAS PARADAS'!D43)","v":3.84},{"$f":"+SUM('HORAS PARADAS'!E43)","v":0},{"$f":"+SUM('HORAS PARADAS'!F43)","v":0},{"$f":"+SUM('HORAS PARADAS'!G43)","v":0},{"$f":"+SUM('HORAS PARADAS'!H43)","v":1.92},{"$f":"+SUM('HORAS PARADAS'!I43)","v":1.92},{"$f":"+SUM('HORAS PARADAS'!J43)","v":0},{"$f":"+SUM('HORAS PARADAS'!K43)","v":0},{"$f":"+SUM('HORAS PARADAS'!L43)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!M43)","v":0},{"$f":"+SUM('HORAS PARADAS'!N43)","v":0},{"$f":"+SUM('HORAS PARADAS'!O43)","v":0},{"$f":"+SUM('HORAS PARADAS'!P43)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q43)","v":0},{"$f":"+SUM('HORAS PARADAS'!R43)","v":0},{"$f":"+SUM('HORAS PARADAS'!S43)","v":0},{"$f":"+SUM('HORAS PARADAS'!T43)","v":0},{"$f":"+SUM('HORAS PARADAS'!U43)","v":0},{"$f":"+SUM('HORAS PARADAS'!V43)","v":0},{"$f":"+SUM('HORAS PARADAS'!W43)","v":0},{"$f":"+SUM('HORAS PARADAS'!X43)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y43)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY43)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ43)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA43)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB43)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC43)","v":0}]
[null,"FILTRADO Cu",{"$f":"+SUM('HORAS PARADAS'!D44)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!E44)","v":0},{"$f":"+SUM('HORAS PARADAS'!F44)","v":0},{"$f":"+SUM('HORAS PARADAS'!G44)","v":0},{"$f":"+SUM('HORAS PARADAS'!H44)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I44)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J44)","v":0},{"$f":"+SUM('HORAS PARADAS'!K44)","v":0},{"$f":"+SUM('HORAS PARADAS'!L44)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!M44)","v":0},{"$f":"+SUM('HORAS PARADAS'!N44)","v":0},{"$f":"+SUM('HORAS PARADAS'!O44)","v":0},{"$f":"+SUM('HORAS PARADAS'!P44)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q44)","v":0},{"$f":"+SUM('HORAS PARADAS'!R44)","v":0},{"$f":"+SUM('HORAS PARADAS'!S44)","v":0},{"$f":"+SUM('HORAS PARADAS'!T44)","v":0},{"$f":"+SUM('HORAS PARADAS'!U44)","v":0},{"$f":"+SUM('HORAS PARADAS'!V44)","v":0},{"$f":"+SUM('HORAS PARADAS'!W44)","v":0},{"$f":"+SUM('HORAS PARADAS'!X44)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y44)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY44)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ44)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA44)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB44)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC44)","v":0}]
[null,"FILTRADO Zn",{"$f":"+SUM('HORAS PARADAS'!D45)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!E45)","v":0},{"$f":"+SUM('HORAS PARADAS'!F45)","v":0},{"$f":"+SUM('HORAS PARADAS'!G45)","v":0},{"$f":"+SUM('HORAS PARADAS'!H45)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I45)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J45)","v":0},{"$f":"+SUM('HORAS PARADAS'!K45)","v":0},{"$f":"+SUM('HORAS PARADAS'!L45)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!M45)","v":0},{"$f":"+SUM('HORAS PARADAS'!N45)","v":0},{"$f":"+SUM('HORAS PARADAS'!O45)","v":0},{"$f":"+SUM('HORAS PARADAS'!P45)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q45)","v":0},{"$f":"+SUM('HORAS PARADAS'!R45)","v":0},{"$f":"+SUM('HORAS PARADAS'!S45)","v":0},{"$f":"+SUM('HORAS PARADAS'!T45)","v":0},{"$f":"+SUM('HORAS PARADAS'!U45)","v":0},{"$f":"+SUM('HORAS PARADAS'!V45)","v":0},{"$f":"+SUM('HORAS PARADAS'!W45)","v":0},{"$f":"+SUM('HORAS PARADAS'!X45)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y45)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY45)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ45)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA45)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB45)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC45)","v":0}]
[null,"FILTRADO Bulk",{"$f":"+SUM('HORAS PARADAS'!D46)","v":4.800000000000001},{"$f":"+SUM('HORAS PARADAS'!E46)","v":0},{"$f":"+SUM('HORAS PARADAS'!F46)","v":0},{"$f":"+SUM('HORAS PARADAS'!G46)","v":0},{"$f":"+SUM('HORAS PARADAS'!H46)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!I46)","v":2.4000000000000004},{"$f":"+SUM('HORAS PARADAS'!J46)","v":0},{"$f":"+SUM('HORAS PARADAS'!K46)","v":0},{"$f":"+SUM('HORAS PARADAS'!L46)","v":3.6},{"$f":"+SUM('HORAS PARADAS'!M46)","v":0},{"$f":"+SUM('HORAS PARADAS'!N46)","v":0},{"$f":"+SUM('HORAS PARADAS'!O46)","v":0},{"$f":"+SUM('HORAS PARADAS'!P46)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q46)","v":0},{"$f":"+SUM('HORAS PARADAS'!R46)","v":0},{"$f":"+SUM('HORAS PARADAS'!S46)","v":0},{"$f":"+SUM('HORAS PARADAS'!T46)","v":0},{"$f":"+SUM('HORAS PARADAS'!U46)","v":0},{"$f":"+SUM('HORAS PARADAS'!V46)","v":0},{"$f":"+SUM('HORAS PARADAS'!W46)","v":0},{"$f":"+SUM('HORAS PARADAS'!X46)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y46)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY46)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ46)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA46)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB46)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC46)","v":0}]
[null,"PLANTA DE NEUTRALIZACION",{"$f":"+SUM('HORAS PARADAS'!D47)","v":5.76},{"$f":"+SUM('HORAS PARADAS'!E47)","v":0},{"$f":"+SUM('HORAS PARADAS'!F47)","v":0},{"$f":"+SUM('HORAS PARADAS'!G47)","v":0},{"$f":"+SUM('HORAS PARADAS'!H47)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!I47)","v":2.88},{"$f":"+SUM('HORAS PARADAS'!J47)","v":0},{"$f":"+SUM('HORAS PARADAS'!K47)","v":0},{"$f":"+SUM('HORAS PARADAS'!L47)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!M47)","v":0},{"$f":"+SUM('HORAS PARADAS'!N47)","v":0},{"$f":"+SUM('HORAS PARADAS'!O47)","v":0},{"$f":"+SUM('HORAS PARADAS'!P47)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q47)","v":0},{"$f":"+SUM('HORAS PARADAS'!R47)","v":0},{"$f":"+SUM('HORAS PARADAS'!S47)","v":0},{"$f":"+SUM('HORAS PARADAS'!T47)","v":0},{"$f":"+SUM('HORAS PARADAS'!U47)","v":0},{"$f":"+SUM('HORAS PARADAS'!V47)","v":0},{"$f":"+SUM('HORAS PARADAS'!W47)","v":0},{"$f":"+SUM('HORAS PARADAS'!X47)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y47)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY47)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ47)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA47)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB47)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC47)","v":0}]
[null,"BOMBAS DE RELAVE",{"$f":"+SUM('HORAS PARADAS'!D48)","v":8.64},{"$f":"+SUM('HORAS PARADAS'!E48)","v":0},{"$f":"+SUM('HORAS PARADAS'!F48)","v":0},{"$f":"+SUM('HORAS PARADAS'!G48)","v":0},{"$f":"+SUM('HORAS PARADAS'!H48)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!I48)","v":4.32},{"$f":"+SUM('HORAS PARADAS'!J48)","v":0},{"$f":"+SUM('HORAS PARADAS'!K48)","v":0},{"$f":"+SUM('HORAS PARADAS'!L48)","v":6.4799999999999995},{"$f":"+SUM('HORAS PARADAS'!M48)","v":0},{"$f":"+SUM('HORAS PARADAS'!N48)","v":0},{"$f":"+SUM('HORAS PARADAS'!O48)","v":0},{"$f":"+SUM('HORAS PARADAS'!P48)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q48)","v":0},{"$f":"+SUM('HORAS PARADAS'!R48)","v":0},{"$f":"+SUM('HORAS PARADAS'!S48)","v":0},{"$f":"+SUM('HORAS PARADAS'!T48)","v":0},{"$f":"+SUM('HORAS PARADAS'!U48)","v":0},{"$f":"+SUM('HORAS PARADAS'!V48)","v":0},{"$f":"+SUM('HORAS PARADAS'!W48)","v":0},{"$f":"+SUM('HORAS PARADAS'!X48)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y48)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY48)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ48)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA48)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB48)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC48)","v":0}]
[null,"HORAS PARADA PREVENTIVO",{"$f":"+SUM('HORAS PARADAS'!D49)","v":95.99999999999999},{"$f":"+SUM('HORAS PARADAS'!E49)","v":0},{"$f":"+SUM('HORAS PARADAS'!F49)","v":0},{"$f":"+SUM('HORAS PARADAS'!G49)","v":0},{"$f":"+SUM('HORAS PARADAS'!H49)","v":47.99999999999999},{"$f":"+SUM('HORAS PARADAS'!I49)","v":47.99999999999999},{"$f":"+SUM('HORAS PARADAS'!J49)","v":0},{"$f":"+SUM('HORAS PARADAS'!K49)","v":0},{"$f":"+SUM('HORAS PARADAS'!L49)","v":72.00000000000001},{"$f":"+SUM('HORAS PARADAS'!M49)","v":0},{"$f":"+SUM('HORAS PARADAS'!N49)","v":0},{"$f":"+SUM('HORAS PARADAS'!O49)","v":0},{"$f":"+SUM('HORAS PARADAS'!P49)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q49)","v":0},{"$f":"+SUM('HORAS PARADAS'!R49)","v":0},{"$f":"+SUM('HORAS PARADAS'!S49)","v":0},{"$f":"+SUM('HORAS PARADAS'!T49)","v":0},{"$f":"+SUM('HORAS PARADAS'!U49)","v":0},{"$f":"+SUM('HORAS PARADAS'!V49)","v":0},{"$f":"+SUM('HORAS PARADAS'!W49)","v":0},{"$f":"+SUM('HORAS PARADAS'!X49)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y49)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY49)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ49)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA49)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB49)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC49)","v":0}]
[null,"HORAS TOTAL MEJORA"]
[null,"HORAS OPERACIÓN",{"$f":"(24*C10-C76-C77)","v":{"v":72.00000000000001,"d":"72"}},{"$f":"(24*D10-D76-D77)","v":168},168,168,120,120,168,168,{"v":95.99999999999999,"d":"96"},{"$f":"(24*L10-L76-L77)","v":168},168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168]
[null,"HORAS REPARACION",{"$f":"IFERROR(+(C$78/$J$1)*$M$1,0)","v":{"v":1.8830769230769235,"d":"2"}},{"$f":"IFERROR(+(D$78/$J$1)*$M$1,0)","v":{"v":4.393846153846154,"d":"4"}},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":3.1384615384615384,"d":"3"},{"v":3.1384615384615384,"d":"3"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":2.5107692307692306,"d":"3"},{"$f":"IFERROR(+(L$78/$J$1)*$M$1,0)","v":{"v":4.393846153846154,"d":"4"}},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},3,{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"},{"v":4.393846153846154,"d":"4"}]
[]
[{"$f":"+A36","v":0.07},{"$f":"+B58","v":"CHANCADO PRIMARIO"},{"$f":"+$A81*C$79","v":{"v":0.13181538461538467,"d":"0.1"}},{"$f":"+$A81*D$79","v":{"v":0.3075692307692308,"d":"0.3"}},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.17575384615384615,"d":"0.2"},{"$f":"+$A81*L$79","v":{"v":0.3075692307692308,"d":"0.3"}},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21000000000000002,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"}]
[{"$f":"+A37","v":0.07},{"$f":"+B59","v":"CHANCADO SECUNDARIO"},{"v":0.13181538461538467,"d":"0.1"},{"$f":"+$A82*D$79","v":{"v":0.3075692307692308,"d":"0.3"}},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.17575384615384615,"d":"0.2"},{"$f":"+$A82*L$79","v":{"v":0.3075692307692308,"d":"0.3"}},{"$f":"+$A82*M$79","v":{"v":0.3075692307692308,"d":"0.3"}},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21000000000000002,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"}]
[0.07,"CHANCADO TERCIARIO",{"v":0.13181538461538467,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21000000000000002,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"}]
[0.06,"MOLIENDA",{"v":0.1129846153846154,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"$f":"+$A84*F$79","v":{"v":0.2636307692307693,"d":"0.3"}},{"v":0.1883076923076923,"d":"0.2"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.55,"d":"0.6"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.15064615384615385,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.18,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"}]
[0.025,"PLANTA DE CAL",{"v":0.04707692307692309,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.06276923076923077,"d":"0.1"},{"$f":"+$A85*L$79","v":{"v":0.10984615384615387,"d":"0.1"}},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.07500000000000001,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"}]
[0.07,"ABASTECIMIENTO DE AGUA",{"v":0.13181538461538467,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"$f":"+$A86*S$79","v":{"v":0.3075692307692308,"d":"0.3"}},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21000000000000002,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"}]
[0.025,"REACTIVOS",{"v":0.04707692307692309,"d":"0.0"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.07846153846153847,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.06276923076923077,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.07500000000000001,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"},{"v":0.10984615384615387,"d":"0.1"}]
[0.05,"FLOTACION Pb",{"v":0.09415384615384619,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15000000000000002,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.05,"FLOTACION Cu",{"v":0.09415384615384619,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15000000000000002,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.05,"FLOTACION Zn",{"v":0.09415384615384619,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15000000000000002,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.05,"FLOTACION Bulk",{"v":0.09415384615384619,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"$f":"+$A91*S$79","v":{"v":0.21969230769230774,"d":"0.2"}},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15000000000000002,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.07,"ESPESADORES",{"v":0.13181538461538467,"d":"0.1"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.21969230769230771,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.17575384615384615,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.21000000000000002,"d":"0.2"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"},{"v":0.3075692307692308,"d":"0.3"}]
[0.04,"FILTRADO Pb",{"v":0.07532307692307694,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.10043076923076923,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.12,"d":"0.1"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"},{"v":0.17575384615384618,"d":"0.2"}]
[0.05,"FILTRADO Cu",{"v":0.09415384615384619,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15000000000000002,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.05,"FILTRADO Zn",{"v":0.09415384615384619,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15000000000000002,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.05,"FILTRADO Bulk",{"v":0.09415384615384619,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.15692307692307694,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.12553846153846154,"d":"0.1"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"$f":"+$A96*S$79","v":{"v":0.21969230769230774,"d":"0.2"}},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.15000000000000002,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"},{"v":0.21969230769230774,"d":"0.2"}]
[0.06,"PLANTA DE NEUTRALIZACION",{"v":0.1129846153846154,"d":"0.1"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.1883076923076923,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.15064615384615385,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.18,"d":"0.2"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"},{"v":0.2636307692307693,"d":"0.3"}]
[0.09,"BOMBAS DE RELAVE",{"v":0.1694769230769231,"d":"0.2"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.28246153846153843,"d":"0.3"},{"v":0.28246153846153843,"d":"0.3"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.22596923076923076,"d":"0.2"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.27,"d":"0.3"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"},{"v":0.3954461538461539,"d":"0.4"}]
[null,"HORAS PARADA CORRECTIVO",{"$f":"C81+C82+C83+C84+C85+C86+C87+IFERROR(1/(IFERROR(1/C88,0)+IFERROR(1/C89,0)+IFERROR(1/C90,0)+IFERROR(1/C91,0)),0)+C92+IFERROR(1/(IFERROR(1/C93,0)+IFERROR(1/C94,0)+IFERROR(1/C95,0)+IFERROR(1/C96,0)),0)+C97+C98","v":{"v":1.1943692307692313,"d":"1.19"}},{"$f":"D81+D82+D83+D84+D85+D86+D87+IFERROR(1/(IFERROR(1/D88,0)+IFERROR(1/D89,0)+IFERROR(1/D90,0)+IFERROR(1/D91,0)),0)+D92+IFERROR(1/(IFERROR(1/D93,0)+IFERROR(1/D94,0)+IFERROR(1/D95,0)+IFERROR(1/D96,0)),0)+D97+D98","v":{"v":2.786861538461539,"d":"2.79"}},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":1.9906153846153845,"d":"1.99"},{"v":1.9906153846153845,"d":"1.99"},{"v":3.07323076923077,"d":"3.07"},{"v":2.786861538461539,"d":"2.79"},{"v":1.5924923076923077,"d":"1.59"},{"$f":"L81+L82+L83+L84+L85+L86+L87+IFERROR(1/(IFERROR(1/L88,0)+IFERROR(1/L89,0)+IFERROR(1/L90,0)+IFERROR(1/L91,0)),0)+L92+IFERROR(1/(IFERROR(1/L93,0)+IFERROR(1/L94,0)+IFERROR(1/L95,0)+IFERROR(1/L96,0)),0)+L97+L98","v":{"v":2.786861538461539,"d":"2.79"}},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":1.9027941176470589,"d":"1.90"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"},{"v":2.786861538461539,"d":"2.79"}]
[]
[null,"HORAS REALES",{"$f":"+C56","v":"SEM01"},{"$f":"+D56","v":"SEM02"},"SEM03","SEM04","SEM05","SEM06","SEM07","SEM08","SEM09","SEM10","SEM11","SEM12","SEM13","SEM14","SEM15","SEM16","SEM17","SEM18","SEM19","SEM20","SEM21","SEM22","SEM23","SEM24","SEM25","SEM26","SEM27","SEM28","SEM29","SEM30","SEM31","SEM32","SEM33","SEM34","SEM35","SEM36","SEM37","SEM38","SEM39","SEM40","SEM41","SEM42","SEM43","SEM44","SEM45","SEM46","SEM47","SEM48","SEM49","SEM50","SEM51","SEM52"]
[0.2,"TOTAL",{"$f":"+C55*24","v":168},{"$f":"+D55*24","v":168},168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,{"$f":"+AZ55*24","v":168},168,168]
[null,{"$f":"+B58","v":"CHANCADO PRIMARIO"},{"$f":"+SUM('HORAS PARADAS'!D55)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E55)","v":0},{"$f":"+SUM('HORAS PARADAS'!F55)","v":0},{"$f":"+SUM('HORAS PARADAS'!G55)","v":0},{"$f":"+SUM('HORAS PARADAS'!H55)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I55)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J55)","v":0},{"$f":"+SUM('HORAS PARADAS'!K55)","v":0},{"$f":"+SUM('HORAS PARADAS'!L55)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M55)","v":0},{"$f":"+SUM('HORAS PARADAS'!N55)","v":0},{"$f":"+SUM('HORAS PARADAS'!O55)","v":0},{"$f":"+SUM('HORAS PARADAS'!P55)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q55)","v":0},{"$f":"+SUM('HORAS PARADAS'!R55)","v":0},{"$f":"+SUM('HORAS PARADAS'!S55)","v":0},{"$f":"+SUM('HORAS PARADAS'!T55)","v":0},{"$f":"+SUM('HORAS PARADAS'!U55)","v":0},{"$f":"+SUM('HORAS PARADAS'!V55)","v":0},{"$f":"+SUM('HORAS PARADAS'!W55)","v":0},{"$f":"+SUM('HORAS PARADAS'!X55)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y55)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY55)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ55)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA55)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB55)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC55)","v":0}]
[0.2,"CHANCADO SECUNDARIO",{"$f":"+SUM('HORAS PARADAS'!D56)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E56)","v":0},{"$f":"+SUM('HORAS PARADAS'!F56)","v":0},{"$f":"+SUM('HORAS PARADAS'!G56)","v":0},{"$f":"+SUM('HORAS PARADAS'!H56)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I56)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J56)","v":0},{"$f":"+SUM('HORAS PARADAS'!K56)","v":0},{"$f":"+SUM('HORAS PARADAS'!L56)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M56)","v":0},{"$f":"+SUM('HORAS PARADAS'!N56)","v":0},{"$f":"+SUM('HORAS PARADAS'!O56)","v":0},{"$f":"+SUM('HORAS PARADAS'!P56)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q56)","v":0},{"$f":"+SUM('HORAS PARADAS'!R56)","v":0},{"$f":"+SUM('HORAS PARADAS'!S56)","v":0},{"$f":"+SUM('HORAS PARADAS'!T56)","v":0},{"$f":"+SUM('HORAS PARADAS'!U56)","v":0},{"$f":"+SUM('HORAS PARADAS'!V56)","v":0},{"$f":"+SUM('HORAS PARADAS'!W56)","v":0},{"$f":"+SUM('HORAS PARADAS'!X56)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y56)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY56)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ56)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA56)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB56)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC56)","v":0}]
[0.2,"CHANCADO TERCIARIO",{"$f":"+SUM('HORAS PARADAS'!D57)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E57)","v":0},{"$f":"+SUM('HORAS PARADAS'!F57)","v":0},{"$f":"+SUM('HORAS PARADAS'!G57)","v":0},{"$f":"+SUM('HORAS PARADAS'!H57)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I57)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J57)","v":0},{"$f":"+SUM('HORAS PARADAS'!K57)","v":0},{"$f":"+SUM('HORAS PARADAS'!L57)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M57)","v":0},{"$f":"+SUM('HORAS PARADAS'!N57)","v":0},{"$f":"+SUM('HORAS PARADAS'!O57)","v":0},{"$f":"+SUM('HORAS PARADAS'!P57)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q57)","v":0},{"$f":"+SUM('HORAS PARADAS'!R57)","v":0},{"$f":"+SUM('HORAS PARADAS'!S57)","v":0},{"$f":"+SUM('HORAS PARADAS'!T57)","v":0},{"$f":"+SUM('HORAS PARADAS'!U57)","v":0},{"$f":"+SUM('HORAS PARADAS'!V57)","v":0},{"$f":"+SUM('HORAS PARADAS'!W57)","v":0},{"$f":"+SUM('HORAS PARADAS'!X57)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y57)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY57)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ57)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA57)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB57)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC57)","v":0}]
[0.1,"MOLIENDA",{"$f":"+SUM('HORAS PARADAS'!D58)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E58)","v":0},{"$f":"+SUM('HORAS PARADAS'!F58)","v":0},{"$f":"+SUM('HORAS PARADAS'!G58)","v":0},{"$f":"+SUM('HORAS PARADAS'!H58)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I58)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J58)","v":0},{"$f":"+SUM('HORAS PARADAS'!K58)","v":0},{"$f":"+SUM('HORAS PARADAS'!L58)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M58)","v":0},{"$f":"+SUM('HORAS PARADAS'!N58)","v":0},{"$f":"+SUM('HORAS PARADAS'!O58)","v":0},{"$f":"+SUM('HORAS PARADAS'!P58)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q58)","v":0},{"$f":"+SUM('HORAS PARADAS'!R58)","v":0},{"$f":"+SUM('HORAS PARADAS'!S58)","v":0},{"$f":"+SUM('HORAS PARADAS'!T58)","v":0},{"$f":"+SUM('HORAS PARADAS'!U58)","v":0},{"$f":"+SUM('HORAS PARADAS'!V58)","v":0},{"$f":"+SUM('HORAS PARADAS'!W58)","v":0},{"$f":"+SUM('HORAS PARADAS'!X58)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y58)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY58)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ58)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA58)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB58)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC58)","v":0}]
[0.05,"PLANTA DE CAL",{"$f":"+SUM('HORAS PARADAS'!D59)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E59)","v":0},{"$f":"+SUM('HORAS PARADAS'!F59)","v":0},{"$f":"+SUM('HORAS PARADAS'!G59)","v":0},{"$f":"+SUM('HORAS PARADAS'!H59)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I59)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J59)","v":0},{"$f":"+SUM('HORAS PARADAS'!K59)","v":0},{"$f":"+SUM('HORAS PARADAS'!L59)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M59)","v":0},{"$f":"+SUM('HORAS PARADAS'!N59)","v":0},{"$f":"+SUM('HORAS PARADAS'!O59)","v":0},{"$f":"+SUM('HORAS PARADAS'!P59)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q59)","v":0},{"$f":"+SUM('HORAS PARADAS'!R59)","v":0},{"$f":"+SUM('HORAS PARADAS'!S59)","v":0},{"$f":"+SUM('HORAS PARADAS'!T59)","v":0},{"$f":"+SUM('HORAS PARADAS'!U59)","v":0},{"$f":"+SUM('HORAS PARADAS'!V59)","v":0},{"$f":"+SUM('HORAS PARADAS'!W59)","v":0},{"$f":"+SUM('HORAS PARADAS'!X59)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y59)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY59)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ59)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA59)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB59)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC59)","v":0}]
[0.15,"ABASTECIMIENTO DE AGUA",{"$f":"+SUM('HORAS PARADAS'!D60)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E60)","v":0},{"$f":"+SUM('HORAS PARADAS'!F60)","v":0},{"$f":"+SUM('HORAS PARADAS'!G60)","v":0},{"$f":"+SUM('HORAS PARADAS'!H60)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I60)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J60)","v":0},{"$f":"+SUM('HORAS PARADAS'!K60)","v":0},{"$f":"+SUM('HORAS PARADAS'!L60)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M60)","v":0},{"$f":"+SUM('HORAS PARADAS'!N60)","v":0},{"$f":"+SUM('HORAS PARADAS'!O60)","v":0},{"$f":"+SUM('HORAS PARADAS'!P60)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q60)","v":0},{"$f":"+SUM('HORAS PARADAS'!R60)","v":0},{"$f":"+SUM('HORAS PARADAS'!S60)","v":0},{"$f":"+SUM('HORAS PARADAS'!T60)","v":0},{"$f":"+SUM('HORAS PARADAS'!U60)","v":0},{"$f":"+SUM('HORAS PARADAS'!V60)","v":0},{"$f":"+SUM('HORAS PARADAS'!W60)","v":0},{"$f":"+SUM('HORAS PARADAS'!X60)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y60)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY60)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ60)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA60)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB60)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC60)","v":0}]
[0.2,"REACTIVOS",{"$f":"+SUM('HORAS PARADAS'!D61)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E61)","v":0},{"$f":"+SUM('HORAS PARADAS'!F61)","v":0},{"$f":"+SUM('HORAS PARADAS'!G61)","v":0},{"$f":"+SUM('HORAS PARADAS'!H61)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I61)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J61)","v":0},{"$f":"+SUM('HORAS PARADAS'!K61)","v":0},{"$f":"+SUM('HORAS PARADAS'!L61)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M61)","v":0},{"$f":"+SUM('HORAS PARADAS'!N61)","v":0},{"$f":"+SUM('HORAS PARADAS'!O61)","v":0},{"$f":"+SUM('HORAS PARADAS'!P61)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q61)","v":0},{"$f":"+SUM('HORAS PARADAS'!R61)","v":0},{"$f":"+SUM('HORAS PARADAS'!S61)","v":0},{"$f":"+SUM('HORAS PARADAS'!T61)","v":0},{"$f":"+SUM('HORAS PARADAS'!U61)","v":0},{"$f":"+SUM('HORAS PARADAS'!V61)","v":0},{"$f":"+SUM('HORAS PARADAS'!W61)","v":0},{"$f":"+SUM('HORAS PARADAS'!X61)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y61)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY61)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ61)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA61)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB61)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC61)","v":0}]
[0.1,"FLOTACION Pb",{"$f":"+SUM('HORAS PARADAS'!D62)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E62)","v":0},{"$f":"+SUM('HORAS PARADAS'!F62)","v":0},{"$f":"+SUM('HORAS PARADAS'!G62)","v":0},{"$f":"+SUM('HORAS PARADAS'!H62)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I62)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J62)","v":0},{"$f":"+SUM('HORAS PARADAS'!K62)","v":0},{"$f":"+SUM('HORAS PARADAS'!L62)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M62)","v":0},{"$f":"+SUM('HORAS PARADAS'!N62)","v":0},{"$f":"+SUM('HORAS PARADAS'!O62)","v":0},{"$f":"+SUM('HORAS PARADAS'!P62)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q62)","v":0},{"$f":"+SUM('HORAS PARADAS'!R62)","v":0},{"$f":"+SUM('HORAS PARADAS'!S62)","v":0},{"$f":"+SUM('HORAS PARADAS'!T62)","v":0},{"$f":"+SUM('HORAS PARADAS'!U62)","v":0},{"$f":"+SUM('HORAS PARADAS'!V62)","v":0},{"$f":"+SUM('HORAS PARADAS'!W62)","v":0},{"$f":"+SUM('HORAS PARADAS'!X62)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y62)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY62)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ62)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA62)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB62)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC62)","v":0}]
[null,"FLOTACION Cu",{"$f":"+SUM('HORAS PARADAS'!D63)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E63)","v":0},{"$f":"+SUM('HORAS PARADAS'!F63)","v":0},{"$f":"+SUM('HORAS PARADAS'!G63)","v":0},{"$f":"+SUM('HORAS PARADAS'!H63)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I63)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J63)","v":0},{"$f":"+SUM('HORAS PARADAS'!K63)","v":0},{"$f":"+SUM('HORAS PARADAS'!L63)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M63)","v":0},{"$f":"+SUM('HORAS PARADAS'!N63)","v":0},{"$f":"+SUM('HORAS PARADAS'!O63)","v":0},{"$f":"+SUM('HORAS PARADAS'!P63)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q63)","v":0},{"$f":"+SUM('HORAS PARADAS'!R63)","v":0},{"$f":"+SUM('HORAS PARADAS'!S63)","v":0},{"$f":"+SUM('HORAS PARADAS'!T63)","v":0},{"$f":"+SUM('HORAS PARADAS'!U63)","v":0},{"$f":"+SUM('HORAS PARADAS'!V63)","v":0},{"$f":"+SUM('HORAS PARADAS'!W63)","v":0},{"$f":"+SUM('HORAS PARADAS'!X63)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y63)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY63)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ63)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA63)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB63)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC63)","v":0}]
[null,"FLOTACION Zn",{"$f":"+SUM('HORAS PARADAS'!D64)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E64)","v":0},{"$f":"+SUM('HORAS PARADAS'!F64)","v":0},{"$f":"+SUM('HORAS PARADAS'!G64)","v":0},{"$f":"+SUM('HORAS PARADAS'!H64)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I64)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J64)","v":0},{"$f":"+SUM('HORAS PARADAS'!K64)","v":0},{"$f":"+SUM('HORAS PARADAS'!L64)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M64)","v":0},{"$f":"+SUM('HORAS PARADAS'!N64)","v":0},{"$f":"+SUM('HORAS PARADAS'!O64)","v":0},{"$f":"+SUM('HORAS PARADAS'!P64)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q64)","v":0},{"$f":"+SUM('HORAS PARADAS'!R64)","v":0},{"$f":"+SUM('HORAS PARADAS'!S64)","v":0},{"$f":"+SUM('HORAS PARADAS'!T64)","v":0},{"$f":"+SUM('HORAS PARADAS'!U64)","v":0},{"$f":"+SUM('HORAS PARADAS'!V64)","v":0},{"$f":"+SUM('HORAS PARADAS'!W64)","v":0},{"$f":"+SUM('HORAS PARADAS'!X64)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y64)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY64)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ64)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA64)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB64)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC64)","v":0}]
[null,"FLOTACION Bulk",{"$f":"+SUM('HORAS PARADAS'!D65)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E65)","v":0},{"$f":"+SUM('HORAS PARADAS'!F65)","v":0},{"$f":"+SUM('HORAS PARADAS'!G65)","v":0},{"$f":"+SUM('HORAS PARADAS'!H65)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I65)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J65)","v":0},{"$f":"+SUM('HORAS PARADAS'!K65)","v":0},{"$f":"+SUM('HORAS PARADAS'!L65)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M65)","v":0},{"$f":"+SUM('HORAS PARADAS'!N65)","v":0},{"$f":"+SUM('HORAS PARADAS'!O65)","v":0},{"$f":"+SUM('HORAS PARADAS'!P65)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q65)","v":0},{"$f":"+SUM('HORAS PARADAS'!R65)","v":0},{"$f":"+SUM('HORAS PARADAS'!S65)","v":0},{"$f":"+SUM('HORAS PARADAS'!T65)","v":0},{"$f":"+SUM('HORAS PARADAS'!U65)","v":0},{"$f":"+SUM('HORAS PARADAS'!V65)","v":0},{"$f":"+SUM('HORAS PARADAS'!W65)","v":0},{"$f":"+SUM('HORAS PARADAS'!X65)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y65)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY65)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ65)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA65)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB65)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC65)","v":0}]
[null,"ESPESADORES",{"$f":"+SUM('HORAS PARADAS'!D66)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E66)","v":0},{"$f":"+SUM('HORAS PARADAS'!F66)","v":0},{"$f":"+SUM('HORAS PARADAS'!G66)","v":0},{"$f":"+SUM('HORAS PARADAS'!H66)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I66)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J66)","v":0},{"$f":"+SUM('HORAS PARADAS'!K66)","v":0},{"$f":"+SUM('HORAS PARADAS'!L66)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M66)","v":0},{"$f":"+SUM('HORAS PARADAS'!N66)","v":0},{"$f":"+SUM('HORAS PARADAS'!O66)","v":0},{"$f":"+SUM('HORAS PARADAS'!P66)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q66)","v":0},{"$f":"+SUM('HORAS PARADAS'!R66)","v":0},{"$f":"+SUM('HORAS PARADAS'!S66)","v":0},{"$f":"+SUM('HORAS PARADAS'!T66)","v":0},{"$f":"+SUM('HORAS PARADAS'!U66)","v":0},{"$f":"+SUM('HORAS PARADAS'!V66)","v":0},{"$f":"+SUM('HORAS PARADAS'!W66)","v":0},{"$f":"+SUM('HORAS PARADAS'!X66)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y66)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY66)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ66)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA66)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB66)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC66)","v":0}]
[null,"FILTRADO Pb",{"$f":"+SUM('HORAS PARADAS'!D67)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E67)","v":0},{"$f":"+SUM('HORAS PARADAS'!F67)","v":0},{"$f":"+SUM('HORAS PARADAS'!G67)","v":0},{"$f":"+SUM('HORAS PARADAS'!H67)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I67)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J67)","v":0},{"$f":"+SUM('HORAS PARADAS'!K67)","v":0},{"$f":"+SUM('HORAS PARADAS'!L67)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M67)","v":0},{"$f":"+SUM('HORAS PARADAS'!N67)","v":0},{"$f":"+SUM('HORAS PARADAS'!O67)","v":0},{"$f":"+SUM('HORAS PARADAS'!P67)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q67)","v":0},{"$f":"+SUM('HORAS PARADAS'!R67)","v":0},{"$f":"+SUM('HORAS PARADAS'!S67)","v":0},{"$f":"+SUM('HORAS PARADAS'!T67)","v":0},{"$f":"+SUM('HORAS PARADAS'!U67)","v":0},{"$f":"+SUM('HORAS PARADAS'!V67)","v":0},{"$f":"+SUM('HORAS PARADAS'!W67)","v":0},{"$f":"+SUM('HORAS PARADAS'!X67)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y67)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY67)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ67)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA67)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB67)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC67)","v":0}]
[null,"FILTRADO Cu",{"$f":"+SUM('HORAS PARADAS'!D68)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E68)","v":0},{"$f":"+SUM('HORAS PARADAS'!F68)","v":0},{"$f":"+SUM('HORAS PARADAS'!G68)","v":0},{"$f":"+SUM('HORAS PARADAS'!H68)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I68)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J68)","v":0},{"$f":"+SUM('HORAS PARADAS'!K68)","v":0},{"$f":"+SUM('HORAS PARADAS'!L68)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M68)","v":0},{"$f":"+SUM('HORAS PARADAS'!N68)","v":0},{"$f":"+SUM('HORAS PARADAS'!O68)","v":0},{"$f":"+SUM('HORAS PARADAS'!P68)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q68)","v":0},{"$f":"+SUM('HORAS PARADAS'!R68)","v":0},{"$f":"+SUM('HORAS PARADAS'!S68)","v":0},{"$f":"+SUM('HORAS PARADAS'!T68)","v":0},{"$f":"+SUM('HORAS PARADAS'!U68)","v":0},{"$f":"+SUM('HORAS PARADAS'!V68)","v":0},{"$f":"+SUM('HORAS PARADAS'!W68)","v":0},{"$f":"+SUM('HORAS PARADAS'!X68)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y68)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY68)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ68)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA68)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB68)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC68)","v":0}]
[null,"FILTRADO Zn",{"$f":"+SUM('HORAS PARADAS'!D69)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E69)","v":0},{"$f":"+SUM('HORAS PARADAS'!F69)","v":0},{"$f":"+SUM('HORAS PARADAS'!G69)","v":0},{"$f":"+SUM('HORAS PARADAS'!H69)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I69)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J69)","v":0},{"$f":"+SUM('HORAS PARADAS'!K69)","v":0},{"$f":"+SUM('HORAS PARADAS'!L69)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M69)","v":0},{"$f":"+SUM('HORAS PARADAS'!N69)","v":0},{"$f":"+SUM('HORAS PARADAS'!O69)","v":0},{"$f":"+SUM('HORAS PARADAS'!P69)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q69)","v":0},{"$f":"+SUM('HORAS PARADAS'!R69)","v":0},{"$f":"+SUM('HORAS PARADAS'!S69)","v":0},{"$f":"+SUM('HORAS PARADAS'!T69)","v":0},{"$f":"+SUM('HORAS PARADAS'!U69)","v":0},{"$f":"+SUM('HORAS PARADAS'!V69)","v":0},{"$f":"+SUM('HORAS PARADAS'!W69)","v":0},{"$f":"+SUM('HORAS PARADAS'!X69)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y69)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY69)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ69)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA69)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB69)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC69)","v":0}]
[null,"FILTRADO Bulk",{"$f":"+SUM('HORAS PARADAS'!D70)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E70)","v":0},{"$f":"+SUM('HORAS PARADAS'!F70)","v":0},{"$f":"+SUM('HORAS PARADAS'!G70)","v":0},{"$f":"+SUM('HORAS PARADAS'!H70)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I70)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J70)","v":0},{"$f":"+SUM('HORAS PARADAS'!K70)","v":0},{"$f":"+SUM('HORAS PARADAS'!L70)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M70)","v":0},{"$f":"+SUM('HORAS PARADAS'!N70)","v":0},{"$f":"+SUM('HORAS PARADAS'!O70)","v":0},{"$f":"+SUM('HORAS PARADAS'!P70)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q70)","v":0},{"$f":"+SUM('HORAS PARADAS'!R70)","v":0},{"$f":"+SUM('HORAS PARADAS'!S70)","v":0},{"$f":"+SUM('HORAS PARADAS'!T70)","v":0},{"$f":"+SUM('HORAS PARADAS'!U70)","v":0},{"$f":"+SUM('HORAS PARADAS'!V70)","v":0},{"$f":"+SUM('HORAS PARADAS'!W70)","v":0},{"$f":"+SUM('HORAS PARADAS'!X70)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y70)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY70)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ70)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA70)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB70)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC70)","v":0}]
[null,"PLANTA DE NEUTRALIZACION",{"$f":"+SUM('HORAS PARADAS'!D71)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E71)","v":0},{"$f":"+SUM('HORAS PARADAS'!F71)","v":0},{"$f":"+SUM('HORAS PARADAS'!G71)","v":0},{"$f":"+SUM('HORAS PARADAS'!H71)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I71)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J71)","v":0},{"$f":"+SUM('HORAS PARADAS'!K71)","v":0},{"$f":"+SUM('HORAS PARADAS'!L71)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M71)","v":0},{"$f":"+SUM('HORAS PARADAS'!N71)","v":0},{"$f":"+SUM('HORAS PARADAS'!O71)","v":0},{"$f":"+SUM('HORAS PARADAS'!P71)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q71)","v":0},{"$f":"+SUM('HORAS PARADAS'!R71)","v":0},{"$f":"+SUM('HORAS PARADAS'!S71)","v":0},{"$f":"+SUM('HORAS PARADAS'!T71)","v":0},{"$f":"+SUM('HORAS PARADAS'!U71)","v":0},{"$f":"+SUM('HORAS PARADAS'!V71)","v":0},{"$f":"+SUM('HORAS PARADAS'!W71)","v":0},{"$f":"+SUM('HORAS PARADAS'!X71)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y71)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY71)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ71)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA71)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB71)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC71)","v":0}]
[null,"BOMBAS DE RELAVE",{"$f":"+SUM('HORAS PARADAS'!D72)","v":6.720000000000001},{"$f":"+SUM('HORAS PARADAS'!E72)","v":0},{"$f":"+SUM('HORAS PARADAS'!F72)","v":0},{"$f":"+SUM('HORAS PARADAS'!G72)","v":0},{"$f":"+SUM('HORAS PARADAS'!H72)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!I72)","v":3.3600000000000003},{"$f":"+SUM('HORAS PARADAS'!J72)","v":0},{"$f":"+SUM('HORAS PARADAS'!K72)","v":0},{"$f":"+SUM('HORAS PARADAS'!L72)","v":5.040000000000001},{"$f":"+SUM('HORAS PARADAS'!M72)","v":0},{"$f":"+SUM('HORAS PARADAS'!N72)","v":0},{"$f":"+SUM('HORAS PARADAS'!O72)","v":0},{"$f":"+SUM('HORAS PARADAS'!P72)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q72)","v":0},{"$f":"+SUM('HORAS PARADAS'!R72)","v":0},{"$f":"+SUM('HORAS PARADAS'!S72)","v":0},{"$f":"+SUM('HORAS PARADAS'!T72)","v":0},{"$f":"+SUM('HORAS PARADAS'!U72)","v":0},{"$f":"+SUM('HORAS PARADAS'!V72)","v":0},{"$f":"+SUM('HORAS PARADAS'!W72)","v":0},{"$f":"+SUM('HORAS PARADAS'!X72)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y72)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY72)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ72)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA72)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB72)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC72)","v":0}]
[null,"HORAS PARADA PREVENTIVO",{"$f":"+SUM('HORAS PARADAS'!D73)","v":120.96},{"$f":"+SUM('HORAS PARADAS'!E73)","v":0},{"$f":"+SUM('HORAS PARADAS'!F73)","v":0},{"$f":"+SUM('HORAS PARADAS'!G73)","v":0},{"$f":"+SUM('HORAS PARADAS'!H73)","v":60.48},{"$f":"+SUM('HORAS PARADAS'!I73)","v":60.48},{"$f":"+SUM('HORAS PARADAS'!J73)","v":0},{"$f":"+SUM('HORAS PARADAS'!K73)","v":0},{"$f":"+SUM('HORAS PARADAS'!L73)","v":90.72000000000003},{"$f":"+SUM('HORAS PARADAS'!M73)","v":0},{"$f":"+SUM('HORAS PARADAS'!N73)","v":0},{"$f":"+SUM('HORAS PARADAS'!O73)","v":0},{"$f":"+SUM('HORAS PARADAS'!P73)","v":0},{"$f":"+SUM('HORAS PARADAS'!Q73)","v":0},{"$f":"+SUM('HORAS PARADAS'!R73)","v":0},{"$f":"+SUM('HORAS PARADAS'!S73)","v":0},{"$f":"+SUM('HORAS PARADAS'!T73)","v":0},{"$f":"+SUM('HORAS PARADAS'!U73)","v":0},{"$f":"+SUM('HORAS PARADAS'!V73)","v":0},{"$f":"+SUM('HORAS PARADAS'!W73)","v":0},{"$f":"+SUM('HORAS PARADAS'!X73)","v":0},{"$f":"+SUM('HORAS PARADAS'!Y73)","v":0},{"$f":"+SUM('HORAS PARADAS'!Z73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AA73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AB73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AC73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AD73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AE73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AF73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AG73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AH73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AI73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AJ73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AK73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AL73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AM73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AN73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AO73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AP73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AQ73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AR73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AS73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AT73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AU73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AV73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AW73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AX73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AY73)","v":0},{"$f":"+SUM('HORAS PARADAS'!AZ73)","v":0},{"$f":"+SUM('HORAS PARADAS'!BA73)","v":0},{"$f":"+SUM('HORAS PARADAS'!BB73)","v":0},{"$f":"+SUM('HORAS PARADAS'!BC73)","v":0}]
[null,"HORAS TOTAL MEJORA"]
[null,"HORAS OPERACIÓN",{"$f":"(24*C10-C121-C122)","v":{"v":47.040000000000006,"d":"47"}},{"$f":"(24*D10-D121-D122)","v":168},168,168,{"v":107.52000000000001,"d":"108"},{"v":107.52000000000001,"d":"108"},168,168,{"v":77.27999999999997,"d":"77"},{"$f":"(24*L10-L121-L122)","v":168},168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168]
[null,"HORAS REPARACION",{"$f":"+C144","v":{"v":18.5,"d":"19"}},{"$f":"+D144","v":{"v":9.25,"d":"9"}},{"v":32.07142857142857,"d":"32"},{"v":11.166666666666666,"d":"11"},{"v":4.25,"d":"4"},{"v":13.157407407407407,"d":"13"},{"v":14.808333333333334,"d":"15"},{"v":10.076923076923077,"d":"10"},{"v":27.166666666666668,"d":"27"},{"v":37.375,"d":"37"},48,{"v":36.7,"d":"37"},{"v":40.5,"d":"41"},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[]
[{"$f":"+A35","v":0},{"$f":"+B103","v":"CHANCADO PRIMARIO"},{"$nulls":3},{"v":2,"d":"2.0"},{"$nulls":5},{"v":2,"d":"2.0"},{"v":5,"d":"5.0"}]
[{"$f":"+A36","v":0.07},"CHANCADO SECUNDARIO",null,null,{"v":2,"d":"2.0"},{"v":4,"d":"4.0"},null,{"v":3,"d":"3.0"},{"v":5,"d":"5.0"},{"v":4,"d":"4.0"},{"v":3,"d":"3.0"},{"v":3,"d":"3.0"},{"v":1,"d":"1.0"},{"v":5,"d":"5.0"}]
[{"$f":"+A37","v":0.07},"CHANCADO TERCIARIO",null,null,{"v":15,"d":"15.0"},null,null,{"v":7,"d":"7.0"},{"v":6,"d":"6.0"},null,{"v":3,"d":"3.0"},null,null,{"v":2,"d":"2.0"}]
[0.07,"MOLIENDA",null,{"v":6,"d":"6.0"},{"v":6,"d":"6.0"},null,null,{"v":2,"d":"2.0"},{"v":1,"d":"1.0"},{"v":2,"d":"2.0"},{"v":16,"d":"16.0"},{"v":24,"d":"24.0"},{"v":24,"d":"24.0"},{"v":24,"d":"24.0"},{"v":24,"d":"24.0"}]
[0.06,"PLANTA DE CAL",{"$nulls":12},{"v":7,"d":"7.0"}]
[0.025,"ABASTECIMIENTO DE AGUA",{"v":13,"d":"13.0"}]
[0.07,"REACTIVOS",null,null,{"v":5,"d":"5.0"}]
[0.025,"FLOTACION Pb",null,null,{"v":3,"d":"3.0"}]
[0.05,"FLOTACION Cu",{"$nulls":6},{"v":1,"d":"1.0"},{"$nulls":5},{"v":5,"d":"5.0"}]
[0.05,"FLOTACION Zn",{"$nulls":3},{"v":2,"d":"2.0"},{"v":4,"d":"4.0"},null,{"v":1,"d":"1.0"},null,{"v":5,"d":"5.0"},{"v":4,"d":"4.0"},{"v":3,"d":"3.0"},{"v":1,"d":"1.0"}]
[0.05,"FLOTACION Bulk"]
[0.05,"ESPESADORES",{"v":2,"d":"2.0"},null,null,{"v":2,"d":"2.0"},{"$nulls":5},{"v":3,"d":"3.0"},{"v":7,"d":"7.0"}]
[0.07,"FILTRADO Pb",{"v":3,"d":"3.0"},null,null,{"v":2,"d":"2.0"},null,{"v":1,"d":"1.0"},null,{"v":4,"d":"4.0"},null,null,{"v":8,"d":"8.0"}]
[0.04,"FILTRADO Cu",{"$nulls":3},{"v":1,"d":"1.0"},null,{"v":107,"d":"107.0"},{"v":158,"d":"158.0"}]
[0.05,"FILTRADO Zn",null,{"v":3,"d":"3.0"},{"v":1,"d":"1.0"},{"$nulls":3},{"v":2,"d":"2.0"},null,null,{"v":1,"d":"1.0"},null,{"v":4,"d":"4.0"},{"v":4,"d":"4.0"}]
[0.05,"FILTRADO Bulk"]
[0.05,"PLANTA DE NEUTRALIZACION",{"v":3,"d":"3.0"},null,null,{"v":2,"d":"2.0"},{"v":4,"d":"4.0"},{"v":6,"d":"6.0"},{"v":3,"d":"3.0"},null,{"v":6,"d":"6.0"},{"v":4,"d":"4.0"},null,{"v":2,"d":"2.0"},{"v":2,"d":"2.0"}]
[0.06,"BOMBAS DE RELAVE",{"v":6,"d":"6.0"},{"v":4,"d":"4.0"},{"v":14,"d":"14.0"},{"$nulls":4},{"v":13,"d":"13.0"},null,{"v":8,"d":"8.0"},null,{"v":5,"d":"5.0"}]
[0.09,"HORAS PARADA CORRECTIVO",{"$f":"C126+C127+C128+C129+C130+C131+C132+IFERROR(1/(IFERROR(1/C133,0)+IFERROR(1/C134,0)+IFERROR(1/C135,0)+IFERROR(1/C136,0)),0)+C137+IFERROR(1/(IFERROR(1/C138,0)+IFERROR(1/C139,0)+IFERROR(1/C140,0)+IFERROR(1/C141,0)),0)+IFERROR(1/C142,0)+IFERROR(1/C143,0)","v":{"v":18.5,"d":"18.50"}},{"$f":"D126+D127+D128+D129+D130+D131+D132+IFERROR(1/(IFERROR(1/D133,0)+IFERROR(1/D134,0)+IFERROR(1/D135,0)+IFERROR(1/D136,0)),0)+D137+IFERROR(1/(IFERROR(1/D138,0)+IFERROR(1/D139,0)+IFERROR(1/D140,0)+IFERROR(1/D141,0)),0)+IFERROR(1/D142,0)+IFERROR(1/D143,0)","v":9.25},{"v":32.07142857142857,"d":"32.07"},{"v":11.166666666666666,"d":"11.17"},4.25,{"$f":"H126+H127+H128+H129+H130+H131+H132+IFERROR(1/(IFERROR(1/H133,0)+IFERROR(1/H134,0)+IFERROR(1/H135,0)+IFERROR(1/H136,0)),0)+H137+IFERROR(1/(IFERROR(1/H138,0)+IFERROR(1/H139,0)+IFERROR(1/H140,0)+IFERROR(1/H141,0)),0)+IFERROR(1/H142,0)+IFERROR(1/H143,0)","v":{"v":13.157407407407407,"d":"13.16"}},{"v":14.808333333333334,"d":"14.81"},{"v":10.076923076923077,"d":"10.08"},{"$f":"K126+K127+K128+K129+K130+K131+K132+IFERROR(1/(IFERROR(1/K133,0)+IFERROR(1/K134,0)+IFERROR(1/K135,0)+IFERROR(1/K136,0)),0)+K137+IFERROR(1/(IFERROR(1/K138,0)+IFERROR(1/K139,0)+IFERROR(1/K140,0)+IFERROR(1/K141,0)),0)+IFERROR(1/K142,0)+IFERROR(1/K143,0)","v":{"v":27.166666666666668,"d":"27.17"}},{"v":37.375,"d":"37.38"},{"v":48,"d":"48.00"},{"v":36.7,"d":"36.70"},{"v":40.5,"d":"40.50"},{"$f":"P126+P127+P128+P129+P130+P131+P132+IFERROR(1/(IFERROR(1/P133,0)+IFERROR(1/P134,0)+IFERROR(1/P135,0)+IFERROR(1/P136,0)),0)+P137+IFERROR(1/(IFERROR(1/P138,0)+IFERROR(1/P139,0)+IFERROR(1/P140,0)+IFERROR(1/P141,0)),0)+IFERROR(1/P142,0)+IFERROR(1/P143,0)","v":{"v":0,"d":"0.00"}},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"$f":"T126+T127+T128+T129+T130+T131+T132+IFERROR(1/(IFERROR(1/T133,0)+IFERROR(1/T134,0)+IFERROR(1/T135,0)+IFERROR(1/T136,0)),0)+T137+IFERROR(1/(IFERROR(T138,0)+IFERROR(T139,0)+IFERROR(T140,0)+IFERROR(T141,0)),0)+IFERROR(1/T142,0)+IFERROR(1/T143,0)","v":{"v":0,"d":"0.00"}},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"$f":"X126+X127+X128+X129+X130+X131+X132+IFERROR(1/(IFERROR(1/X133,0)+IFERROR(1/X134,0)+IFERROR(1/X135,0)+IFERROR(1/X136,0)),0)+X137+IFERROR(1/(IFERROR(1/X138,0)+IFERROR(1/X139,0)+IFERROR(1/X140,0)+IFERROR(1/X141,0)),0)+IFERROR(1/X142,0)+IFERROR(1/X143,0)","v":{"v":0,"d":"0.00"}},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"$f":"AZ126+AZ127+AZ128+AZ129+AZ130+AZ131+AZ132+IFERROR(1/(IFERROR(1/AZ133,0)+IFERROR(1/AZ134,0)+IFERROR(1/AZ135,0)+IFERROR(1/AZ136,0)),0)+AZ137+IFERROR(1/(IFERROR(1/AZ138,0)+IFERROR(1/AZ139,0)+IFERROR(1/AZ140,0)+IFERROR(1/AZ141,0)),0)+IFERROR(1/AZ142,0)+IFERROR(1/AZ143,0)","v":{"v":0,"d":"0.00"}},{"$f":"BA126+BA127+BA128+BA129+BA130+BA131+BA132+IFERROR(1/(IFERROR(1/BA133,0)+IFERROR(1/BA134,0)+IFERROR(1/BA135,0)+IFERROR(1/BA136,0)),0)+BA137+IFERROR(1/(IFERROR(1/BA138,0)+IFERROR(1/BA139,0)+IFERROR(1/BA140,0)+IFERROR(1/BA141,0)),0)+IFERROR(1/BA142,0)+IFERROR(1/BA143,0)","v":{"v":0,"d":"0.00"}},{"v":0,"d":"0.00"}]
[]
[null,"HORAS CONTR",{"$f":"+C101","v":"SEM01"},{"$f":"+D101","v":"SEM02"},"SEM03","SEM04","SEM05","SEM06","SEM07","SEM08","SEM09","SEM10","SEM11","SEM12","SEM13","SEM14","SEM15","SEM16","SEM17","SEM18","SEM19","SEM20","SEM21","SEM22","SEM23","SEM24","SEM25","SEM26","SEM27","SEM28","SEM29","SEM30","SEM31","SEM32","SEM33","SEM34","SEM35","SEM36","SEM37","SEM38","SEM39","SEM40","SEM41","SEM42","SEM43","SEM44","SEM45","SEM46","SEM47","SEM48","SEM49","SEM50","SEM51","SEM52"]
[0.2,"TOTAL",{"$f":"+C102","v":168},{"$f":"+D102","v":168},168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,{"$f":"+BA102","v":168},168]
[null,{"$f":"+B103","v":"CHANCADO PRIMARIO"},{"$f":"+C103","v":6.720000000000001},{"$f":"+D103","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+W103","v":0},0,0,{"$f":"+Z103","v":0},0,0,0,0,0,0,0,{"$f":"+AH103","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[0.2,"CHANCADO SECUNDARIO",6.720000000000001,{"$f":"+D104","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z104","v":0},0,0,0,0,0,0,0,{"$f":"+AH104","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[0.2,"CHANCADO TERCIARIO",6.720000000000001,{"$f":"+D105","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z105","v":0},0,0,0,0,0,0,0,{"$f":"+AH105","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[0.1,"MOLIENDA",6.720000000000001,{"$f":"+D106","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z106","v":0},0,0,0,0,0,0,0,{"$f":"+AH106","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[0.05,"PLANTA DE CAL",6.720000000000001,{"$f":"+D107","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z107","v":0},0,0,0,0,0,0,0,{"$f":"+AH107","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[0.15,"ABASTECIMIENTO DE AGUA",6.720000000000001,{"$f":"+D108","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z108","v":0},0,0,0,0,0,0,0,{"$f":"+AH108","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[0.2,"REACTIVOS",6.720000000000001,{"$f":"+D109","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z109","v":0},0,0,0,0,0,0,0,{"$f":"+AH109","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[0.1,"FLOTACION Pb",6.720000000000001,{"$f":"+D110","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z110","v":0},0,0,0,0,0,0,0,{"$f":"+AH110","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"FLOTACION Cu",6.720000000000001,{"$f":"+D111","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z111","v":0},0,0,0,0,0,0,0,{"$f":"+AH111","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"FLOTACION Zn",6.720000000000001,{"$f":"+D112","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z112","v":0},0,0,0,0,0,0,0,{"$f":"+AH112","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"FLOTACION Bulk",6.720000000000001,{"$f":"+D113","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z113","v":0},0,0,0,0,0,0,0,{"$f":"+AH113","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"ESPESADORES",6.720000000000001,{"$f":"+D114","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z114","v":0},0,0,0,0,0,0,0,{"$f":"+AH114","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"FILTRADO Pb",6.720000000000001,{"$f":"+D115","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z115","v":0},0,0,0,0,0,0,0,{"$f":"+AH115","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"FILTRADO Cu",6.720000000000001,{"$f":"+D116","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z116","v":0},0,0,0,0,0,0,0,{"$f":"+AH116","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"FILTRADO Zn",6.720000000000001,{"$f":"+D117","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z117","v":0},0,0,0,0,0,0,0,{"$f":"+AH117","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"FILTRADO Bulk",6.720000000000001,{"$f":"+D118","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z118","v":0},0,0,0,0,0,0,0,{"$f":"+AH118","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"PLANTA DE NEUTRALIZACION",6.720000000000001,{"$f":"+D119","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z119","v":0},0,0,0,0,0,0,0,{"$f":"+AH119","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"BOMBAS DE RELAVE",6.720000000000001,{"$f":"+D120","v":0},0,0,3.3600000000000003,3.3600000000000003,0,0,5.040000000000001,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"+Z120","v":0},0,0,0,0,0,0,0,{"$f":"+AH120","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,"HORAS PARADA PREVENTIVO",{"$f":"SUM(C148:C165)","v":{"v":120.96,"d":"121.0"}},{"$f":"SUM(D148:D165)","v":{"v":0,"d":"0.0"}},{"$f":"SUM(E148:E165)","v":{"v":0,"d":"0.0"}},{"$f":"SUM(F148:F165)","v":{"v":0,"d":"0.0"}},{"$f":"SUM(G148:G165)","v":{"v":60.48,"d":"60.5"}},{"$f":"SUM(H148:H165)","v":{"v":60.48,"d":"60.5"}},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"$f":"SUM(K148:K165)","v":{"v":90.72000000000003,"d":"90.7"}},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"$f":"SUM(Y148:Y165)","v":{"v":0,"d":"0.0"}},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"},{"v":0,"d":"0.0"}]
[null,"HORAS TOTAL MEJORA"]
[null,"HORAS OPERACIÓN",{"$f":"(24*C55-C166-C167)","v":{"v":47.040000000000006,"d":"47"}},{"$f":"(24*D55-D166-D167)","v":168},168,168,{"v":107.52000000000001,"d":"108"},{"v":107.52000000000001,"d":"108"},168,168,{"v":77.27999999999997,"d":"77"},168,168,168,168,168,168,168,{"$f":"(24*S55-S166-S167)","v":168},168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168,168]
[null,"HORAS REPARACION",{"$f":"+C189","v":{"v":14.666666666666666,"d":"15"}},{"$f":"+D189","v":0},{"v":5.071428571428571,"d":"5"},{"v":4.5,"d":"5"},0,5,4,{"v":4.090909090909091,"d":"4"},6,2,54,{"v":3.5333333333333337,"d":"4"},{"v":0.75,"d":"1"},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[]
[{"$f":"+A80","v":0},{"$f":"+B148","v":"CHANCADO PRIMARIO"},{"$nulls":9},{"v":2,"d":"2.0"},{"v":5,"d":"5.0"}]
[{"$f":"+A81","v":0.07},"CHANCADO SECUNDARIO",null,null,{"v":2,"d":"2.0"},{"v":2,"d":"2.0"},null,{"v":2,"d":"2.0"},{"v":2,"d":"2.0"},{"v":4,"d":"4.0"},null,null,{"v":1,"d":"1.0"}]
[{"$f":"+A82","v":0.07},"CHANCADO TERCIARIO",{"$nulls":5},{"v":3,"d":"3.0"},null,null,{"v":3,"d":"3.0"},null,null,{"v":2,"d":"2.0"}]
[0.07,"MOLIENDA",null,null,{"v":2,"d":"2.0"},{"$nulls":3},{"v":1,"d":"1.0"},{"$nulls":3},{"v":43,"d":"43.0"}]
[0.06,"PLANTA DE CAL"]
[0.025,"ABASTECIMIENTO DE AGUA",12.5]
[0.07,"REACTIVOS"]
[0.025,"FLOTACION Pb"]
[0.05,"FLOTACION Cu"]
[0.05,"FLOTACION Zn",{"$nulls":6},{"v":1,"d":"1.0"},null,{"v":3,"d":"3.0"},null,null,{"v":1,"d":"1.0"}]
[0.05,"FLOTACION Bulk"]
[0.05,"ESPESADORES",{"v":2,"d":"2.0"},null,null,{"v":2,"d":"2.0"},{"$nulls":6},{"v":5,"d":"5.0"}]
[0.07,"FILTRADO Pb",{"$nulls":3},{"v":2,"d":"2.0"}]
[0.04,"FILTRADO Cu"]
[0.05,"FILTRADO Zn",null,null,{"v":1,"d":"1.0"},{"$nulls":8},{"v":3,"d":"3.0"},{"v":4,"d":"4.0"}]
[0.05,"FILTRADO Bulk"]
[0.05,"PLANTA DE NEUTRALIZACION",{"$nulls":12},{"v":2,"d":"2.0"}]
[0.06,"BOMBAS DE RELAVE",{"v":6,"d":"6.0"},null,{"v":14,"d":"14.0"},{"$nulls":4},{"v":11,"d":"11.0"},{"$nulls":3},{"v":5,"d":"5.0"}]
[0.09,"HORAS CONTR CORRECTIVO",{"$f":"C171+C172+C173+C174+C175+C176+C177+IFERROR(1/(IFERROR(1/C178,0)+IFERROR(1/C179,0)+IFERROR(1/C180,0)+IFERROR(1/C181,0)),0)+C182+IFERROR(1/(IFERROR(C183,0)+IFERROR(C184,0)+IFERROR(C185,0)+IFERROR(C186,0)),0)+IFERROR(1/C187,0)+IFERROR(1/C188,0)","v":{"v":14.666666666666666,"d":"14.67"}},{"v":0,"d":"0.00"},{"v":5.071428571428571,"d":"5.07"},{"v":4.5,"d":"4.50"},{"v":0,"d":"0.00"},{"v":5,"d":"5.00"},{"v":4,"d":"4.00"},{"v":4.090909090909091,"d":"4.09"},{"v":6,"d":"6.00"},{"v":2,"d":"2.00"},{"v":54,"d":"54.00"},{"v":3.5333333333333337,"d":"3.53"},0.75,{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"$f":"T171+T172+T173+T174+T175+T176+T177+IFERROR(1/(IFERROR(1/T178,0)+IFERROR(1/T179,0)+IFERROR(1/T180,0)+IFERROR(1/T181,0)),0)+T182+IFERROR(1/(IFERROR(T183,0)+IFERROR(T184,0)+IFERROR(T185,0)+IFERROR(T186,0)),0)+IFERROR(1/T187,0)+IFERROR(1/T188,0)","v":{"v":0,"d":"0.00"}},{"$f":"U171+U172+U173+U174+U175+U176+U177+IFERROR(1/(IFERROR(1/U178,0)+IFERROR(1/U179,0)+IFERROR(1/U180,0)+IFERROR(1/U181,0)),0)+U182+IFERROR(1/(IFERROR(U183,0)+IFERROR(U184,0)+IFERROR(U185,0)+IFERROR(U186,0)),0)+IFERROR(1/U187,0)+IFERROR(1/U188,0)","v":{"v":0,"d":"0.00"}},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"$f":"X171+X172+X173+X174+X175+X176+X177+IFERROR(1/(IFERROR(1/X178,0)+IFERROR(1/X179,0)+IFERROR(1/X180,0)+IFERROR(1/X181,0)),0)+X182+IFERROR(1/(IFERROR(X183,0)+IFERROR(X184,0)+IFERROR(X185,0)+IFERROR(X186,0)),0)+IFERROR(1/X187,0)+IFERROR(1/X188,0)","v":{"v":0,"d":"0.00"}},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"},{"v":0,"d":"0.00"}]
[]
[null,"DISPONIBILIDAD PLANTA","SEM01","SEM02","SEM03","SEM04","SEM05","SEM06","SEM07","SEM08","SEM09","SEM10","SEM11","SEM12","SEM13","SEM14","SEM15","SEM16","SEM17","SEM18","SEM19","SEM20","SEM21","SEM22","SEM23","SEM24","SEM25","SEM26","SEM27","SEM28","SEM29","SEM30","SEM31","SEM32","SEM33","SEM34","SEM35","SEM36","SEM37","SEM38","SEM39","SEM40","SEM41","SEM42","SEM43","SEM44","SEM45","SEM46","SEM47","SEM48","SEM49","SEM50","SEM51","SEM52","PROMEDIO"]
[null,"DF Budget",{"$f":"((24*C10)-C31-C32-C54)/(24*C10)","v":{"v":0.5619494505494504,"d":"56.2%"}},{"$f":"((24*D10)-D31-D32-D54)/(24*D10)","v":{"v":0.9834115384615384,"d":"98.3%"}},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.7024368131868132,"d":"70.2%"},{"v":0.7024368131868132,"d":"70.2%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.8429241758241759,"d":"84.3%"},{"v":0.7024368131868132,"d":"70.2%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.28097472527472517,"d":"28.1%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"$f":"((24*T10)-T31-T32-T54)/(24*T10)","v":{"v":0.28097472527472517,"d":"28.1%"}},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"$f":"((24*X10)-X31-X32-X54)/(24*X10)","v":{"v":0.9834115384615384,"d":"98.3%"}},{"v":0.7024368131868132,"d":"70.2%"},{"v":0.5619494505494504,"d":"56.2%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.28097472527472517,"d":"28.1%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.421462087912088,"d":"42.1%"},{"v":0.8429241758241759,"d":"84.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.8429241758241759,"d":"84.3%"},{"v":0.4262016483516485,"d":"42.6%"},{"v":0.9976302197802198,"d":"99.8%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.28097472527472517,"d":"28.1%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.5619494505494504,"d":"56.2%"},{"v":0.7024368131868132,"d":"70.2%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.8429241758241759,"d":"84.3%"},{"v":0.7024368131868132,"d":"70.2%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"$f":"AVERAGE(C192:O192)","v":{"v":0.8753443364327981,"d":"87.5%"}}]
[null,"DF Forecast",{"$f":"((24*C10)-C76-C77-C99)/(24*C10)","v":{"v":0.421462087912088,"d":"42.1%"}},{"$f":"((24*D10)-D76-D77-D99)/(24*D10)","v":{"v":0.9834115384615384,"d":"98.3%"}},{"$f":"((24*E10)-E76-E77-E99)/(24*E10)","v":{"v":0.9834115384615384,"d":"98.3%"}},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.7024368131868132,"d":"70.2%"},{"v":0.7024368131868132,"d":"70.2%"},{"v":0.9817069597069596,"d":"98.2%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.5619494505494504,"d":"56.2%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"$f":"((24*T10)-T76-T77-T99)/(24*T10)","v":{"v":0.9834115384615384,"d":"98.3%"}},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"$f":"((24*X10)-X76-X77-X99)/(24*X10)","v":{"v":0.9834115384615384,"d":"98.3%"}},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9886738445378151,"d":"98.9%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"$f":"((24*AV10)-AV76-AV77-AV99)/(24*AV10)","v":{"v":0.9834115384615384,"d":"98.3%"}},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"v":0.9834115384615384,"d":"98.3%"},{"$f":"((24*BA10)-BA76-BA77-BA99)/(24*BA10)","v":{"v":0.9834115384615384,"d":"98.3%"}},{"v":0.9834115384615384,"d":"98.3%"},{"$f":"AVERAGE(C193:O193)","v":{"v":0.8644064947872642,"d":"86.4%"}}]
[null,"DF Real",{"$f":"((24*C10)-(C121+C122+C144))/(24*C10)","v":{"v":0.1698809523809525,"d":"17.0%"}},{"v":0.9449404761904762,"d":"94.5%"},{"v":0.8090986394557824,"d":"80.9%"},{"v":0.933531746031746,"d":"93.4%"},{"v":0.6147023809523811,"d":"61.5%"},{"v":0.5616820987654321,"d":"56.2%"},{"$f":"((24*I10)-(I121+I122+I144))/(24*I10)","v":{"v":0.9118551587301587,"d":"91.2%"}},{"v":0.9400183150183151,"d":"94.0%"},{"$f":"((24*K10)-(K121+K122+K144))/(24*K10)","v":{"v":0.2982936507936506,"d":"29.8%"}},{"v":0.7775297619047619,"d":"77.8%"},{"v":0.7142857142857143,"d":"71.4%"},{"v":0.7815476190476192,"d":"78.2%"},{"v":0.7589285714285714,"d":"75.9%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":1,"d":"100.0%"},{"v":0.7089457757681201,"d":"70.9%"}]
[null,"DF Real - CONTR",{"$f":"((24*C10)-(C166+C167+C189))/(24*C10)","v":{"v":0.1926984126984127,"d":"19.3%"}},{"v":1,"d":"100.0%"},{"v":0.969812925170068,"d":"97.0%"},{"v":0.9732142857142857,"d":"97.3%"},{"v":0.64,"d":"64.0%"},{"v":0.6102380952380952,"d":"61.0%"},{"$f":"((24*I10)-(I166+I167+I189))/(24*I10)","v":{"v":0.9761904761904762,"d":"97.6%"}},{"v":0.9756493506493507,"d":"97.6%"},{"$f":"((24*K10)-(K166+K167+K189))/(24*K10)","v":{"v":0.4242857142857141,"d":"42.4%"}},{"v":0.9880952380952381,"d":"98.8%"},{"v":0.6785714285714286,"d":"67.9%"},{"v":0.9789682539682539,"d":"97.9%"},{"v":0.9955357142857143,"d":"99.6%"},{"$nulls":39},{"v":0.8002507611436183,"d":"80.0%"}]
{"$rows_empty":27}
[null,"PRINCIPALES ACTIVIDADES"]
[null,null,"SEMANA N°1","ESPESADOR DE PLOMO",{"$nulls":4},"Falla en la linea de distribucion de agua (tuberia HDPE con desgaste)"]
[{"$nulls":3},"BOMBA NOVA Nº1",{"$nulls":4},"Falla en el sistema estructural (oltura de elementos de sujecion)"]
[{"$nulls":3},"BOMBA MARS Nº2",{"$nulls":4},"Falla en el sistema estructural (rotura del soporte de la estructura de valvulas neumaticas)"]
[{"$nulls":3},"BOMBA VOGT Nº2 FILTRO PRENSA",{"$nulls":4},"Falla en el sistema de bombeo (atoro de la bomba)"]
[{"$nulls":3},"BOMBA RIO TORRES Nº1",{"$nulls":4},"Falla en la linea de distribucion de carga (fuga de carga por agujero)"]
[null,null,"SEMANA N°2","MUESTREADOR DE RELAVE METSO",{"$nulls":4},"Falla en el sistema electrico (quemadura de motor)"]
[{"$nulls":3},"CELDA WENCO ZN SCAVENGER N° 6",{"$nulls":4},"Falla en el sistema electrico (rotura de estructura de motor)"]
[{"$nulls":3},"ZARANDA DE ALTA FRECUENCIA / SAF",{"$nulls":4},"Falla en el sistema electrico (rotura de estructura de motor)"]
[null,null,"SEMANA N°3","CELDA DR 500 #02",{"$nulls":4},"Falla en el sistema de agitacion(dispersor)",{"$nulls":46},{"$f":"CONCATENATE(D232,\"; \",I232)","v":"CELDA DR 500 #02; Falla en el sistema de agitacion(dispersor)"}]
[{"$nulls":3},"MOLINO #01",{"$nulls":4},"falla en el sistema de transmision(chumacera de contraeje)",{"$nulls":46},{"$f":"CONCATENATE(D233,\"; \",I233)","v":"MOLINO #01; falla en el sistema de transmision(chumacera de contraeje)"}]
[{"$nulls":3},"BOMBA MARS #01",{"$nulls":4},"falla en el sistema de transmision(caja de transmsionh)",{"$nulls":46},"BOMBA MARS #01; falla en el sistema de transmision(caja de transmsionh)"]
[{"$nulls":3},"VALVULA NEUMATICA DESCARGA DE CALACON ALIMENTO A POZA DE MARS # 01",{"$nulls":4},"Falla en el sistema de bombeo(valvula)",{"$nulls":46},"VALVULA NEUMATICA DESCARGA DE CALACON ALIMENTO A POZA DE MARS # 01; Falla en el sistema de bombeo(valvula)"]
[{"$nulls":3},"CEDAZO # 01",{"$nulls":4},"Falla en el sistema de transmision(tambor)",{"$nulls":46},"CEDAZO # 01; Falla en el sistema de transmision(tambor)"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":4},"Falla en el sistema electronico",{"$nulls":46},"FILTRO PRENSA; Falla en el sistema electronico"]
[{"$nulls":3},"MOLINO FULLER ",{"$nulls":4},"Falla en el sistema de transmision(reductor)",{"$nulls":46},"MOLINO FULLER ; Falla en el sistema de transmision(reductor)"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº136",{"$nulls":4},"Falla en el sistema de distribucion(manga)",{"$nulls":46},"BOMBA DOSIFICADORA Nº136; Falla en el sistema de distribucion(manga)"]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":4},"Falla en el sistema de la zaranda(panel)",{"$nulls":46},"CEDAZO 02 ; Falla en el sistema de la zaranda(panel)"]
[{"$nulls":3},"BOMBA DE LUBRICACION #01 DE MOLINO 8X11",{"$nulls":4},"Falla en el sistema de transmision(acoplamiento)",{"$nulls":46},"BOMBA DE LUBRICACION #01 DE MOLINO 8X11; Falla en el sistema de transmision(acoplamiento)"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº122",{"$nulls":4},"Falla en el sistema de distribucion(manga)",{"$nulls":46},"BOMBA DOSIFICADORA Nº122; Falla en el sistema de distribucion(manga)"]
[null,null,"SEMANA N°4","ESPESADOR DE ZINC",{"$nulls":51},"Falla en la linea de descarga del cono  del espesador"]
[{"$nulls":3},"FILTRO CC 30",{"$nulls":51},"Falla en  sistema de de transmison de la rastra"]
[{"$nulls":3},"COMPRESORA ST1509",{"$nulls":51},"Falla en el circuito de aire de la compresora(valvula de alivio) "]
[{"$nulls":3},"BOMBA DE LODOS 3 Y 4",{"$nulls":51},"Falla en el sistema de bombeo. Operativo"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":51},"Falla en el sistema de transmision"]
[{"$nulls":3},"BOMBA DOSIFICADORA FLOTACION",{"$nulls":51},"Falla en el sistema de bombeo "]
[{"$nulls":3},"DETECTOR DE METALES  FAJA 5A",{"$nulls":51},"Falla en el funcionamiento de control del equipo"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Falla en el sistema de regulacion de la valvula diafragma"]
[null,null,"SEMANA N°5","CELDA DENVER SUB A-24 Nº2",{"$nulls":51},"Falla en la linea de electrico (rotor)"]
[{"$nulls":3},"SOPLADOR INGERSOLL RAND",{"$nulls":51},"Falla en sistema de alimentacion de aire"]
[null,null,"SEMANA N°6","BOMBA VERTICAL 02 DE RETORNO CURRIER ",{"$nulls":51},"Fallla en el sistema de bombeo"]
[{"$nulls":3},"CEDAZO #02",{"$nulls":51},"Falla en el sistema de transmision"]
[{"$nulls":3},"BOMBA 02 DE MOLINO 8 X 11",{"$nulls":51},"Fallla en el sistema de bombeo"]
[{"$nulls":3},"BOMBA NOVA 02",{"$nulls":51},"Falla en el sistema de bombeo"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":51},"Falla en el sistema electronico"]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":51},"Falla en el sistema de transmision"]
[{"$nulls":3},"CHANCADORA TERCIARIA ",{"$nulls":51},"Falla en el sistema de transmision"]
[{"$nulls":3},"FAJA 07 DE CHANCADO ",{"$nulls":51},"Falla en el sistema de transmision"]
[{"$nulls":3},"CLARIFICADOR N° 3",{"$nulls":51},"Falla en el sistema electrico"]
[{"$nulls":3},"CEDAZO #01",{"$nulls":51},"Falla en el sistema de transmision"]
[null,null,"SEMANA N°7","CEDAZO 02",{"$nulls":51},"Falla en el mecanismo(tambor)"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":51},"Falla en el motor electrico(templador)"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":51},"Falla en el sistema de control del sensor(final de carrera)"]
[{"$nulls":3},"BOMBAS NOVA 4",{"$nulls":51},"Falla en el sendor de nivel(actuador de boya)"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":51},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"BOMBA # 01 DE CELDA SK 240",{"$nulls":51},"Falla en el sistema de bombeo(impulsor)"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":51},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"FAJA N° 7",{"$nulls":51},"Falla en el motoreductor"]
[{"$nulls":3},"BOMBA 77 A",{"$nulls":51},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"CELDA SP-18 ",{"$nulls":51},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"FAJA 5D DE CHANCADO",{"$nulls":51},"Falla en el empalme de la banda transportadora"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":51},"Falla en el sistema electronico"]
[null,null,"SEMANA N°8","FAJA TRANSPORTADORA DE ALIMENTO AL MOLINO 8X11",{"$nulls":51},"Falla en el sistema de acarreo de mineral (banda transportadora)"]
[{"$nulls":3},"BOMBA MARS 04",{"$nulls":51},"Falla en el sistema estructural (base de bomba)"]
[{"$nulls":3},"BOMBA 1.5 COURIER CONCENTRADO DE PLOMO",{"$nulls":51},"Falla en la linea de tuberias de descarga"]
[{"$nulls":3},"BOMBA HIDROSTAL EF05 Nº1",{"$nulls":51},"Falla en el sistema de bombeo"]
[{"$nulls":3},"FAJA 5C DE CHANCADO",{"$nulls":51},"Falla en el sistema de transmision(cadena de transmision)"]
[{"$nulls":3},"BOMBA MARS 02",{"$nulls":51},"Falla en la linea de tuberias de descarga (valvula de descarga)"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":51},"Falla en el sistema de zarandeo (malla)"]
[null,null,"SEMANA N°9","BOMBA DE LODOS N° 6",{"$nulls":51},"Falla en el sistema de bombeo(impulsor)"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":51},"Falla en el sistema de transmision(chumacera de la base de motor)"]
[{"$nulls":3},"BOMBA 77 B",{"$nulls":51},"Falla en el sistema de bombeo(bocina)"]
[{"$nulls":3},"BOMBA PERISTATICA Nª3 DE CAL",{"$nulls":51},"Falla en el sistema de bombeo(reten)"]
[{"$nulls":3},"CEDAZO 01",{"$nulls":51},"Falla en el sistema de selección de mineral(malla sflex)"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":51},"Falla en el sistema de transmision(chumacera de la base de motor)"]
[{"$nulls":3},"BOMBA 77 \"A\"",{"$nulls":51},"Falla en el sistema de bombeo(tuberia de descarga)"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Falla en la unidad compresora(valvula espiral)"]
[null,null,"SEMANA N°10","BOMBAS MARS 04",{"$nulls":51},"Se paro el equipo por falla en el sistema de la caja de valvulas(asiento de valvulas)"]
[{"$nulls":3},"CICLON DE RELAVERA",{"$nulls":51},"Se paro el equipo por falla en el sistema de la linea de descarga(manga pinch de 6\")"]
[{"$nulls":3},"BOMBA DE LODOS # 04",{"$nulls":51},"Se paro equipo por falla en el sistema de transmision(caja de rodamientos)"]
[{"$nulls":3},"BOMBA Nº106 - ESPESADOR DE ZINC",{"$nulls":51},"Se paro el equipo por falla en el motor electrico de la manga de descarga"]
[{"$nulls":3},"ESPESADOR DE ZINC",{"$nulls":51},"Se paro el equipo por falla en la line de descargas (manga de valvula poinch de 4\")"]
[{"$nulls":3},"CHANCADORA PRIMARIA",{"$nulls":51},"Se paro el equipo por falla en el sistema de trituracion(pernos de forro movil)"]
[{"$nulls":3},"CEDAZO Nº01",{"$nulls":51},"Se parada operativa del equipo(cambio de malla)"]
[{"$nulls":3},"BOMBA MARS Nº04",{"$nulls":51},"Se paro el equipo por falla en el sistema de la caja de valvulas(asiento de valvulas)"]
[{"$nulls":3},"BOMBA VERTICAL 2.5 STD DE RETORNO DE COURIER Nº02",{"$nulls":51},"Se paro el equipo por falla en el sistema de bombeo(linea de alimentacion)"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Falla en la unidad compresora(valvula espiral)"]
[null,null,"SEMANA N°11","FAJA Nº 03 DE CHANCADO",{"$nulls":51},"Falla en el sistema de acarreo de mineral (banda transportadora)"]
[{"$nulls":3},"MOLINO Nº2",{"$nulls":51},"Falla en el sistema de transmision (volante, eje, contraeje)"]
[{"$nulls":3},"BOMBA 104",{"$nulls":51},"Falla en el sistema de bombeo (forros con desgaste prematuro)"]
[{"$nulls":3},"BOMBA VERTICAL 1,5 Nº09 DEL ESPESADOR DE RELAVE",{"$nulls":51},"Falla en el sistema de transmision (polea - motor)"]
[{"$nulls":3},"ESPESADOR DE ZINC",{"$nulls":51},"Falla en el sistema neumatico (manga)"]
[{"$nulls":3},"CEDAZO Nº01",{"$nulls":51},"Falla en el sistema de transmision (polea - motor)"]
[{"$nulls":3},"BOMBA 106",{"$nulls":51},"Falla en el sistema neumatico (manga)"]
[{"$nulls":3},"FAJA Nº01 DE PB",{"$nulls":51},"Falla en el sistema de transmision (cadena - sprocket)"]
[{"$nulls":3},"FAJA Nº 02 DE CHANCADO",{"$nulls":51},"Falla en el sistema de acarreo de mineral (electroiman)"]
[null,null,"SEMANA N°12","BOMBA MARS L-180 N° 4",{"$nulls":51},"Falla en la camara de bombeo(rotura de piston rod)"]
[{"$nulls":3},"CEDAZO # 01",{"$nulls":51},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":51},"Falla en el sistema de compresion de concentrado(pernos de fijacion de los tacos de las placas)"]
[{"$nulls":3},"FAJA TRANSPORTADORA N°5D ",{"$nulls":51},"Falla en el sistema de transporte (banda transportadora)"]
[{"$nulls":3},"BOMBA CENTRIFUGA 77 A, 6X4 AH WARMAN ",{"$nulls":51},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"BOMBA VERTICAL 1.5 DE RELAVE GENERAL ",{"$nulls":51},"Falla en el sistema de transmision(correas de transmision)"]
[{"$nulls":3},"CEDAZO #01",{"$nulls":51},"Parada operativa(cambio de mallas para seleccion de mineral)"]
[{"$nulls":3},"COMPRESORA TS20 #01",{"$nulls":51},"Falla en el sistema de transmision(acople omega20\")"]
[{"$nulls":3},"COMPRESORA TS20 #01",{"$nulls":51},"Falla el el sistema de control electronico(alerta de presion alta)"]
[{"$nulls":3},"CEDAZO # 02 ",{"$nulls":51},"Falla en sistema de selección de mineral(paneles)"]
[{"$nulls":3},"SOPLADOR SPENCER",{"$nulls":51},"Falla en sistema de arranque(motor electrico)"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Falla en la unidad compresora(valvula espiral)"]
[null,null,"SEMANA N°13","BOMBA DE CICLON DE CAL ",{"$nulls":51},"Falla en el sistema de bombeo(forros)",{"$f":"CONCATENATE(D321,\"; \",BD321)","v":"BOMBA DE CICLON DE CAL ; Falla en el sistema de bombeo(forros)"}]
[{"$nulls":3},"MOTOR DE ZARANDA DE ALTA FRECUENCIA",{"$nulls":51},"Falla en el motor electrico(rodamientos)",{"$f":"CONCATENATE(D322,\"; \",BD322)","v":"MOTOR DE ZARANDA DE ALTA FRECUENCIA; Falla en el motor electrico(rodamientos)"}]
[{"$nulls":3},"LÍNEA DE DESCARGA DE HIDROCICLÓN RELAVE",{"$nulls":51},"Falla en la linea de descarag del ciclon(rotura de tuberis)","LÍNEA DE DESCARGA DE HIDROCICLÓN RELAVE; Falla en la linea de descarag del ciclon(rotura de tuberis)"]
[{"$nulls":3},"BOMBA DE LODOS Nº 4",{"$nulls":51},"Falla en el sistema de bombeo(bocina)","BOMBA DE LODOS Nº 4; Falla en el sistema de bombeo(bocina)"]
[{"$nulls":3},"FAJA 1 DE CAL",{"$nulls":51},"Falla en el sistema de transporte de carga(raspador)","FAJA 1 DE CAL; Falla en el sistema de transporte de carga(raspador)"]
[{"$nulls":3},"BOMBA HORIZONTAL 103",{"$nulls":51},"Falla en el sistema de bombeo(forros)","BOMBA HORIZONTAL 103; Falla en el sistema de bombeo(forros)"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":51},"Falla en la unidad compresora(valvula espiral)","FILTRO PRENSA; Falla en la unidad compresora(valvula espiral)"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA"]

{"sheet":"MTTR_SEM","index":16,"n_rows":194,"n_cols":57,"rows_kept":194,"merged":[[7,2,7,13],[89,2,93,2],[89,3,89,7],[89,8,89,13],[90,3,90,7],[90,8,90,13],[91,3,91,7],[91,8,91,13],[92,3,92,7],[92,8,92,13],[93,3,93,7],[93,8,93,13],[94,2,96,2],[94,3,94,7],[94,8,94,13],[95,3,95,7],[95,8,95,13],[96,3,96,7],[96,8,96,13],[97,2,107,2],[97,3,97,7],[97,8,97,13],[98,3,98,7],[98,8,98,13],[99,3,99,7],[99,8,99,13],[100,3,100,7],[100,8,100,13],[101,3,101,7],[101,8,101,13],[102,3,102,7],[102,8,102,13],[103,3,103,7],[103,8,103,13],[104,3,104,7],[104,8,104,13],[105,3,105,7],[105,8,105,13],[106,3,106,7],[106,8,106,13],[107,3,107,7],[107,8,107,13],[108,2,115,2],[108,3,108,7],[109,3,109,7],[110,3,110,7],[111,3,111,7],[112,3,112,7],[113,3,113,7],[114,3,114,7],[115,3,115,7],[116,2,117,2],[116,3,116,7],[117,3,117,7],[118,2,127,2],[118,3,118,7],[119,3,119,7],[120,3,120,7],[121,3,121,7],[122,3,122,7],[123,3,123,7],[124,3,124,7],[125,3,125,7],[126,3,126,7],[127,3,127,7],[128,2,139,2],[128,3,128,7],[129,3,129,7],[130,3,130,7],[131,3,131,7],[132,3,132,7],[133,3,133,7],[134,3,134,7],[135,3,135,7],[136,3,136,7],[137,3,137,7],[138,3,138,7],[139,3,139,7],[140,2,146,2],[147,2,154,2],[155,2,164,2],[165,2,173,2],[174,2,185,2],[186,2,193,2]]}
[null,"MTTR PLANTA CONCENTRADORA 2024",{"$nulls":6},"MTBF",65,null,"MTTR",{"$f":"+DISP_PLANTA!M1","v":1.7}]
[]
[null,null,"2012-01-01","2012-02-01","2012-03-01","2012-04-01","2012-05-01"]
[null,"MTBF",{"v":22.921034482758625,"d":"22.9"},{"v":29.868571428571425,"d":"29.9"},{"v":21.071290322580644,"d":"21.1"},{"v":28.742272727272734,"d":"28.7"},{"v":40.345882352941175,"d":"40.3"}]
[null,"MTTR",{"v":1.358620689655173,"d":"1.4"},{"v":0.7095238095238091,"d":"0.7"},{"v":1.4032258064516132,"d":"1.4"},{"v":1.6143939393939393,"d":"1.6"},{"v":0.5872549019607843,"d":"0.6"}]
[]
[]
[null,null,2024]
[]
[null,null,31,29,31,30,31,30,31,31,30,31,30,31]
[null,"MTTR","SEM01","SEM02","SEM03","SEM04","SEM05","SEM06","SEM07","SEM08","SEM09","SEM10","SEM11","SEM12","SEM13","SEM14","SEM15","SEM16","SEM17","SEM18","SEM19","SEM20","SEM21","SEM22","SEM23","SEM24","SEM25","SEM26","SEM27","SEM28","SEM29","SEM30","SEM31","SEM32","SEM33","SEM34","SEM35","SEM36","SEM37","SEM38","SEM39","SEM40","SEM41","SEM42","SEM43","SEM44","SEM45","SEM46","SEM47","SEM48","SEM49","SEM50","SEM51","SEM52"]
[0.2,"PLANEADO",{"$f":"+$M$1","v":1.7},{"$f":"+$M$1","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,{"$f":"+$M$1","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,{"$f":"+$M$1","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7]
[0.2,"PROYECTADO",{"$f":"+$M$1","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7]
[0.2,"REALIZADO",{"$f":"C34","v":5.3},{"v":4.333333333333333,"d":"4.3"},{"v":4.5285714285714285,"d":"4.5"},{"v":1.8285714285714287,"d":"1.8"},{"v":4,"d":"4.0"},{"v":10.533333333333333,"d":"10.5"},21.2,{"$f":"J34","v":{"v":2.95,"d":"3.0"}},5.1,2.9,{"v":9.433333333333332,"d":"9.4"},{"v":10.114285714285714,"d":"10.1"},14.7,{"$f":"P34","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7]
[]
[0.07,"CHANCADO PRIMARIO",{"$nulls":3},2,{"$nulls":5},{"v":1.5,"d":"2"},{"v":2.3,"d":"2"}]
[0.07,"CHANCADO SECUNDARIO",null,null,2,{"v":1.8,"d":"2"},null,{"v":1.5,"d":"2"},{"v":1.7,"d":"2"},2,{"v":2.5,"d":"3"},3,1,{"v":2.5,"d":"3"}]
[0.07,"CHANCADO TERCIARIO",null,null,{"v":14.7,"d":"15"},null,null,{"v":2.2,"d":"2"},2,null,{"v":1.5,"d":"2"},null,null,1]
[0.06,"MOLIENDA",null,6,2,null,null,2,1,{"v":1.5,"d":"2"},16,null,43,{"v":57.3,"d":"57"},59]
[0.025,"PLANTA DE CAL",{"$nulls":12},{"v":3.5,"d":"4"}]
[0.07,"ABASTECIMIENTO DE AGUA",12.5]
[0.025,"REACTIVOS",null,null,{"v":2.5,"d":"3"}]
[0.05,"FLOTACION Pb",null,null,{"v":2.5,"d":"3"}]
[0.05,"FLOTACION Cu",{"$nulls":6},1,{"$nulls":5},5]
[0.05,"FLOTACION Zn",null,3,1,2,4,null,1,null,{"v":2.5,"d":"3"},4,3,1]
[0.05,"FLOTACION Bulk"]
[0.07,"ESPESADORES",{"v":2,"d":"2.0"},null,null,2,{"$nulls":5},3,{"v":3.5,"d":"4"}]
[0.04,"FILTRADO Pb",{"v":3,"d":"3.0"},null,null,2,null,1,null,4,null,null,{"v":3.8,"d":"4"}]
[0.05,"FILTRADO Cu",{"$nulls":3},1,null,{"v":53.5,"d":"54"},{"v":157.9,"d":"158"},null,null,1]
[0.05,"FILTRADO Zn",{"$nulls":6},2,{"$nulls":4},2,4]
[0.05,"FILTRADO Bulk"]
[0.06,"PLANTA DE NEUTRALIZACION",{"v":3,"d":"3.0"},null,null,2,4,3,3,null,3,4,null,2,2]
[0.09,"BOMBAS DE RELAVE",{"v":6,"d":"6.0"},4,7,{"$nulls":4},{"v":4.3,"d":"4"},null,{"v":3.8,"d":"4"},null,5]
[null,"MTTR TOTAL",{"$f":"IF(SUM(C16:C33)=0,C13,AVERAGE(C16:C33))","v":5.3},{"$f":"IF(SUM(D16:D33)=0,D13,AVERAGE(D16:D33))","v":{"v":4.333333333333333,"d":"4.3"}},{"$f":"IF(SUM(E16:E33)=0,E13,AVERAGE(E16:E33))","v":{"v":4.5285714285714285,"d":"4.5"}},{"$f":"IF(SUM(F16:F33)=0,F13,AVERAGE(F16:F33))","v":{"v":1.8285714285714287,"d":"1.8"}},{"$f":"IF(SUM(G16:G33)=0,G13,AVERAGE(G16:G33))","v":{"v":4,"d":"4.0"}},{"v":10.533333333333333,"d":"10.5"},21.2,{"v":2.95,"d":"3.0"},5.1,2.9,{"v":9.433333333333332,"d":"9.4"},{"v":10.114285714285714,"d":"10.1"},{"$f":"IF(SUM(O16:O33)=0,O13,AVERAGE(O16:O33))","v":14.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7]
[null,null,{"$f":"+C10","v":31},29,31,30,31,30,31,31,30,31,30,31]
[0.07,"CHANCADO PRIMARIO",{"$nulls":9},{"v":1.5,"d":"2"},{"v":2.3,"d":"2"}]
[0.07,"CHANCADO SECUNDARIO",null,null,2,{"v":1.5,"d":"2"},null,2,2,2,null,null,1,2]
[0.07,"CHANCADO TERCIARIO",{"$nulls":5},3,null,null,{"v":1.5,"d":"2"}]
[0.06,"MOLIENDA",null,null,2,{"$nulls":3},1,{"$nulls":3},43]
[0.025,"PLANTA DE CAL"]
[0.07,"ABASTECIMIENTO DE AGUA",12.5]
[0.025,"REACTIVOS"]
[0.05,"FLOTACION Pb"]
[0.05,"FLOTACION Cu"]
[0.05,"FLOTACION Zn",{"$nulls":6},1,null,3,null,null,1]
[0.05,"FLOTACION Bulk"]
[0.07,"ESPESADORES",{"v":2,"d":"2.0"},null,null,2,{"$nulls":6},5]
[0.04,"FILTRADO Pb",{"$nulls":3},2]
[0.05,"FILTRADO Cu"]
[0.05,"FILTRADO Zn",null,null,1,{"$nulls":8},3,4]
[0.05,"FILTRADO Bulk"]
[0.06,"PLANTA DE NEUTRALIZACION",{"$nulls":12},2]
[0.09,"BOMBAS DE RELAVE",{"v":6,"d":"6.0"},null,7,{"$nulls":4},{"v":5.5,"d":"6"},{"$nulls":3},5]
[null,"MTTR TOTAL",{"$f":"IF(SUM(C36:C53)=0,C14,AVERAGE(C36:C53))","v":{"v":6.833333333333333,"d":"6.8"}},{"v":4.333333333333333,"d":"4.3"},{"v":3,"d":"3.0"},{"v":1.8333333333333333,"d":"1.8"},{"v":4,"d":"4.0"},2.5,{"v":1.3333333333333333,"d":"1.3"},{"v":3.75,"d":"3.8"},{"v":2.25,"d":"2.3"},1.5,{"v":12.825,"d":"12.8"},{"v":2.75,"d":"2.8"},{"$f":"IF(SUM(O36:O53)=0,O14,AVERAGE(O36:O53))","v":{"v":3,"d":"3.0"}},1.7,1.7,1.7,{"$f":"IF(SUM(S36:S53)=0,S14,AVERAGE(S36:S53))","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,{"$f":"IF(SUM(AN36:AN53)=0,AN14,AVERAGE(AN36:AN53))","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7]
[null,null,{"$f":"+C30","v":0},0,0,0,0,0,2,0,0,0,0,2]
[null,"DISPONIBILIDAD PLANTA","SEM01","SEM02","SEM03","SEM04","SEM05","SEM06","SEM07","SEM08","SEM09","SEM10","SEM11","SEM12","SEM13","SEM14","SEM15","SEM16","SEM17","SEM18","SEM19","SEM20","SEM21","SEM22","SEM23","SEM24","SEM25","SEM26","SEM27","SEM28","SEM29","SEM30","SEM31","SEM32","SEM33","SEM34","SEM35","SEM36","SEM37","SEM38","SEM39","SEM40","SEM41","SEM42","SEM43","SEM44","SEM45","SEM46","SEM47","SEM48","SEM49","SEM50","SEM51","SEM52","Promedio"]
[null,"DF Budget (Producción)",{"v":0.943,"d":"94.3%"},{"v":1.943,"d":"194.3%"},{"v":2.943,"d":"294.3%"},{"v":3.943,"d":"394.3%"},{"v":4.943,"d":"494.3%"},{"v":5.943,"d":"594.3%"},{"v":6.943,"d":"694.3%"},{"v":7.943,"d":"794.3%"},{"v":8.943,"d":"894.3%"},{"v":9.943,"d":"994.3%"},{"v":10.943,"d":"1094.3%"},{"v":11.943,"d":"1194.3%"},{"v":12.943,"d":"1294.3%"},{"v":13.943,"d":"1394.3%"},{"v":14.943,"d":"1494.3%"},{"v":15.943,"d":"1594.3%"},{"v":16.943,"d":"1694.3%"},{"v":17.943,"d":"1794.3%"},{"v":18.943,"d":"1894.3%"},{"v":19.943,"d":"1994.3%"},{"v":20.943,"d":"2094.3%"},{"v":21.943,"d":"2194.3%"},{"v":22.943,"d":"2294.3%"},{"v":23.943,"d":"2394.3%"},{"v":24.943,"d":"2494.3%"},{"v":25.943,"d":"2594.3%"},{"v":26.943,"d":"2694.3%"},{"v":27.943,"d":"2794.3%"},{"v":28.943,"d":"2894.3%"},{"v":29.943,"d":"2994.3%"},{"v":30.943,"d":"3094.3%"},{"v":31.943,"d":"3194.3%"},{"v":32.943,"d":"3294.3%"},{"v":33.943,"d":"3394.3%"},{"v":34.943,"d":"3494.3%"},{"v":35.943,"d":"3594.3%"},{"v":36.943,"d":"3694.3%"},{"v":37.943,"d":"3794.3%"},{"v":38.943,"d":"3894.3%"},{"v":39.943,"d":"3994.3%"},{"v":40.943,"d":"4094.3%"},{"v":41.943,"d":"4194.3%"},{"v":42.943,"d":"4294.3%"},{"v":43.943,"d":"4394.3%"},{"v":44.943,"d":"4494.3%"},{"v":45.943,"d":"4594.3%"},{"v":46.943,"d":"4694.3%"},{"v":47.943,"d":"4794.3%"},{"v":48.943,"d":"4894.3%"},{"v":49.943,"d":"4994.3%"},{"v":50.943,"d":"5094.3%"},{"v":51.943,"d":"5194.3%"}]
[null,"MTTR Budget",{"$f":"IF(C12=0,\"-\",C12)","v":1.7},{"$f":"IF(D12=0,\"-\",D12)","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,{"$f":"IF(M12=0,\"-\",M12)","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,{"$f":"AVERAGE(C58:O58)","v":{"v":1.6999999999999995,"d":"2"}}]
[null,"MTTR Forecast",{"$f":"IF(C13=0,\"-\",C13)","v":1.7},{"$f":"IF(D13=0,\"-\",D13)","v":1.7},1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,{"$f":"AVERAGE(C59:O59)","v":{"v":1.6999999999999995,"d":"2"}}]
[null,"MTTR Real",{"$f":"IF(C14=0,\"-\",C14)","v":5.3},{"$f":"IF(D14=0,\"-\",D14)","v":{"v":4.333333333333333,"d":"4.3"}},{"v":4.5285714285714285,"d":"4.5"},{"v":1.8285714285714287,"d":"1.8"},{"v":4,"d":"4.0"},{"v":10.533333333333333,"d":"10.5"},21.2,{"v":2.95,"d":"3.0"},{"$f":"IF(K14=0,\"-\",K14)","v":5.1},2.9,{"v":9.433333333333332,"d":"9.4"},{"v":10.114285714285714,"d":"10.1"},14.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,1.7,{"v":7.455494505494506,"d":"7"}]
[null,"MTTR Real - CONTR.",{"$f":"+C54","v":{"v":6.833333333333333,"d":"6.8"}},{"v":4.333333333333333,"d":"4.3"},{"v":3,"d":"3.0"},{"v":1.8333333333333333,"d":"1.8"},{"v":4,"d":"4.0"},2.5,{"$f":"+I54","v":{"v":1.3333333333333333,"d":"1.3"}},{"v":3.75,"d":"3.8"},{"$f":"+K54","v":{"v":2.25,"d":"2.3"}},1.5,{"v":12.825,"d":"12.8"},{"v":2.75,"d":"2.8"},{"v":3,"d":"3.0"},{"$nulls":38},{"$f":"IF(BB54=0,\"-\",+BB54)","v":1.7},{"v":3.839102564102564,"d":"4"}]
{"$rows_empty":27}
[null,"PRINCIPALES ACTIVIDADES"]
[null,null,"SEMANA N°1","ESPESADOR DE PLOMO",{"$nulls":4},"Fuga de carga por agujero en el codo de la tuberia HDPE de descarga"]
[{"$nulls":3},"BOMBA NOVA Nº1",{"$nulls":4},"Soltura de elemento de sujecion de bomba"]
[{"$nulls":3},"BOMBA MARS Nº2",{"$nulls":4},"Presencia de rotura del soporte de la estructura de valvulas neumaticas"]
[{"$nulls":3},"BOMBA VOGT Nº2 FILTRO PRENSA",{"$nulls":4},"Atoro de la bomba, por ingreso de material extraño"]
[{"$nulls":3},"BOMBA RIO TORRES Nº1",{"$nulls":4},"Fuga de carga por agujero de tuberia de descarga",{"$nulls":46},{"$f":"CONCATENATE(D94,\"; \",I94)","v":"BOMBA RIO TORRES Nº1; Fuga de carga por agujero de tuberia de descarga"}]
[null,null,"SEMANA N°2","MUESTREADOR DE RELAVE METSO",{"$nulls":4},"Quemadura de motor",{"$nulls":46},{"$f":"CONCATENATE(D95,\"; \",I95)","v":"MUESTREADOR DE RELAVE METSO; Quemadura de motor"}]
[{"$nulls":3},"CELDA WENCO ZN SCAVENGER N° 6",{"$nulls":4},"Rotura de estructura de motor por juego axial",{"$nulls":46},"CELDA WENCO ZN SCAVENGER N° 6; Rotura de estructura de motor por juego axial"]
[{"$nulls":3},"ZARANDA DE ALTA FRECUENCIA / SAF",{"$nulls":4},"Rotura de los portarodajes del motor",{"$nulls":46},"ZARANDA DE ALTA FRECUENCIA / SAF; Rotura de los portarodajes del motor"]
[null,null,"SEMANA N°3","CELDA DR 500 #02",{"$nulls":4},"Soltura de dispersor por corrosion de pernos de fijacion",{"$nulls":46},"CELDA DR 500 #02; Soltura de dispersor por corrosion de pernos de fijacion"]
[{"$nulls":3},"MOLINO #01",{"$nulls":4},"Soltura de pernos de chumacera del contraeje por vibracion excesiva",{"$nulls":46},"MOLINO #01; Soltura de pernos de chumacera del contraeje por vibracion excesiva"]
[{"$nulls":3},"BOMBA MARS #01",{"$nulls":4},"Fuga de aceite por la caja de transmision por falta de ajuste en el montaje",{"$nulls":46},"BOMBA MARS #01; Fuga de aceite por la caja de transmision por falta de ajuste en el montaje"]
[{"$nulls":3},"VALVULA NEUMATICA DESCARGA DE CALACON ALIMENTO A POZA DE MARS # 01",{"$nulls":4},"Fuga de carga por brida de la linea de la bomba vertical",{"$nulls":46},"VALVULA NEUMATICA DESCARGA DE CALACON ALIMENTO A POZA DE MARS # 01; Fuga de carga por brida de la linea de la bomba vertical"]
[{"$nulls":3},"CEDAZO # 01",{"$nulls":4},"Fuga de aceite en el tambor por excesiva vibracion ",{"$nulls":46},"CEDAZO # 01; Fuga de aceite en el tambor por excesiva vibracion "]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":4},"Falsa señal de final de carrera por descalibracion",{"$nulls":46},"FILTRO PRENSA; Falsa señal de final de carrera por descalibracion"]
[{"$nulls":3},"MOLINO FULLER ",{"$nulls":4},"Sonido elevado del reductor por desgaste de piñon",{"$nulls":46},"MOLINO FULLER ; Sonido elevado del reductor por desgaste de piñon"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº136",{"$nulls":4},"Fisura de manga por rosamiento de componente",{"$nulls":46},"BOMBA DOSIFICADORA Nº136; Fisura de manga por rosamiento de componente"]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":4},"Rotura de panel por ingreso de material extraño",{"$nulls":46},"CEDAZO 02 ; Rotura de panel por ingreso de material extraño"]
[{"$nulls":3},"BOMBA DE LUBRICACION #01 DE MOLINO 8X11",{"$nulls":4},"Rotura de acoplamiento omega por fatiga",{"$nulls":46},"BOMBA DE LUBRICACION #01 DE MOLINO 8X11; Rotura de acoplamiento omega por fatiga"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº122",{"$nulls":4},"Fisura de manga por rosamiento de componente",{"$nulls":46},"BOMBA DOSIFICADORA Nº122; Fisura de manga por rosamiento de componente"]
[null,null,"SEMANA N°4","ESPESADOR DE ZINC",{"$nulls":51},"Derrame de carga por fisura de manga de la valvula de descarga"]
[{"$nulls":3},"FILTRO CC 30",{"$nulls":51},"Vibracion excesiva por soltura de pernos de la chumacera de la rastra"]
[{"$nulls":3},"COMPRESORA ST1509",{"$nulls":51},"Parametro elevados por falta de señal a la valvula de alivio"]
[{"$nulls":3},"BOMBA DE LODOS 3 Y 4",{"$nulls":51},"Perdida de presion por ingreso de material extraño en la camara de bombeo"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":51},"Quemado de correas de transmision por desgaste de polea"]
[{"$nulls":3},"BOMBA DOSIFICADORA FLOTACION",{"$nulls":51},"Derrame de carga por fisura de manga"]
[{"$nulls":3},"DETECTOR DE METALES  FAJA 5A",{"$nulls":51},"Perdida de eficiencia por quemado de varistor"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Perdida de eficiencia por rotura de resorte de control de diafragma"]
[null,null,"SEMANA N°5","CELDA DENVER SUB A-24 Nº2",{"$nulls":51},"Recalentamiento de motor electrico por la presencia de pernos rotos"]
[{"$nulls":3},"SOPLADOR INGERSOLL RAND",{"$nulls":51},"Recalentamiento de soplador por obstruccion del filtro de aire"]
[null,null,"SEMANA N°6","BOMBA VERTICAL 02 DE RETORNO CURRIER ",{"$nulls":51},"Perdida de presion de bombeo por arenamiento"]
[{"$nulls":3},"CEDAZO #02",{"$nulls":51},"Rotura de fajas por desalineamiento"]
[{"$nulls":3},"BOMBA 02 DE MOLINO 8 X 11",{"$nulls":51},"Perdida de presion de bombeo por arenamiento"]
[{"$nulls":3},"BOMBA NOVA 02",{"$nulls":51},"Perdida de presion de bombeo por soltura  pernos de acoplamiento de rotor"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":51},"Alerta en el modulo de control del equipo"]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":51},"Rotura de fajas por desalineamiento"]
[{"$nulls":3},"CHANCADORA TERCIARIA ",{"$nulls":51},"Rotura de fajas por ingreso de material extraño"]
[{"$nulls":3},"FAJA 07 DE CHANCADO ",{"$nulls":51},"Soltura de cadena de transmision por desgaste"]
[{"$nulls":3},"CLARIFICADOR N° 3",{"$nulls":51},"Recalentamiento del motor por trabamiento de rodamientos del motor"]
[{"$nulls":3},"CEDAZO #01",{"$nulls":51},"Soltura de fajas por destemplado "]
[null,null,"SEMANA N°7","CEDAZO 02",{"$nulls":51},"Se amarro los rodamiento del tambor por mala reparacion"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":51},"Rotura del templador por sobreesfuerzo en el sistema de transmision(tambor)"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":51},"Perdida de señal de eficiencia en final de carrera por descalibracion de sensor"]
[{"$nulls":3},"BOMBAS NOVA 4",{"$nulls":51},"Perdida de señal en la activacion del actuador de la boya, por cumplimiento de vida util"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":51},"Quemado de correas por ingreso de inchancable(restos de jebe)"]
[{"$nulls":3},"BOMBA # 01 DE CELDA SK 240",{"$nulls":51},"Perdida de presion de bombeo por arenamiento  en la linea de alimentacion"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":51},"Quemado de correas por ingreso de inchancable(restos de jebe)"]
[{"$nulls":3},"FAJA N° 7",{"$nulls":51},"Sonido en el motoreductor por presencia de desgaste de rodamientos"]
[{"$nulls":3},"BOMBA 77 A",{"$nulls":51},"Quemado de correas por desalineamiento(polea conducida con desgaste)"]
[{"$nulls":3},"CELDA SP-18 ",{"$nulls":51},"Rotura de correa de transmision por fatiga(01 correa)"]
[{"$nulls":3},"FAJA 5D DE CHANCADO",{"$nulls":51},"Soltura de empalme de la banda por ingreso de material extraño(carga abrasiva)"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":51},"Cables de control en mal estado por ambiente inadecuado"]
[null,null,"SEMANA N°8","FAJA TRANSPORTADORA DE ALIMENTO AL MOLINO 8X11",{"$nulls":51},"Angulo de raspador en contacto con la banda transportadora (genero cortes pqueños)"]
[{"$nulls":3},"BOMBA MARS 04",{"$nulls":51},"Presencia de pernos rotos de media luna de la botella de mezcla"]
[{"$nulls":3},"BOMBA 1.5 COURIER CONCENTRADO DE PLOMO",{"$nulls":51},"Presencia de fisuras en la tuberia de descarga"]
[{"$nulls":3},"BOMBA HIDROSTAL EF05 Nº1",{"$nulls":51},"Fuga de agua por sellos mecanicos de la bomba"]
[{"$nulls":3},"FAJA 5C DE CHANCADO",{"$nulls":51},"Cadena de transmision RS 100 trabada"]
[{"$nulls":3},"BOMBA MARS 02",{"$nulls":51},"Perdida de eficiencia de la valvula de descarga (presenta oxidacion excesiva)"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":51},"Mallas con agujeros producto del trabajo"]
[null,null,"SEMANA N°9","BOMBA DE LODOS N° 6",{"$nulls":51},"Parada operativa por reporte de atoramiento en el sistema de bombeo"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":51},"Rotura de chumacera de la base del motor electrico por desalineamiento del sistema de transmision"]
[{"$nulls":3},"BOMBA 77 B",{"$nulls":51},"Fuga de carga por desgaste de la bocina"]
[{"$nulls":3},"BOMBA PERISTATICA Nª3 DE CAL",{"$nulls":51},"Fuga de carga de la bomba por desgaste del reten"]
[{"$nulls":3},"CEDAZO 01",{"$nulls":51},"Parada operativa en el sistema de selección de mineral(malla sflex), ingreso de mineral grande"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":51},"Rotura de chumacera de la base del motor electrico por desalineamiento del sistema de transmision"]
[{"$nulls":3},"BOMBA 77 \"A\"",{"$nulls":51},"Fuga de carga en la tuberia de alimento, por desgaste"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Perdida de eficiencia de la unidad de la compresora(valvula espiral) por cumplimiento de vida util de los componentes"]
[null,null,"SEMANA N°10","BOMBAS MARS 04",{"$nulls":51},"Perdida de presion de bombeo por perforacion de asientos de valvulas, debido al ingreso de material extraño"]
[{"$nulls":3},"CICLON DE RELAVERA",{"$nulls":51},"Fuga de carga en la linea de descarga por rotura de manga de 6\""]
[{"$nulls":3},"BOMBA DE LODOS # 04",{"$nulls":51},"Recalentamiento de caja de rodamientos por parametros alto de temperatura y envolvente"]
[{"$nulls":3},"BOMBA Nº106 - ESPESADOR DE ZINC",{"$nulls":51},"Deterioro de contactos de motor electrico por rebalse de carga"]
[{"$nulls":3},"ESPESADOR DE ZINC",{"$nulls":51},"Fuga de carga por rotura de manga de la linea de descarga"]
[{"$nulls":3},"CHANCADORA PRIMARIA",{"$nulls":51},"Soltura de forro movil por rotura de perno"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":51},"Ingreso de material grande, por malla inadecuada"]
[{"$nulls":3},"BOMBA MARS Nº04",{"$nulls":51},"Perdida de presion de bombeo por perforacion de asientos de valvulas, debido al ingreso de material extraño"]
[{"$nulls":3},"BOMBA VERTICAL 2.5 STD DE RETORNO DE COURIER Nº02",{"$nulls":51},"Fuga de carga, por arenamiento de la linea de alimentacion "]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Perdida de eficiencia de la unidad de la compresora(valvula espiral) por cumplimiento de vida util de los componentes"]
[null,null,"SEMANA N°11","FAJA Nº 03 DE CHANCADO",{"$nulls":51},"Fuga de carga por desalineamiento de banda transportadora"]
[{"$nulls":3},"MOLINO Nº2",{"$nulls":51},"Rotura de eje de volante por fatifa estructural del eje"]
[{"$nulls":3},"BOMBA 104",{"$nulls":51},"Desgaste prematuro de forro debido al diseño"]
[{"$nulls":3},"BOMBA VERTICAL 1,5 Nº09 DEL ESPESADOR DE RELAVE",{"$nulls":51},"Desgaste y mucha holgura de las fajas de transmision generados por desalineamiento"]
[{"$nulls":3},"ESPESADOR DE ZINC",{"$nulls":51},"Manga con fisuras y cortes producto de la degeneracion ocacionada por la pulpa del mineral"]
[{"$nulls":3},"CEDAZO Nº01",{"$nulls":51},"Desgaste y mucha holgura de las fajas de transmision generados por desalineamiento"]
[{"$nulls":3},"BOMBA 106",{"$nulls":51},"Manga con fisuras y cortes producto de la degeneracion ocacionada por la pulpa del mineral"]
[{"$nulls":3},"FAJA Nº01 DE PB",{"$nulls":51},"Soltura de cadena de transmision debido a ajuste inadecuado"]
[{"$nulls":3},"FAJA Nº 02 DE CHANCADO",{"$nulls":51},"Estructura doblada de electroiman debido a la fatiga de la estructura por tiempo de vida util"]
[null,null,"SEMANA N°12","BOMBA MARS L-180 N° 4",{"$nulls":51},"Rotura de piston rod por fatiga del sistema de bombeo"]
[{"$nulls":3},"CEDAZO # 01",{"$nulls":51},"Rotura de correas de transmision por desalineamiento"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":51},"Rotura de pernos de fijacion de los tacos de las placas por sobreesfuerzo"]
[{"$nulls":3},"FAJA TRANSPORTADORA N°5D ",{"$nulls":51},"Resane de empalme de  banda transportadora por presencia de carga abrasiva"]
[{"$nulls":3},"BOMBA CENTRIFUGA 77 A, 6X4 AH WARMAN ",{"$nulls":51},"Rotura de correas de transmision por desalineamiento"]
[{"$nulls":3},"BOMBA VERTICAL 1.5 DE RELAVE GENERAL ",{"$nulls":51},"Rotura de correas de transmision por desalineamiento"]
[{"$nulls":3},"CEDAZO #01",{"$nulls":51},"Parada operativa(cambio de mallas para seleccion de mineral)"]
[{"$nulls":3},"COMPRESORA TS20 #01",{"$nulls":51},"Rotura de acople omega de 20\" por fatiga de componente"]
[{"$nulls":3},"COMPRESORA TS20 #01",{"$nulls":51},"Activavion de alerta  de presion alta por rotura de acoplamiento omega"]
[{"$nulls":3},"CEDAZO # 02 ",{"$nulls":51},"Rotura de paneles por ingreso de mineral grande"]
[{"$nulls":3},"SOPLADOR SPENCER",{"$nulls":51},"Parada de arranque de motor electrico por sobrecarga"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Perdida de eficiencia de la unidad de la compresora(valvula espiral) por cumplimiento de vida util de los componentes"]
[null,null,"SEMANA N°13","BOMBA DE CICLON DE CAL ",{"$nulls":51},"Fuga de carga en el sistema de bombeo por desgaste del cover plate",{"$f":"CONCATENATE(D187,\"; \",BD187)","v":"BOMBA DE CICLON DE CAL ; Fuga de carga en el sistema de bombeo por desgaste del cover plate"}]
[{"$nulls":3},"MOTOR DE ZARANDA DE ALTA FRECUENCIA",{"$nulls":51},"Temperatura alta por desgaste de rodamientos del motor",{"$f":"CONCATENATE(D188,\"; \",BD188)","v":"MOTOR DE ZARANDA DE ALTA FRECUENCIA; Temperatura alta por desgaste de rodamientos del motor"}]
[{"$nulls":3},"LÍNEA DE DESCARGA DE HIDROCICLÓN RELAVE",{"$nulls":51},"Rotura de tuberis de la linea de descarga del ciclon por corrosion","LÍNEA DE DESCARGA DE HIDROCICLÓN RELAVE; Rotura de tuberis de la linea de descarga del ciclon por corrosion"]
[{"$nulls":3},"BOMBA DE LODOS Nº 4",{"$nulls":51},"Fuga de carga por desgaste de la bocina","BOMBA DE LODOS Nº 4; Fuga de carga por desgaste de la bocina"]
[{"$nulls":3},"FAJA 1 DE CAL",{"$nulls":51},"Desgaste de raspador en el sistema de transporte de carga","FAJA 1 DE CAL; Desgaste de raspador en el sistema de transporte de carga"]
[{"$nulls":3},"BOMBA HORIZONTAL 103",{"$nulls":51},"Fuga de carga en el sistema de bombeo por desgaste del cover plate","BOMBA HORIZONTAL 103; Fuga de carga en el sistema de bombeo por desgaste del cover plate"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":51},"Fuga de aceite por corte de manguera del sistema hidraulico","FILTRO PRENSA; Fuga de aceite por corte de manguera del sistema hidraulico"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Perdida de eficiencia de la unidad de la compresora(valvula espiral) por cumplimiento de vida util de los componentes","COMPRESORA TS 20 FILTRO PRENSA; Perdida de eficiencia de la unidad de la compresora(valvula espiral) por cumplimiento de vida util de los componentes"]

{"sheet":"MTBF_SEM","index":17,"n_rows":194,"n_cols":57,"rows_kept":194,"merged":[[7,2,7,13],[89,2,93,2],[89,3,89,7],[89,8,89,13],[90,3,90,7],[90,8,90,13],[91,3,91,7],[91,8,91,13],[92,3,92,7],[92,8,92,13],[93,3,93,7],[93,8,93,13],[94,2,96,2],[94,3,94,7],[94,8,94,13],[95,3,95,7],[95,8,95,13],[96,3,96,7],[96,8,96,13],[97,2,107,2],[97,3,97,7],[97,8,97,13],[98,3,98,7],[98,8,98,13],[99,3,99,7],[99,8,99,13],[100,3,100,7],[100,8,100,13],[101,3,101,7],[101,8,101,13],[102,3,102,7],[102,8,102,13],[103,3,103,7],[103,8,103,13],[104,3,104,7],[104,8,104,13],[105,3,105,7],[105,8,105,13],[106,3,106,7],[106,8,106,13],[107,3,107,7],[107,8,107,13],[108,2,115,2],[108,3,108,7],[109,3,109,7],[110,3,110,7],[111,3,111,7],[112,3,112,7],[113,3,113,7],[114,3,114,7],[115,3,115,7],[116,2,117,2],[116,3,116,7],[117,3,117,7],[118,2,127,2],[118,3,118,7],[119,3,119,7],[120,3,120,7],[121,3,121,7],[122,3,122,7],[123,3,123,7],[124,3,124,7],[125,3,125,7],[126,3,126,7],[127,3,127,7],[128,2,139,2],[128,3,128,7],[129,3,129,7],[130,3,130,7],[131,3,131,7],[132,3,132,7],[133,3,133,7],[134,3,134,7],[135,3,135,7],[136,3,136,7],[137,3,137,7],[138,3,138,7],[139,3,139,7],[140,2,146,2],[147,2,154,2],[155,2,164,2],[165,2,173,2],[174,2,185,2],[186,2,193,2]]}
[null,"MTBF PLANTA CONCENTRADORA 2024",{"$nulls":6},"MTBF",65,null,"MTTR",{"$f":"+DISP_PLANTA!M1","v":1.7}]
[]
[null,null,"2012-01-01","2012-02-01","2012-03-01","2012-04-01","2012-05-01"]
[null,"MTBF",{"v":22.921034482758625,"d":"22.9"},{"v":29.868571428571425,"d":"29.9"},{"v":21.071290322580644,"d":"21.1"},{"v":28.742272727272734,"d":"28.7"},{"v":40.345882352941175,"d":"40.3"}]
[null,"MTTR",{"v":1.358620689655173,"d":"1.4"},{"v":0.7095238095238091,"d":"0.7"},{"v":1.4032258064516132,"d":"1.4"},{"v":1.6143939393939393,"d":"1.6"},{"v":0.5872549019607843,"d":"0.6"}]
[]
[]
[null,null,2024]
[]
[null,null,31,29,31,30,31,30,31,31,30,31,30,31]
[null,"MTBF","SEM01","SEM02","SEM03","SEM04","SEM05","SEM06","SEM07","SEM08","SEM09","SEM10","SEM11","SEM12","SEM13","SEM14","SEM15","SEM16","SEM17","SEM18","SEM19","SEM20","SEM21","SEM22","SEM23","SEM24","SEM25","SEM26","SEM27","SEM28","SEM29","SEM30","SEM31","SEM32","SEM33","SEM34","SEM35","SEM36","SEM37","SEM38","SEM39","SEM40","SEM41","SEM42","SEM43","SEM44","SEM45","SEM46","SEM47","SEM48","SEM49","SEM50","SEM51","SEM52"]
[0.2,"PLANEADO",{"$f":"+$J$1","v":65},65,65,{"$f":"+$J$1","v":65},65,65,65,65,65,65,65,65,65,65,65,65,65,{"$f":"+$J$1","v":65},65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65]
[0.2,"PROYECTADO",65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65]
[0.2,"REALIZADO",{"$f":"C34","v":72},168,128,156,120,{"v":76.66666666666667,"d":"77"},140,119,{"v":100.8,"d":"101"},120,126,116,{"v":128.8,"d":"129"},65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65,65]
[]
[0.07,"CHANCADO PRIMARIO",{"$nulls":3},{"v":168,"d":"168.0"},{"$nulls":5},{"v":120,"d":"120.0"},{"v":84,"d":"84.0"}]
[0.07,"CHANCADO SECUNDARIO",null,null,{"v":168,"d":"168.0"},{"v":84,"d":"84.0"},null,{"v":60,"d":"60.0"},{"v":56,"d":"56.0"},{"v":84,"d":"84.0"},{"v":144,"d":"144.0"},{"v":120,"d":"120.0"},{"v":168,"d":"168.0"},{"v":84,"d":"84.0"}]
[0.07,"CHANCADO TERCIARIO",null,null,{"v":168,"d":"168.0"},null,null,{"v":40,"d":"40.0"},{"v":56,"d":"56.0"},null,{"v":72,"d":"72.0"},null,null,{"v":84,"d":"84.0"}]
[0.06,"MOLIENDA",null,{"v":168,"d":"168.0"},{"v":56,"d":"56.0"},null,null,{"v":120,"d":"120.0"},{"v":168,"d":"168.0"},{"v":168,"d":"168.0"},{"v":144,"d":"144.0"},{"v":120,"d":"120.0"},{"v":168,"d":"168.0"},{"v":56,"d":"56.0"},{"v":56,"d":"56.0"}]
[0.025,"PLANTA DE CAL",{"$nulls":12},{"v":84,"d":"84.0"}]
[0.07,"ABASTECIMIENTO DE AGUA",{"v":72,"d":"72.0"}]
[0.025,"REACTIVOS",null,null,{"v":84,"d":"84.0"}]
[0.05,"FLOTACION Pb",null,null,{"v":168,"d":"168.0"}]
[0.05,"FLOTACION Cu",{"$nulls":3},{"v":168,"d":"168.0"},null,null,{"v":168,"d":"168.0"},{"$nulls":5},{"v":168,"d":"168.0"}]
[0.05,"FLOTACION Zn",null,{"v":168,"d":"168.0"},null,{"v":168,"d":"168.0"},{"v":120,"d":"120.0"},null,{"v":168,"d":"168.0"},null,{"v":72,"d":"72.0"},{"v":120,"d":"120.0"},{"v":168,"d":"168.0"},{"v":168,"d":"168.0"}]
[0.05,"FLOTACION Bulk"]
[0.07,"ESPESADORES",{"v":72,"d":"72.0"},null,null,{"v":168,"d":"168.0"},{"$nulls":5},{"v":120,"d":"120.0"},{"v":84,"d":"84.0"}]
[0.04,"FILTRADO Pb",{"v":72,"d":"72.0"},null,null,{"v":168,"d":"168.0"},null,{"v":120,"d":"120.0"},null,{"v":168,"d":"168.0"},null,null,{"v":84,"d":"84.0"}]
[0.05,"FILTRADO Cu",{"$nulls":5},{"v":60,"d":"60.0"},{"v":168,"d":"168.0"}]
[0.05,"FILTRADO Zn",null,null,{"v":168,"d":"168.0"},{"$nulls":3},{"v":168,"d":"168.0"},null,null,{"v":120,"d":"120.0"},null,{"v":84,"d":"84.0"},{"v":168,"d":"168.0"}]
[0.05,"FILTRADO Bulk"]
[0.06,"PLANTA DE NEUTRALIZACION",{"v":72,"d":"72.0"},null,null,{"v":168,"d":"168.0"},{"v":120,"d":"120.0"},{"v":60,"d":"60.0"},{"v":168,"d":"168.0"},null,{"v":72,"d":"72.0"},{"v":120,"d":"120.0"},null,{"v":168,"d":"168.0"},{"v":168,"d":"168.0"}]
[0.09,"BOMBAS DE RELAVE",{"v":72,"d":"72.0"},{"v":168,"d":"168.0"},{"v":84,"d":"84.0"},{"$nulls":4},{"v":56,"d":"56.0"},null,{"v":120,"d":"120.0"},null,{"v":168,"d":"168.0"}]
[null,"MTBF TOTAL",{"$f":"IF(SUM(C16:C33)=0,C13,AVERAGE(C16:C33))","v":{"v":72,"d":"72.0"}},{"$f":"IF(SUM(D16:D33)=0,D13,AVERAGE(D16:D33))","v":{"v":168,"d":"168.0"}},{"$f":"IF(SUM(E16:E33)=0,E13,AVERAGE(E16:E33))","v":{"v":128,"d":"128.0"}},{"$f":"IF(SUM(F16:F33)=0,F13,AVERAGE(F16:F33))","v":{"v":156,"d":"156.0"}},{"$f":"IF(SUM(G16:G33)=0,G13,AVERAGE(G16:G33))","v":{"v":120,"d":"120.0"}},{"v":76.66666666666667,"d":"76.7"},{"v":140,"d":"140.0"},{"v":119,"d":"119.0"},{"$f":"IF(SUM(K16:K33)=0,K13,AVERAGE(K16:K33))","v":100.8},{"v":120,"d":"120.0"},{"v":126,"d":"126.0"},{"v":116,"d":"116.0"},{"$f":"IF(SUM(O16:O33)=0,O13,AVERAGE(O16:O33))","v":128.8},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"$f":"IF(SUM(BB16:BB33)=0,BB13,AVERAGE(BB16:BB33))","v":{"v":65,"d":"65.0"}}]
[null,null,{"$f":"+C10","v":31},29,31,30,31,30,31,31,30,31,30,31]
[0.07,"CHANCADO PRIMARIO",{"$nulls":9},{"v":120,"d":"120.0"},{"v":84,"d":"84.0"}]
[0.07,"CHANCADO SECUNDARIO",null,null,{"v":2,"d":"2.0"},{"v":168,"d":"168.0"},null,{"v":120,"d":"120.0"},{"v":168,"d":"168.0"},{"v":84,"d":"84.0"},null,null,{"v":168,"d":"168.0"},{"v":168,"d":"168.0"}]
[0.07,"CHANCADO TERCIARIO",{"$nulls":5},{"v":120,"d":"120.0"},null,null,{"v":72,"d":"72.0"}]
[0.06,"MOLIENDA",null,null,{"v":2,"d":"2.0"},{"$nulls":3},{"v":168,"d":"168.0"},{"$nulls":3},{"v":168,"d":"168.0"}]
[0.025,"PLANTA DE CAL"]
[0.07,"ABASTECIMIENTO DE AGUA",{"v":72,"d":"72.0"}]
[0.025,"REACTIVOS"]
[0.05,"FLOTACION Pb"]
[0.05,"FLOTACION Cu"]
[0.05,"FLOTACION Zn",{"$nulls":6},{"v":168,"d":"168.0"},null,{"v":144,"d":"144.0"},null,null,{"v":168,"d":"168.0"}]
[0.05,"FLOTACION Bulk"]
[0.07,"ESPESADORES",{"v":72,"d":"72.0"},null,null,{"v":168,"d":"168.0"},{"$nulls":6},{"v":168,"d":"168.0"}]
[0.04,"FILTRADO Pb",{"$nulls":3},{"v":168,"d":"168.0"}]
[0.05,"FILTRADO Cu"]
[0.05,"FILTRADO Zn",null,null,{"v":1,"d":"1.0"},{"$nulls":8},{"v":168,"d":"168.0"},{"v":168,"d":"168.0"}]
[0.05,"FILTRADO Bulk"]
[0.06,"PLANTA DE NEUTRALIZACION",{"$nulls":12},{"v":168,"d":"168.0"}]
[0.09,"BOMBAS DE RELAVE",{"v":72,"d":"72.0"},null,{"v":7,"d":"7.0"},{"$nulls":4},{"v":84,"d":"84.0"},{"$nulls":3},{"v":168,"d":"168.0"}]
[null,"MTBF CONTRACTUAL",{"$f":"IF(SUM(C36:C53)=0,C14,AVERAGE(C36:C53))","v":{"v":72,"d":"72.0"}},{"$f":"IF(SUM(D36:D53)=0,D14,AVERAGE(D36:D53))","v":{"v":168,"d":"168.0"}},{"$f":"IF(SUM(E36:E53)=0,E14,AVERAGE(E36:E53))","v":{"v":3,"d":"3.0"}},{"$f":"IF(SUM(F36:F53)=0,F14,AVERAGE(F36:F53))","v":{"v":168,"d":"168.0"}},{"$f":"IF(SUM(G36:G53)=0,G14,AVERAGE(G36:G53))","v":{"v":120,"d":"120.0"}},{"v":120,"d":"120.0"},{"v":168,"d":"168.0"},{"v":84,"d":"84.0"},{"v":108,"d":"108.0"},{"v":120,"d":"120.0"},{"v":147,"d":"147.0"},{"v":168,"d":"168.0"},{"$f":"IF(SUM(O36:O53)=0,O14,AVERAGE(O36:O53))","v":{"v":168,"d":"168.0"}},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"$f":"IF(SUM(S36:S53)=0,S14,AVERAGE(S36:S53))","v":{"v":65,"d":"65.0"}},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":0,"d":"0.0"}]
[null,null,{"$f":"+C30","v":0},0,168,0,0,0,168,0,0,120,0,84]
[null,{"$f":"+B1","v":"MTBF PLANTA CONCENTRADORA 2024"},"SEM01","SEM02","SEM03","SEM04","SEM05","SEM06","SEM07","SEM08","SEM09","SEM10","SEM11","SEM12","SEM13","SEM14","SEM15","SEM16","SEM17","SEM18","SEM19","SEM20","SEM21","SEM22","SEM23","SEM24","SEM25","SEM26","SEM27","SEM28","SEM29","SEM30","SEM31","SEM32","SEM33","SEM34","SEM35","SEM36","SEM37","SEM38","SEM39","SEM40","SEM41","SEM42","SEM43","SEM44","SEM45","SEM46","SEM47","SEM48","SEM49","SEM50","SEM51","SEM52","Promedio"]
[null,"DF Budget (Producción)",{"v":0.943,"d":"94.3%"},{"v":1.943,"d":"194.3%"},{"v":2.943,"d":"294.3%"},{"v":3.943,"d":"394.3%"},{"v":4.943,"d":"494.3%"},{"v":5.943,"d":"594.3%"},{"v":6.943,"d":"694.3%"},{"v":7.943,"d":"794.3%"},{"v":8.943,"d":"894.3%"},{"v":9.943,"d":"994.3%"},{"v":10.943,"d":"1094.3%"},{"v":11.943,"d":"1194.3%"},{"v":12.943,"d":"1294.3%"},{"v":13.943,"d":"1394.3%"},{"v":14.943,"d":"1494.3%"},{"v":15.943,"d":"1594.3%"},{"v":16.943,"d":"1694.3%"},{"v":17.943,"d":"1794.3%"},{"v":18.943,"d":"1894.3%"},{"v":19.943,"d":"1994.3%"},{"v":20.943,"d":"2094.3%"},{"v":21.943,"d":"2194.3%"},{"v":22.943,"d":"2294.3%"},{"v":23.943,"d":"2394.3%"},{"v":24.943,"d":"2494.3%"},{"v":25.943,"d":"2594.3%"},{"v":26.943,"d":"2694.3%"},{"v":27.943,"d":"2794.3%"},{"v":28.943,"d":"2894.3%"},{"v":29.943,"d":"2994.3%"},{"v":30.943,"d":"3094.3%"},{"v":31.943,"d":"3194.3%"},{"v":32.943,"d":"3294.3%"},{"v":33.943,"d":"3394.3%"},{"v":34.943,"d":"3494.3%"},{"v":35.943,"d":"3594.3%"},{"v":36.943,"d":"3694.3%"},{"v":37.943,"d":"3794.3%"},{"v":38.943,"d":"3894.3%"},{"v":39.943,"d":"3994.3%"},{"v":40.943,"d":"4094.3%"},{"v":41.943,"d":"4194.3%"},{"v":42.943,"d":"4294.3%"},{"v":43.943,"d":"4394.3%"},{"v":44.943,"d":"4494.3%"},{"v":45.943,"d":"4594.3%"},{"v":46.943,"d":"4694.3%"},{"v":47.943,"d":"4794.3%"},{"v":48.943,"d":"4894.3%"},{"v":49.943,"d":"4994.3%"},{"v":50.943,"d":"5094.3%"},{"v":51.943,"d":"5194.3%"}]
[null,"MTBF Budget",{"$f":"IF(C12=0,\"-\",C12)","v":{"v":65,"d":"65.0"}},{"$f":"IF(D12=0,\"-\",D12)","v":{"v":65,"d":"65.0"}},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"$f":"AVERAGE(C58:O58)","v":65}]
[null,"MTBF Forecast",{"$f":"IF(C13=0,\"-\",C13)","v":{"v":65,"d":"65.0"}},{"$f":"IF(D13=0,\"-\",D13)","v":{"v":65,"d":"65.0"}},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"$f":"AVERAGE(C59:O59)","v":65}]
[null,"MTBF Real",{"$f":"IF(C14=0,\"-\",C14)","v":{"v":72,"d":"72.0"}},{"$f":"IF(D14=0,\"-\",D14)","v":{"v":168,"d":"168.0"}},{"v":128,"d":"128.0"},{"v":156,"d":"156.0"},{"v":120,"d":"120.0"},{"v":76.66666666666667,"d":"76.7"},{"v":140,"d":"140.0"},{"v":119,"d":"119.0"},{"$f":"IF(K14=0,\"-\",K14)","v":100.8},{"v":120,"d":"120.0"},{"v":126,"d":"126.0"},{"v":116,"d":"116.0"},128.8,{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},"-",{"v":120.86666666666666,"d":"121"}]
[null,"MTBF Real - CONTR",{"$f":"+C54","v":{"v":72,"d":"72.0"}},{"v":168,"d":"168.0"},{"$f":"+E54","v":{"v":3,"d":"3.0"}},{"v":168,"d":"168.0"},{"v":120,"d":"120.0"},{"v":120,"d":"120.0"},{"v":168,"d":"168.0"},{"v":84,"d":"84.0"},{"$f":"+K54","v":{"v":108,"d":"108.0"}},{"v":120,"d":"120.0"},{"v":147,"d":"147.0"},{"v":168,"d":"168.0"},{"v":168,"d":"168.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":65,"d":"65.0"},{"v":0,"d":"0.0"},{"v":124.15384615384616,"d":"124"}]
{"$rows_empty":27}
[null,"PRINCIPALES ACTIVIDADES"]
[null,null,"SEMANA N°1","ESPESADOR DE PLOMO",{"$nulls":4},"Termofusionado de codo con autogeno e inspeccion de la linea de tuberias"]
[{"$nulls":3},"BOMBA NOVA Nº1",{"$nulls":4},"Reajuste de elementos de sujecion y verificacion de alineamientos"]
[{"$nulls":3},"BOMBA MARS Nº2",{"$nulls":4},"Reparacion de soporte de las válvulas nemáticas"]
[{"$nulls":3},"BOMBA VOGT Nº2 FILTRO PRENSA",{"$nulls":4},"Limpieza de carga de la bomba VOGT e inspeccion del estado del impulsor"]
[{"$nulls":3},"BOMBA RIO TORRES Nº1",{"$nulls":4},"Desembridado de válvula de cuchilla de 8\" para drenaje de agua de las quenas y reparacion de agujeros de tuberia"]
[null,null,"SEMANA N°2","MUESTREADOR DE RELAVE METSO",{"$nulls":4},"Cambio de cadena y alineamiento de motor"]
[{"$nulls":3},"CELDA WENCO ZN SCAVENGER N° 6",{"$nulls":4},"Reparacion de estructura de motor"]
[{"$nulls":3},"ZARANDA DE ALTA FRECUENCIA / SAF",{"$nulls":4},"Reparacion de estructura de motor"]
[null,null,"SEMANA N°3","CELDA DR 500 #02",{"$nulls":4},"Cambio de pernos de fijacion del dispersor",{"$nulls":46},{"$f":"CONCATENATE(D98,\"; \",I98)","v":"CELDA DR 500 #02; Cambio de pernos de fijacion del dispersor"}]
[{"$nulls":3},"MOLINO #01",{"$nulls":4},"Ajuste de pernos de chumacera del contraeje",{"$nulls":46},{"$f":"CONCATENATE(D99,\"; \",I99)","v":"MOLINO #01; Ajuste de pernos de chumacera del contraeje"}]
[{"$nulls":3},"BOMBA MARS #01",{"$nulls":4},"Ajuste de pernos de fijacion de la caja de transmision",{"$nulls":46},"BOMBA MARS #01; Ajuste de pernos de fijacion de la caja de transmision"]
[{"$nulls":3},"VALVULA NEUMATICA DESCARGA DE CALACON ALIMENTO A POZA DE MARS # 01",{"$nulls":4},"Reparacion de la  brida de  la linea de descarga de la bomba vertical",{"$nulls":46},"VALVULA NEUMATICA DESCARGA DE CALACON ALIMENTO A POZA DE MARS # 01; Reparacion de la  brida de  la linea de descarga de la bomba vertical"]
[{"$nulls":3},"CEDAZO # 01",{"$nulls":4},"Ajuste de los pernos del tambor ",{"$nulls":46},"CEDAZO # 01; Ajuste de los pernos del tambor "]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":4},"Calibracion y seguimiento del final de carrera",{"$nulls":46},"FILTRO PRENSA; Calibracion y seguimiento del final de carrera"]
[{"$nulls":3},"MOLINO FULLER ",{"$nulls":4},"Cambio de aceite del reductor y medicion de desgaste del piñon",{"$nulls":46},"MOLINO FULLER ; Cambio de aceite del reductor y medicion de desgaste del piñon"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº136",{"$nulls":4},"Cambio de manga ",{"$nulls":46},"BOMBA DOSIFICADORA Nº136; Cambio de manga "]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":4},"Cambiuo de panel y piunes de sujecion",{"$nulls":46},"CEDAZO 02 ; Cambiuo de panel y piunes de sujecion"]
[{"$nulls":3},"BOMBA DE LUBRICACION #01 DE MOLINO 8X11",{"$nulls":4},"Cambio de acoplamiento y alineamiento del sistema de transmision",{"$nulls":46},"BOMBA DE LUBRICACION #01 DE MOLINO 8X11; Cambio de acoplamiento y alineamiento del sistema de transmision"]
[{"$nulls":3},"BOMBA DOSIFICADORA Nº122",{"$nulls":4},"Cambio de manga ",{"$nulls":46},"BOMBA DOSIFICADORA Nº122; Cambio de manga "]
[null,null,"SEMANA N°4","ESPESADOR DE ZINC",{"$nulls":51},"Se cambio manga de la valvula de descarga"]
[{"$nulls":3},"FILTRO CC 30",{"$nulls":51},"Se ajusto  pernos de la chumacera de la rastra y se alineo el sistema de transmision"]
[{"$nulls":3},"COMPRESORA ST1509",{"$nulls":51},"Se realizo mantenimiento de la  valvula de alivio"]
[{"$nulls":3},"BOMBA DE LODOS 3 Y 4",{"$nulls":51},"Se reviso y retiromaterial extraño en la camara de bombeo"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":51},"Se cambio correas y las poleas  del sistema de  transmision"]
[{"$nulls":3},"BOMBA DOSIFICADORA FLOTACION",{"$nulls":51},"Se cambio manga y glicerina"]
[{"$nulls":3},"DETECTOR DE METALES  FAJA 5A",{"$nulls":51},"Se realizo el cambio del varistor y regulacion de parametros"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Se cambio resorte de control de diafragma"]
[null,null,"SEMANA N°5","CELDA DENVER SUB A-24 Nº2",{"$nulls":51},"Se realiza cambio de pernos y seguimiento del funcionamiento"]
[{"$nulls":3},"SOPLADOR INGERSOLL RAND",{"$nulls":51},"Se realiza cambio de filtro de aire, nivelacion de aceite y seguimiento del funcionamiento"]
[null,null,"SEMANA N°6","BOMBA VERTICAL 02 DE RETORNO CURRIER ",{"$nulls":51},"Se realizo desarenamiento de la linea de bombeo"]
[{"$nulls":3},"CEDAZO #02",{"$nulls":51},"Se cambio las fajas de trasmision"]
[{"$nulls":3},"BOMBA 02 DE MOLINO 8 X 11",{"$nulls":51},"Se realizo desarenamiento de sistema de bombeo"]
[{"$nulls":3},"BOMBA NOVA 02",{"$nulls":51},"Se ajusto los  pernos de acoplamiento de rotor"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":51},"Equipo fuera de servicio"]
[{"$nulls":3},"CEDAZO 02 ",{"$nulls":51},"Se cambio las fajas de trasmision"]
[{"$nulls":3},"CHANCADORA TERCIARIA ",{"$nulls":51},"Se cambio las fajas  de transmision"]
[{"$nulls":3},"FAJA 07 DE CHANCADO ",{"$nulls":51},"Se cambio y templo la cadena de transmision "]
[{"$nulls":3},"CLARIFICADOR N° 3",{"$nulls":51},"Se cambio el motor electrico y se alineo las poleas"]
[{"$nulls":3},"CEDAZO #01",{"$nulls":51},"Se realizo el templado de las fajas de transmision"]
[null,null,"SEMANA N°7","CEDAZO 02",{"$nulls":51},"Se reinstalo el  tambor por falla del tambor reparado"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":51},"Se cambio motor electrico stand by y se alineo las poleas y templado de correas"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":51},"Se calibro el sensor de final de carrera ."]
[{"$nulls":3},"BOMBAS NOVA 4",{"$nulls":51},"Se realizo el mantenimiento del  actuador de la boya,"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":51},"Se cambio, se alineo y templo las correas de transmision"]
[{"$nulls":3},"BOMBA # 01 DE CELDA SK 240",{"$nulls":51},"Se cambio el impulsor y se desareno la linea de alimentaion"]
[{"$nulls":3},"CHANCADORA SECUNDARIA ",{"$nulls":51},"Se cambio, se alineo y templo las correas de transmision"]
[{"$nulls":3},"FAJA N° 7",{"$nulls":51},"Se cambio el motoreductor y se templo la cadena del sistema de transmision"]
[{"$nulls":3},"BOMBA 77 A",{"$nulls":51},"Se cambio, se alineo y templo las correas de transmision"]
[{"$nulls":3},"CELDA SP-18 ",{"$nulls":51},"Se cambio, se alineo y templo las correas de transmision"]
[{"$nulls":3},"FAJA 5D DE CHANCADO",{"$nulls":51},"Se realizo el pegado del empalme sueltop de la banda transportadora"]
[{"$nulls":3},"COMPRESORA TS 20 DE FILTRO PRENSA ",{"$nulls":51},"Se realizó la Inspección por el proveedor dejando operativo el equipo( cables de control en mal estado y suelto), se dejo seteado la presion a 120 psi y la temperatura a 170  ºF, con al observacion de realizar la reparacion de la valvula espiral(se dejo anulado)."]
[null,null,"SEMANA N°8","FAJA TRANSPORTADORA DE ALIMENTO AL MOLINO 8X11",{"$nulls":51},"Se retiro el angulo, se verifico los cortes y se resano banda"]
[{"$nulls":3},"BOMBA MARS 04",{"$nulls":51},"Cambio de pernos de media luna de la botella de mezcla"]
[{"$nulls":3},"BOMBA 1.5 COURIER CONCENTRADO DE PLOMO",{"$nulls":51},"Resane de fisuras en la tuberia de descarga"]
[{"$nulls":3},"BOMBA HIDROSTAL EF05 Nº1",{"$nulls":51},"Cambio de sellos mecanicos de la bomba"]
[{"$nulls":3},"FAJA 5C DE CHANCADO",{"$nulls":51},"Cambio de cadena de transmision RS 100"]
[{"$nulls":3},"BOMBA MARS 02",{"$nulls":51},"Cambio de valvula de descarga"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":51},"Reparacion de mallas"]
[null,null,"SEMANA N°9","BOMBA DE LODOS N° 6",{"$nulls":51},"Se realizo limpieza e inspeccion de componentes del sistema de bombeo"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":51},"Se cambio chumaceras y se alineo el sistema de transmision"]
[{"$nulls":3},"BOMBA 77 B",{"$nulls":51},"Se cambio bocina y se hizo limpieza en la tuberia de alimento"]
[{"$nulls":3},"BOMBA PERISTATICA Nª3 DE CAL",{"$nulls":51},"Se cambio reten de la bomba peristaltica"]
[{"$nulls":3},"CEDAZO 01",{"$nulls":51},"Falla en el sistema de selección de mineral(malla sflex)"]
[{"$nulls":3},"CEDAZO 02",{"$nulls":51},"Se cambio chumaceras y se alineo el sistema de transmision"]
[{"$nulls":3},"BOMBA 77 \"A\"",{"$nulls":51},"Se realizo la reparacion de la tuberia de descarga"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Se envio la unidad compresora para su reparacion al proveedor"]
[null,null,"SEMANA N°10","BOMBAS MARS 04",{"$nulls":51},"Se cambio asiento de valvula e inspecciono desgaste de componentes internos"]
[{"$nulls":3},"CICLON DE RELAVERA",{"$nulls":51},"Se cambio manga pinch de 6\" de la linea de descarga del ciclon"]
[{"$nulls":3},"BOMBA DE LODOS # 04",{"$nulls":51},"Se cambio caja de rodamientos stand by"]
[{"$nulls":3},"BOMBA Nº106 - ESPESADOR DE ZINC",{"$nulls":51},"Se cambio motor electrico stand by"]
[{"$nulls":3},"ESPESADOR DE ZINC",{"$nulls":51},"Se cambio manga pinch de 6\"de valvula de descarga "]
[{"$nulls":3},"CHANCADORA PRIMARIA",{"$nulls":51},"Se cambio perno de forro movil superior roto"]
[{"$nulls":3},"CEDAZO Nº01 - CHANCADO",{"$nulls":51},"Se cambio malla de 10 mm para la selección de mineral"]
[{"$nulls":3},"BOMBA MARS Nº04",{"$nulls":51},"Se cambio asiento de valvula e inspecciono desgaste de componentes internos"]
[{"$nulls":3},"BOMBA VERTICAL 2.5 STD DE RETORNO DE COURIER Nº02",{"$nulls":51},"Se cambio forros y se desareno la linea de alimentacion"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Se envio la unidad compresora para su reparacion al proveedor"]
[null,null,"SEMANA N°11","FAJA Nº 03 DE CHANCADO",{"$nulls":51},"Alineamiento de banda transportadora y toma de parametros del motorreductor"]
[{"$nulls":3},"MOLINO Nº2",{"$nulls":51},"Cambio de eje y volante, cambio de rodamientos, cambio de pernos de acoplamiento y alineamiento del sistema de transmision"]
[{"$nulls":3},"BOMBA 104",{"$nulls":51},"Cambio de forros por nuevo modelo con rotulacion blanca (reymosa)"]
[{"$nulls":3},"BOMBA VERTICAL 1,5 Nº09 DEL ESPESADOR DE RELAVE",{"$nulls":51},"Cambio de 04 fajas de transmision y alineamiento del sistema polea - motor"]
[{"$nulls":3},"ESPESADOR DE ZINC",{"$nulls":51},"Cambio de manga"]
[{"$nulls":3},"CEDAZO Nº01",{"$nulls":51},"Cambio de 06 fajas de transmision y alineamiento del sistema polea - motor"]
[{"$nulls":3},"BOMBA 106",{"$nulls":51},"Cambio de manga"]
[{"$nulls":3},"FAJA Nº01 DE PB",{"$nulls":51},"Tensado de cadena de transmision"]
[{"$nulls":3},"FAJA Nº 02 DE CHANCADO",{"$nulls":51},"Modificacion de estructura que soporta al electroiman"]
[null,null,"SEMANA N°12","BOMBA MARS L-180 N° 4",{"$nulls":51},"Cambio de correas de transmision y alineamiento"]
[{"$nulls":3},"CEDAZO # 01",{"$nulls":51},"Cambio de correas de transmision y alineamiento"]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":51},"Cambio pernos de fijacion de los tacos de las placas "]
[{"$nulls":3},"FAJA TRANSPORTADORA N°5D ",{"$nulls":51},"Resane de empalme de  banda transportadora por presencia de carga abrasiva"]
[{"$nulls":3},"BOMBA CENTRIFUGA 77 A, 6X4 AH WARMAN ",{"$nulls":51},"Cambio de correas de transmision y alineamiento"]
[{"$nulls":3},"BOMBA VERTICAL 1.5 DE RELAVE GENERAL ",{"$nulls":51},"Cambio de correas de transmision y alineamiento"]
[{"$nulls":3},"CEDAZO #01",{"$nulls":51},"Cambio de mallas para seleccion de mineral"]
[{"$nulls":3},"COMPRESORA TS20 #01",{"$nulls":51},"Cambio de acople omega de 20\" y alineamiento del sistema de transmision"]
[{"$nulls":3},"COMPRESORA TS20 #01",{"$nulls":51},"Cambio de acoplamiento omega y reseteo de panel de control"]
[{"$nulls":3},"CEDAZO # 02 ",{"$nulls":51},"Cambio de  paneles(03 unidades)"]
[{"$nulls":3},"SOPLADOR SPENCER",{"$nulls":51},"Mantenimiento del arranque de motor electrico y alineamiento del sistema de transmision"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Equipo fuera de servicio(en reparacion)"]
[null,null,"SEMANA N°13","BOMBA DE CICLON DE CAL ",{"$nulls":51},"Cambio de forros del sistema de bombeo ",{"$f":"CONCATENATE(D187,\"; \",BD187)","v":"BOMBA DE CICLON DE CAL ; Cambio de forros del sistema de bombeo "}]
[{"$nulls":3},"MOTOR DE ZARANDA DE ALTA FRECUENCIA",{"$nulls":51},"Cambio de rodamientos del motor",{"$f":"CONCATENATE(D188,\"; \",BD188)","v":"MOTOR DE ZARANDA DE ALTA FRECUENCIA; Cambio de rodamientos del motor"}]
[{"$nulls":3},"LÍNEA DE DESCARGA DE HIDROCICLÓN RELAVE",{"$nulls":51},"Reparacion de tuberia de descarga del ciclon ","LÍNEA DE DESCARGA DE HIDROCICLÓN RELAVE; Reparacion de tuberia de descarga del ciclon "]
[{"$nulls":3},"BOMBA DE LODOS Nº 4",{"$nulls":51},"Cambio de bocina, ajuste de estopas del sistema de bombeo","BOMBA DE LODOS Nº 4; Cambio de bocina, ajuste de estopas del sistema de bombeo"]
[{"$nulls":3},"FAJA 1 DE CAL",{"$nulls":51},"Cambio de raspador del sistema de transport de carga","FAJA 1 DE CAL; Cambio de raspador del sistema de transport de carga"]
[{"$nulls":3},"BOMBA HORIZONTAL 103",{"$nulls":51},"Cambio de forros del sistema de bombeo ","BOMBA HORIZONTAL 103; Cambio de forros del sistema de bombeo "]
[{"$nulls":3},"FILTRO PRENSA",{"$nulls":51},"Cambio de manguera, aceite y filtros del sistema hidraulico","FILTRO PRENSA; Cambio de manguera, aceite y filtros del sistema hidraulico"]
[{"$nulls":3},"COMPRESORA TS 20 FILTRO PRENSA",{"$nulls":51},"Equipo fuera de servicio(en reparacion)","COMPRESORA TS 20 FILTRO PRENSA; Equipo fuera de servicio(en reparacion)"]